## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bajkul Zone-I | SM/12489 | Augmentation | Laying of Distribution pipe line to accommodate FHTC(2596 Nos) with construction of R.C.C. Elevated Reservoir of capacity 400 cum and staging height 20.00 mtr. as per Departmental Drawing with allied works for Augmentation of Bajkul Zone - I Water Supply Scheme within Bhagabanpur- II Block under Contai Sub-Division of Tamluk Division P.H.E.DTE. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000486/2022-2023 | 1892/TD | 24/11/2022 | 26/11/2026 | BANDHAB ENGINEERS CO-OPERATIVE SOCIETY LTD. | 440.22 | 264.92 | 60.18 | 78
2 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bajkul Zone-I | SM/12489 | Augmentation | Sinking of 3 (Three) nos. Tube Well at different sites. Name of Sites: i) Sinking of 250mm. x 150mm. dia. x 225 mtr. Deep Tube well by direct rotary rig method for 1st Tube Well (Mouza- Kismat Bajkul, JL No. 156) of Augmentation of Bajkul Zone-I Water Supply Scheme within Bhagwanpur- II Block under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. ii) Sinking of 250mm. x 150mm. dia. x 225 mtr. Deep Tube well by direct rotary rig method for 2nd Tube Well (Mouza- Kismat Bajkul, JL No. 156) of Augmentation of Bajkul Zone-I Water Supply Scheme within Bhagwanpur- II Block under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. iii) Sinking of 250mm. x 150mm. dia. x 225 mtr. Deep Tube well by direct rotary rig method for 3rd Tube Well (Mouza- Kismat Bajkul, JL No. 156) of Augmentation of Bajkul Zone-I Water Supply Scheme within Bhagwanpur- II Block under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000560/2022-2023 | 2243/TD | 29/12/2022 | 07/02/2023 | R K CONSTRUCTION | 39.67 | 12.07 | 30.42 | 0
3 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bajkul Zone-I | SM/12489 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Bajkul Water Supply Scheme (Zone-I) under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000888/2021-2022 | 1802/TD | 08/02/2022 | 28/02/2022 | GEOTECHNICAL ENGINEERS CONSORTIUM | 4.79 | 3.3 | 69.01 | 100
4 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bajkul Zone-I | SM/12489 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000115/2022-2023 | 1670/TD | 03/11/2022 | 03/11/2022 | Resource Division | 95.79 | 0 | 0 | 0
5 | PURBA MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Bajkul Zone-I | SM/12489 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Piped Water Supply Scheme for Bajkul Zone-I, Block Bhagawanpur II, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001915/2022-2023 | 818/W/MMD | 24/03/2023 | 20/09/2023 | EMCON | 11.83 | 11 | 92.95 | 100
6 | PURBA MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Bajkul Zone-I | SM/12489 | Augmentation | Hiring of inspection vehicle for supervision and monitoring of different on-going piped water supply scheme for covering Contai Sub-Division and its adjacent Sub-Division under the Dist. of Purba Medinipur under Jal Jeevan Mission programe. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000749/2023-2024 | 688/HESD | 29/08/2023 | 29/08/2024 | S.S.GHORAI | 2.12 | 0 | 0 | 50
7 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bajkul Zone-I | SM/12489 | Augmentation | Laying of Left-Out portion uPVC Pipe line, Construction of New Pump House, Boundary Wall and others allied works for 3rd Tube well site and Repair & renovation and others allied works of Pump House, Boundary Wall for head works (1st. Tube well) site and 2nd Tube well site at mouza- Kismat Bajkul,J.L- No -156, under Bajkul Zone-I Water Supply Scheme. ( Augmentation) in Bhagabanpur-II Block within Contai Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000575/2023-2024 | 2184/TD | 01/09/2023 | 21/09/2026 | BANDHAB ENGINEERS CO-OPERATIVE SOCIETY LTD. | 65.41 | 0 | 0 | 70
8 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bajkul Zone-I | SM/12489 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000023/2023-2024 | 607/TD | 17/05/2023 | 17/05/2023 | Resource Division | 15.99 | 0 | 0 | 0
9 | PURBA MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Bajkul Zone-I | SM/12489 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk and replacement Tube well at BAJKUL zone I Water supply scheme, BHAGWANPUR - II block, District - Purba Medinipur under Midnapore Mechanical Division P.H.E. Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/002728/2023-2024 | 1077/W/MMD | 15/03/2024 | 11/09/2024 | SOUMEN ELECTRIC | 24.86 | 8.41 | 33.82 | 35
10 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bajkul Zone-I | SM/12489 | Augmentation | Quotation money for shifting of 11 KV OH Henria Feeder at Bajkul for Bajukl Zone-I PWSS under Tamluk Division, PHE Dte. |  |  | BILL/01686/2023-2024 | BP-2023-24-744 | 04/01/2024 | 04/01/2024 | WBSEDCL | 2.08 | 0 | 0 | 0
11 | PURBA MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Bajkul Zone-I | SM/12489 | Augmentation | FUEL CHARGES BILL FOR VEHICLE NO-WB31-9339. W/O NO-688/HESD DATED-29.08.2023. FOR THE MONTH OF NOVEMBER'2023 UNDER HESD, PHE DTE |  |  | BILL/04351/2025-2026 |  | 14/01/2026 | 14/01/2026 | S.S.GHORAI | 0.19 | 0 | 0 | 0
12 | PURBA MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Bajkul Zone-I | SM/12489 | Augmentation | FUEL CHARGES BILL FOR VEHICLE NO-WB31-9339. W/O NO-832/W/MMD DATED-28.08.2024. FOR THE MONTH OF OCT'2024 UNDER HESD, PHE DTE |  |  | BILL/04362/2025-2026 |  | 14/01/2026 | 14/01/2026 | S.S.GHORAI | 0.16 | 0 | 0 | 0
Total | [13 empty] | 703.12 | 299.7 | 42.62