## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bajkul Zone-II | SM/12490 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Bajkul Water Supply Scheme (Zone-II) under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000889/2021-2022 | 1803/TD | 08/02/2022 | 28/02/2022 | GEOTECHNICAL ENGINEERS CONSORTIUM | 4.79 | 3.32 | 69.3 | 100
2 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bajkul Zone-II | SM/12490 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000116/2022-2023 | 1671/TD | 03/11/2022 | 03/11/2022 | Resource Division | 39.54 | 0 | 0 | 0
3 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bajkul Zone-II | SM/12490 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000024/2023-2024 | 608/TD | 17/05/2023 | 17/05/2023 | Resource Division | 13.82 | 0 | 0 | 0
4 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bajkul Zone-II | SM/12490 | Augmentation | Name of Work: Sinking of 4 (Four) nos. Tube Well at different sites. Name of Sites: i) Sinking of 250mm. x 150mm. dia. x 225 mtr. Deep Tube well by direct rotary rig method for 1st Tube Well (Mouza- Pora Chingra, JL No. 155) of Augmentation of Bajkul Zone-II Water Supply Scheme within Bhagwanpur- II Block under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. ii) Sinking of 250mm. x 150mm. dia. x 225 mtr. Deep Tube well by direct rotary rig method for 2nd Tube Well (Mouza- Kismat Bajkul, JL No. 156) of Augmentation of Bajkul Zone-II Water Supply Scheme within Bhagwanpur- II Block under Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. iii) Sinking of 300mm. x 200mm. dia. x 225 mtr. Deep Tube well by direct rotary rig method for 3rd Tube Well (Mouza- Kismat Bajkul, JL No. 156) of Augmentation of Bajkul Zone-III Water Supply Scheme under Bhagwanpur- II Block of Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. iv) Sinking of 300mm. x 200mm. dia. x 225 mtr. Deep Tube well by direct rotary rig method for Additional Tube Well (Mouza- Kismat Bajkul, JL No. 156) of Augmentation of Bajkul Zone-III Water Supply Scheme under Bhagwanpur- II Block of Contai Sub-Division, of Tamluk Division P.H.E. Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000561/2022-2023 | 2244/TD | 29/12/2022 | 07/02/2023 | PRANTIK DRILLING AGENCY | 61.68 | 23.98 | 38.87 | 90
5 | PURBA MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Bajkul Zone-II | SM/12490 | Augmentation | Electric Quotation for BAJKUL Water Supply Scheme T/W-I, Zone- II, (Ref. ID-204114262) |  |  | BILL/03058/2023-2024 | BP-2023-24-374 | 01/12/2023 | 01/12/2023 | WBSEDCL | 3.48 | 0 | 0 | 0
6 | PURBA MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Bajkul Zone-II | SM/12490 | Augmentation | Electric Quotation for BAJKUL Water Supply Scheme T/W-II, Zone- II, (Ref. ID-204114267) |  |  | BILL/03059/2023-2024 | BP-2023-24-375 | 02/12/2023 | 02/12/2023 | WBSEDCL | 4.77 | 0 | 0 | 0
7 | PURBA MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Bajkul Zone-II | SM/12490 | Augmentation | Additional Quotation Bill for the Service connection at T/W NO-I , ZONE-II Of BAJKUL W/S Scheme Under Jal Jeevan Mission under MMD, PHE, Dte. Block- BHAGWANPUR-II, WBSEDCL SUPPLY OFFICE: KHEJURI C.C.C. Ref. Memo No-KJR/QTN/200 DT. 25-06-2024 Application NO- 100000111551 DT. 25-06-2024 Application type-ADDITIONAL QUOTATION FOR SERVICE CONNECTION REF. Id- 860303091 |  |  | BILL/01400/2024-2025 | BP-2024-25-379 | 08/07/2024 | 08/07/2024 | WBSEDCL | 0.53 | 0 | 0 | 0
8 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bajkul Zone-II | SM/12490 | Augmentation | Laying of Distribution pipe line to accommodate FHTC (2244 Nos) with construction of R.C.C. Elevated Reservoir of capacity 300 cum and staging height 20.00 mtr. as per Departmental Drawing with allied works for Augmentation of Bajkul Zone - II Water Supply Scheme within Bhagabanpur- II Block under Contai Sub-Division of Tamluk Division P.H.E.DTE. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000494/2022-2023 | 1891/TD | 24/11/2022 | 01/12/2025 | MAA ANANDAMAYEE | 407.46 | 227.81 | 55.91 | 50
9 | PURBA MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Bajkul Zone-II | SM/12490 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Piped Water Supply Scheme for Bajkul Zone-II, Block Bhagawanpur II, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001980/2022-2023 | 819/W/MMD | 24/03/2023 | 20/09/2023 | S.K.ENTERPRISE | 23.7 | 21.81 | 92.05 | 85
10 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bajkul Zone-II | SM/12490 | Augmentation | Laying of Left-Out portion uPVC Pipe line, Construction of New Pump House, Boundary Wall and others allied works for 3rd Tube well site and Repair & renovation and others allied works of Pump House, Boundary Wall for head works (1st. Tube well) site and 2nd Tube well site at mouza- Kismat Bajkul,J.L- No -156, under Bajkul Zone-II Water Supply scheme. ( Augmentation) in Bhagabanpur-II Block within Contai Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000577/2023-2024 | 2185/TD | 01/09/2023 | 10/10/2025 | MAA ANANDAMAYEE | 84.88 | 37.42 | 44.09 | 60
11 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bajkul Zone-II | SM/12490 | Augmentation | Brick bats road due to smoothly carring Rig Machine and soil testing equipment for Head Works site at Mouza-Pora Chingra, J.L. NO.-155, under Bajkul Zone-II W/S Scheme (Augmentation) within Bhagwanpur-II Block under Contai Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000841/2023-2024 | 1705/CSD | 31/08/2023 | 15/09/2023 | M/S MONDAL CONSTRUCTION & CO. | 0.8 | 0 | 0 | 0
Total | [13 empty] | 645.47 | 314.35 | 48.7