## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Narandia | SM/12491 | Augmentation | Preparation of D.P.R. for different works for providing Functional Household Tap Connection (FHTC) by Augmentation of Narandiha Water Supply Scheme under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000325/2021-2022 | 1618/TD | 14/01/2022 | 03/02/2022 | GEOTECHNICAL ENGINEERS CONSORTIUM | 3.06 | 0 | 0 | 100
2 | PURBA MEDINIPUR |  | Central Drilling | Augmentation of Ground Water Based Piped Water Supply Scheme for Narandia | SM/12491 | Augmentation | Providing Drilling crew and other allied works for construction of Tube well (300mm x 200mm x 220 mtrs. Depth) by utilising Departmental machineries for Narandiha W/S Scheme (TW-III), Ramnagar-II block under Purba Midnapore District, CDD PHE Dte. | Driller In Charge | Junior Engineer | ORD/000011/2023-2024 | 14/CDD | 04/04/2023 | 04/05/2023 | MENAKA ENTERPRISE | 17.39 | 0 | 0 | 100
3 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Narandia | SM/12491 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000280/2022-2023 | 2619/TD | 02/02/2023 | 02/02/2023 | Resource Division | 41.76 | 0 | 0 | 0
4 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Narandia | SM/12491 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000285/2022-2023 | 2638/TD | 02/02/2023 | 02/02/2023 | Resource Division | 19.64 | 0 | 0 | 0
5 | PURBA MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Narandia | SM/12491 | Augmentation | Electric Quotation for NARANDIHA Water Supply Scheme T/W-III, (Ref. ID-204068440) |  |  | BILL/01931/2023-2024 | BP-2023-24-236 | 08/09/2023 | 08/09/2023 | WBSEDCL | 3.76 | 0 | 0 | 0
6 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Narandia | SM/12491 | Augmentation | Laying of distribution pipe line to accommodate FHTC with new construction of R.C.C. Elevated Reservoir of capacity 400cum and staging height 20.00 mtr. as per Departmental Drawing with allied works including supply of all labour & materials for Augmentation of NARANDIA PWSS Scheme In Ramnagar-II Block under Digha Sub-Division of Tamluk Division, P.H.E.Dte, Purba Medinipur.(Part-A) | Assistant Engineer | Junior Engineer | ORD/000554/2022-2023 | 2182/TD | 20/12/2022 | 18/06/2023 | MAITY CONSTRUCTION | 299.31 | 0 | 0 | 42
7 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Narandia | SM/12491 | Augmentation | Laying of distribution pipe line to accommodate FHTC with new construction of Pump House for Augmentation of NARANDIHA PWSS Scheme In Ramnagar-II Block under Digha Sub-Division of Tamluk Division, P.H.E.Dte, Purba Medinipur.(Part-B) | Assistant Engineer | Junior Engineer | ORD/000555/2022-2023 | 2181/TD | 20/12/2022 | 18/02/2023 | MAITY CONSTRUCTION | 112.72 | 0 | 0 | 80
8 | PURBA MEDINIPUR |  | Central Drilling | Augmentation of Ground Water Based Piped Water Supply Scheme for Narandia | SM/12491 | Augmentation | Providing drilling crew and other allied works for construction of Tube Well ( 300mm X200mm X 220 Mtrs. Depth) by utilising Departmental Machineries for Narandiha W/S Scheme (T/W-I) , Ramangar-II Block under Purba Medinipur District, Central Drilling Division, P.H.E. Dte. | Driller In Charge | Junior Engineer | ORD/000182/2023-2024 | 13/CDD | 04/04/2023 | 29/10/2024 | MENAKA ENTERPRISE | 17.39 | 0 | 0 | 100
9 | PURBA MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Narandia | SM/12491 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Piped Water Supply Scheme for Narandia, Block Ramnagar II, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division | ORD/001978/2022-2023 | 817/W/MMD | 24/03/2023 | 20/09/2023 | S.K.ENTERPRISE | 35.55 | 0 | 0 | 40
10 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Narandia | SM/12491 | Augmentation | Soil Investigation work in Connection of Construction of R.C.C. Over Head Reservoir (Capacity - 400 Cum) due to change of land with Laying of Balance Distribution Pipe Line for Provided balance FHTC and other allied works of Narandiha Piped Water Supply Scheme within Ramnagar-II Block under Digha Sub-Division of Tamluk Division,PHE Dte., Purba Medinipur. |  |  | ORD/000639/2024-2025 | 851/TD | 19/03/2025 | 18/04/2025 | MAITY CONSTRUCTION | 48.33 | 0 | 0 | 0
11 | PURBA MEDINIPUR |  | Tamluk Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Narandia | SM/12491 | Augmentation | Construction of Boundary Wall (as per Departmental Design & Drawing) at Head work site for Narandiha W/S Scheme within Ramnagar -II Block under Digha Sub-Division of Tamluk Division, P.H.E.Dte.Purba Medinipur.(Lenght-146 Mtr.) | Assistant Engineer | Junior Engineer | ORD/000194/2023-2024 | 395/TD | 27/04/2023 | 06/06/2023 | VENUS ENGINEERS CO-OPERATIVE SOCIETY LTD. | 13.72 | 0 | 0 | 100
Total | [13 empty] | 612.63 | 0 | 0