## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Bhagawanpur-I | Tamluk Division | SIMULYA & IT'S ADJOINING MOUJAS PWSS | SM/12492 | New | Material Requisition To Resource Division |  |  | RTOR000242/2022-2023 | 2725/TD | 06/02/2023 | 06/02/2023 | Resource Division | 58.93 | 0 | 0 | 0
2 | PURBA MEDINIPUR | Bhagawanpur-I | Tamluk Division | SIMULYA & IT'S ADJOINING MOUJAS PWSS | SM/12492 | New | Preparation of design based on soil test report and submission of drawing of foundation for construction of 350 cum RCC OHR at Simulya PWSS at Bhagwanpur-I Block under Tamluk Division, PHE Dte. | Assistant Engineer, Headquaters |  | ORD/000193/2024-2025 | 2203/TD | 09/07/2024 | 19/07/2024 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.95 | 0.95 | 100 | 100
3 | PURBA MEDINIPUR | Bhagawanpur-I | Midnapore Mechanical | SIMULYA & IT'S ADJOINING MOUJAS PWSS | SM/12492 | New | Quotation Bill for New Service connection at T/W NO-II Of SIMULIA W/S Scheme under MMD, PHE, Dte. Block- BHAGWANPUR-I, WBSEDCL SUPPLY OFFICE: BHAGWANPUR C.C.C. Ref. Memo No-2004691120/QUOT/03 DT. 19-04-2024 Application NO- 2004691120 Application type-New connection Consumer Id- 204280540 |  |  | BILL/00704/2024-2025 | BP-2024-25-142 | 09/05/2024 | 09/05/2024 | WBSEDCL | 11.94 | 0 | 0 | 0
4 | PURBA MEDINIPUR | Bhagawanpur-I | Midnapore Mechanical | SIMULYA & IT'S ADJOINING MOUJAS PWSS | SM/12492 | New | Quotation Bill for New Service connection at T/W NO-I Of SIMULIA W/S Scheme under MMD, PHE, Dte. Block- BHAGWANPUR-I, WBSEDCL SUPPLY OFFICE: BHAGWANPUR C.C.C. Ref. Memo No-2004686956/QUOT/03 DT. 19-04-2024 Application NO- 2004686956 Application type-New connection Consumer Id- 204277583 |  |  | BILL/00703/2024-2025 | BP-2024-25-143 | 09/05/2024 | 09/05/2024 | WBSEDCL | 2.78 | 0 | 0 | 0
5 | PURBA MEDINIPUR | Bhagawanpur-I | Midnapore Mechanical | SIMULYA & IT'S ADJOINING MOUJAS PWSS | SM/12492 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for SIMULYA and ADJOINING MOUJAS, Block - Bhagawanpur I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001653/2022-2023 | 525/W/MMD | 20/03/2023 | 16/09/2023 | BHABANI PRASAD MANNA | 23.7 | 19.94 | 84.12 | 80
6 | PURBA MEDINIPUR | Bhagawanpur-I | Tamluk Division | SIMULYA & IT'S ADJOINING MOUJAS PWSS | SM/12492 | New | Sinking of Tube Well ,Construction of Pump House ,350 cum OHR (Intze type with pile foundation), Rising main, Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC (2740 nos) under JJM with allied work including 02(two) Years Operation & Maintenance of SIMULYA PWSS within Bhagwanpur-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer,Assistant Engineer, Headquaters | Junior Engineer | ORD/000221/2023-2024 | 451/TD | 04/05/2023 | 26/09/2025 | TARUN KOLEY | 663.05 | 209.12 | 31.54 | 35
Total | [13 empty] | 761.36 | 230.01 | 30.21