## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Mahisadal | Tamluk Division | BAMANPUR AND ADJOINING MOUJAS PWSS | SM/12493 | New | Material Requisition To Resource Division |  |  | RTOR000330/2022-2023 | 2986/TD | 27/02/2023 | 27/02/2023 | Resource Division | 15.66 | 0 | 0 | 0
2 | PURBA MEDINIPUR | Mahisadal | Tamluk Division | BAMANPUR AND ADJOINING MOUJAS PWSS | SM/12493 | New | Payment of WBSEDCL for Quotation of Shifting of 11 KV HTOH Line under Tamluk Division, PHE Dte. |  |  | BILL/01480/2023-2024 | BP-2023-24-665 | 15/12/2023 | 15/12/2023 | WBSEDCL | 5.18 | 0 | 0 | 0
3 | PURBA MEDINIPUR | Mahisadal | Tamluk Division | BAMANPUR AND ADJOINING MOUJAS PWSS | SM/12493 | New | Ground water based Bamanpur Water Supply Scheme by providing Laying of Distribution pipe line and FHTC work within Mahishadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-C) | Assistant Engineer | Junior Engineer | ORD/000136/2023-2024 | 277/TD | 20/04/2023 | 15/05/2023 | TARUN KHATUA | 19.88 | 0 | 0 | 60
4 | PURBA MEDINIPUR | Mahisadal | Tamluk Division | BAMANPUR AND ADJOINING MOUJAS PWSS | SM/12493 | New | Ground water based Bamanpur Water Supply Scheme by providing Laying of Distribution pipe line and FHTC (240 nos.) work within Mahishadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. (Part-G+H+I) | Assistant Engineer | Junior Engineer | ORD/000137/2023-2024 | 278/TD | 20/04/2023 | 04/06/2023 | BHOLANATH DEY | 90.98 | 0 | 0 | 76
5 | PURBA MEDINIPUR | Mahisadal | Tamluk Division | BAMANPUR AND ADJOINING MOUJAS PWSS | SM/12493 | New | Ground water based Bamanpur Water Supply Scheme by providing Laying of Distribution pipe line and FHTC work within Mahishadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. (Part-J+K) | Assistant Engineer | Junior Engineer | ORD/000138/2023-2024 | 279/TD | 20/04/2023 | 20/05/2023 | AMMON ENGINEERS CO-OPERATIVE SOCIETY LTD. | 33.8 | 0 | 0 | 80
6 | PURBA MEDINIPUR | Mahisadal | Tamluk Division | BAMANPUR AND ADJOINING MOUJAS PWSS | SM/12493 | New | Ground water based Bamanpur Water Supply Scheme by providing Laying of Distribution pipe line and FHTC (480 nos.) work and Construction of R.C.C. Over Head Reservoir of capacity 150 cum and staging height 20.00 mtr. with allied work including Sub Soil Investigation within Mahishadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-B) | Assistant Engineer | Junior Engineer | ORD/000411/2023-2024 | 1097/TD | 08/06/2023 | 05/12/2023 | SUSIL KUMAR HAZRA | 104.34 | 0 | 0 | 10
7 | PURBA MEDINIPUR | Mahisadal | Tamluk Division | BAMANPUR AND ADJOINING MOUJAS PWSS | SM/12493 | New | Canal Crossing Structure for Laying Distribution (Nodal Point -161-163, 378-382, R1 - 1, 12-16) Pipe line of Bamanpur Water Supply Scheme under Haldia Sub- Division of Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000649/2023-2024 | 2615/TD | 11/10/2023 | 10/11/2023 | TARUN KHATUA | 8.77 | 0 | 0 | 100
8 | PURBA MEDINIPUR | Mahisadal | Tamluk Division | BAMANPUR AND ADJOINING MOUJAS PWSS | SM/12493 | New | Material Requisition To Resource Division |  |  | RTOR000117/2023-2024 | 81/TD | 05/01/2024 | 05/01/2024 | Resource Division | 8.39 | 0 | 0 | 0
9 | PURBA MEDINIPUR | Mahisadal | Midnapore Mechanical | BAMANPUR AND ADJOINING MOUJAS PWSS | SM/12493 | New | Quotation for new connection at Bamanpur w/s scheme PH I in the district of Purba Medinipur under MMD PHE Dte. ( App No 2004732591, Ref ID 204305895) |  |  | BILL/01366/2024-2025 | BP-2024-25-376 | 08/07/2024 | 08/07/2024 | WBSEDCL | 10.38 | 0 | 0 | 0
10 | PURBA MEDINIPUR | Mahisadal | Midnapore Mechanical | BAMANPUR AND ADJOINING MOUJAS PWSS | SM/12493 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for BAMANPUR and ADJOINING MOUJAS, Block - Mahishadal, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/001600/2022-2023 | 504/W/MMD | 20/03/2023 | 31/08/2025 | SUJOY RANJAN BHOWMICK | 21.62 | 0 | 0 | 50
11 | PURBA MEDINIPUR | Mahisadal | Tamluk Division | BAMANPUR AND ADJOINING MOUJAS PWSS | SM/12493 | New | Ground water based Bamanpur Water Supply Scheme by providing Construction of Pump House, Boundary Wall, Laying of Rising main, Laying of Distribution pipe line and FHTC (425 nos.)work within Mahishadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. (Part-D+E+F) | Assistant Engineer | Junior Engineer | ORD/000665/2023-2024 | 2678/TD | 16/10/2023 | 26/07/2025 | SK. SARFARAJ | 93.13 | 0 | 0 | 10
12 | PURBA MEDINIPUR | Mahisadal | Tamluk Division | BAMANPUR AND ADJOINING MOUJAS PWSS | SM/12493 | New | Land development of Head work site at Bamanpur Water Supply Scheme within Mahishadal Development Block under Haldia Sub-Division, PEH Dte. | Assistant Engineer | Junior Engineer | ORD/000294/2025-2026 | 638/HSD, | 12/06/2025 | 22/06/2025 | M/S SOURAV MAHAPATRA | 2.27 | 0 | 0 | 0
13 | PURBA MEDINIPUR | Mahisadal | Tamluk Division | BAMANPUR AND ADJOINING MOUJAS PWSS | SM/12493 | New | Sinking of 4 (Four) nos. Tube Well at different sites. Name of Sites: i) Sinking of 250mm. x 150mm. dia. x 280 mtr. Deep additional Tube well by direct rotary rig method at 1st Tube well Site of Bamanpur Water Supply Scheme within Mahishadal Dev. Block under Haldia Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. ii) Sinking of 250mm. x 150mm. dia. x 280 mtr. Deep additional Tube well by direct rotary rig method at 2nd Tube well Site of Bamanpur Water Supply Scheme within Mahishadal Dev. Block under Haldia Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. iii) Sinking of 250mm. x 150mm. dia. x 280 mtr. Deep additional Tube well by direct rotary rig method at 1st Tube well Site of Madhya Hingli Water Supply Scheme within Mahishadal Dev. Block under Haldia Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. iv) Sinking of 250mm. x 150mm. dia. x 280 mtr. Deep additional Tube well by direct rotary rig method at 2nd Tube well Site of Madhya Hingli Water Supply Scheme within Mahishadal Dev. Block under Haldia Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000898/2022-2023 | 3348/TD | 22/03/2023 | 19/12/2024 | M/S SYCHROTECH INDUSTRY | 62.36 | 0 | 0 | 100
Total | [13 empty] | 476.76 | 0 | 0