## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Egra-I | Tamluk Division | SHWNIA AND ADJOINING MOUJAS PWSS | SM/12494 | New | Material Requisition To Resource Division |  |  | RTOR000129/2022-2023 | 2413/TD | 16/01/2023 | 16/01/2023 | Resource Division | 19.96 | 0 | 0 | 0
2 | PURBA MEDINIPUR | Egra-I | Midnapore Mechanical | SHWNIA AND ADJOINING MOUJAS PWSS | SM/12494 | New | Quotation For New Service Connections at Tube Well-I of Shwina W/S scheme under MMD PHE Dte. Chorepalia CCC Block- Egra-I Application No.-2004746256 Consumer ID.-204316922 Application Date.-29/05/2024 |  |  | BILL/01138/2024-2025 | BP-2024-25-253 | 06/06/2024 | 06/06/2024 | WBSEDCL | 3.74 | 0 | 0 | 0
3 | PURBA MEDINIPUR | Egra-I | Midnapore Mechanical | SHWNIA AND ADJOINING MOUJAS PWSS | SM/12494 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for SHWNIA and ADJOINING MOUJAS, Block - Egra I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division | ORD/001598/2022-2023 | 502/W/MMD | 20/03/2023 | 31/07/2025 | SRI KRISHNA NIRMAN | 21.57 | 0 | 0 | 53
4 | PURBA MEDINIPUR | Egra-I | Tamluk Division | SHWNIA AND ADJOINING MOUJAS PWSS | SM/12494 | New | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House & Providing Functional Household Tap Connection (61964 Nos) For 38 nos Pipe water supply Scheme including two years Operation & Maintainance within Patashpur-I, Patashpur-II , Egra-I and Deshapran Block Under Tamluk Division PHE Dte. Under Purba Medinipur District. | Assistant Engineer,Assistant Engineer, Headquaters | Junior Engineer | ORD/000677/2023-2024 | 2702/TD | 20/10/2023 | 30/03/2026 | MACKINTOSH BURN LIMITED | 19507.71 | 145.8 | 0.75 | 51
Total | [13 empty] | 19552.98 | 145.8 | 0.75