## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Khejuri-II | Tamluk Division | CHAUDDHA CHULI AND IT'S ADJOINING MOUJAS PWSS | SM/12495 | New | Material Requisition To Resource Division |  |  | RTOR000333/2022-2023 | 2982/TD | 27/02/2023 | 27/02/2023 | Resource Division | 32.13 | 0 | 0 | 0
2 | PURBA MEDINIPUR | Khejuri-II | Midnapore Mechanical | CHAUDDHA CHULI AND IT'S ADJOINING MOUJAS PWSS | SM/12495 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for CHAUDDHA CHULI and ADJOINING MOUJAS, Block - Khejuri II, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/001629/2022-2023 | 513/W/MMD | 20/03/2023 | 16/09/2023 | GLACIER ENGINEERING CO. | 22.79 | 17.58 | 77.15 | 50
3 | PURBA MEDINIPUR | Khejuri-II | Tamluk Division | CHAUDDHA CHULI AND IT'S ADJOINING MOUJAS PWSS | SM/12495 | New | Block Level Orientation Programme involving PRI functionaries on Jal Jeevan Mission at different blocks within Contai Sub- Division under Tamluk division,PHE Dte. Block Name- Khejuri-I, Khejuri-II, Patashpur-I & Patashpur-II ) | Assistant Engineer | Junior Engineer | ORD/001291/2023-2024 | 563/CSD | 14/03/2024 | 24/03/2024 | SAURAV HAZRA | 0.54 | 0.27 | 50.22 | 100
4 | PURBA MEDINIPUR | Khejuri-II | Tamluk Division | CHAUDDHA CHULI AND IT'S ADJOINING MOUJAS PWSS | SM/12495 | New | Sinking Tube well,Pump House ,250 cum OHR (Intze type with pile foundation), Rising main, Laying distribution pipe line, , Boundary Wall, Soil investigation & Accommodate FHTC (1623 nos) including 2 years of Operation Maintenance under JJM with allied work for Chauddha Chuli & its adjoining moujas PWSS in Khajuri-II Block within Contai Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000851/2023-2024 | 74/TD | 05/01/2024 | 25/12/2025 | SRIMANTA KUMAR MAITY | 501.66 | 90.39 | 18.02 | 40
Total | [13 empty] | 557.12 | 108.24 | 19.43