## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Potashpur-I | Tamluk Division | SHOULA BHERI AND ADJOINING MOUJAS PWSS | SM/12496 | New | Material Requisition To Resource Division |  |  | RTOR000142/2022-2023 | 2442/TD | 16/01/2023 | 16/01/2023 | Resource Division | 19.52 | 0 | 0 | 0
2 | PURBA MEDINIPUR | Potashpur-I | Midnapore Mechanical | SHOULA BHERI AND ADJOINING MOUJAS PWSS | SM/12496 | New | Quotation Bill for New Service connection at T/W NO-II Of SHOULABHERI W/S Scheme under MMD, PHE, Dte. Block- PATASHPUR-I, WBSEDCL SUPPLY OFFICE: AMARSHI C.C.C. Ref. Memo No- 2004790382/QUOT/03 DT. 24-06-2024 MEMO NO: AMR/PHE/212 DT. 24-06-2024 Application NO- 2004790382 Application type-New connection Consumer Id- 204339027 |  |  | BILL/01368/2024-2025 | BP-2024-25-374 | 08/07/2024 | 08/07/2024 | WBSEDCL | 2.17 | 0 | 0 | 0
3 | PURBA MEDINIPUR | Potashpur-I | Midnapore Mechanical | SHOULA BHERI AND ADJOINING MOUJAS PWSS | SM/12496 | New | Quotation Bill for New Service connection at T/W NO-I Of SHOULABHERI W/S Scheme under MMD, PHE, Dte. Block- PATASHPUR-I, WBSEDCL SUPPLY OFFICE: AMARSHI C.C.C. Ref. Memo No- 2004790353/QUOT/03 DT. 24-06-2024 MEMO NO: AMR/PHE/211 DT. 24-06-2024 Application NO- 2004790353 Application type-New connection Consumer Id- 204339004 |  |  | BILL/01367/2024-2025 | BP-2024-25-375 | 08/07/2024 | 08/07/2024 | WBSEDCL | 5.65 | 0 | 0 | 0
4 | PURBA MEDINIPUR | Potashpur-I | Midnapore Mechanical | SHOULA BHERI AND ADJOINING MOUJAS PWSS | SM/12496 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for SHOULA BHERI and ADJOINING MOUJAS, Block - Potashpur I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001660/2022-2023 | 529/W/MMD | 20/03/2023 | 25/08/2025 | BHABANI PRASAD MANNA | 25.26 | 0 | 0 | 50
5 | PURBA MEDINIPUR | Potashpur-I | Tamluk Division | SHOULA BHERI AND ADJOINING MOUJAS PWSS | SM/12496 | New | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House & Providing Functional Household Tap Connection (61964 Nos) For 38 nos Pipe water supply Scheme including two years Operation & Maintainance within Patashpur-I, Patashpur-II , Egra-I and Deshapran Block Under Tamluk Division PHE Dte. Under Purba Medinipur District. | Assistant Engineer,Assistant Engineer, Headquaters | Junior Engineer | ORD/000677/2023-2024 | 2702/TD | 20/10/2023 | 30/03/2026 | MACKINTOSH BURN LIMITED | 19507.71 | 255.59 | 1.31 | 51
Total | [13 empty] | 19560.32 | 255.59 | 1.31