## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Contai-I | Tamluk Division | BIRAMPUT AND ADJOINING MOUJAS PWSS | SM/12497 | New | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House & Providing Functional Household Tap Connection (32862 Nos), including 2 years Operation & Maintenance For 21 nos Pipe Water Supply Scheme within MOYNA AND CONTAI -I Block Under Tamluk Division PHE Dte. Under Purba Medinipur District. | Assistant Engineer | Junior Engiener,Junior Engineer | ORD/000538/2023-2024 | 1937/TD | 16/08/2023 | 28/03/2026 | MACKINTOSH BURN LIMITED | 10310.59 | 175.52 | 1.7 | 75
2 | PURBA MEDINIPUR | Contai-I | Midnapore Mechanical | BIRAMPUT AND ADJOINING MOUJAS PWSS | SM/12497 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for BIRAMPUT and ADJOINING MOUJAS, Block - Contai I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division | ORD/001599/2022-2023 | 503/W/MMD | 20/03/2023 | 31/07/2025 | SUJOY RANJAN BHOWMICK | 21.62 | 10.07 | 46.56 | 100
3 | PURBA MEDINIPUR | Contai-I | Tamluk Division | BIRAMPUT AND ADJOINING MOUJAS PWSS | SM/12497 | New | Material Requisition To Resource Division |  |  | RTOR000167/2022-2023 | 2390/TD | 16/01/2023 | 16/01/2023 | Resource Division | 43.89 | 0 | 0 | 0
4 | PURBA MEDINIPUR | Contai-I | Tamluk Division | BIRAMPUT AND ADJOINING MOUJAS PWSS | SM/12497 | New | Preparation of design based on soil test report and submission of drawing of foundation for construction of 150 cum RCC OHR at Biramput PWSS at Contai-I Block under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000155/2024-2025 | 2067/TD | 24/06/2024 | 04/07/2024 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.95 | 0.95 | 100 | 100
5 | PURBA MEDINIPUR | Contai-I | Tamluk Division | BIRAMPUT AND ADJOINING MOUJAS PWSS | SM/12497 | New | Material Requisition To Resource Division |  |  | RTOR000077/2024-2025 | 2951/TD | 12/09/2024 | 12/09/2024 | Resource Division | 5.79 | 0 | 0 | 0
6 | PURBA MEDINIPUR | Contai-I | Tamluk Division | BIRAMPUT AND ADJOINING MOUJAS PWSS | SM/12497 | New | Restoration of damaged road work under WBSRDA, Purba Medinipur after laying of pipe line by PHE for different Piped Water Supply Scheme under Tamluk Division, PHE Dte. |  |  | BILL/01161/2024-2025 | BP-2024-25-607 | 30/10/2024 | 30/10/2024 | EXE-OFFICER, WBSRDA PURBA MEDINIPUR | 60.85 | 0 | 0 | 0
7 | PURBA MEDINIPUR | Contai-I | Midnapore Mechanical | BIRAMPUT AND ADJOINING MOUJAS PWSS | SM/12497 | New | Quotation Bill for New Service connection at T/W NO-I Of BIRAMPUT W/S Scheme under MMD, PHE, Dte. Block- CONTAI-I, CONTAI C.C.C. Ref. Memo No-2004614786/QUOT/03 DT. 23-02-2024 Application NO- 2004614786 Application type-New connection Reference Id- 204225082 |  |  | BILL/04264/2023-2024 | BP-2023-24-792 | 06/03/2024 | 06/03/2024 | WBSEDCL | 3.83 | 0 | 0 | 0
8 | PURBA MEDINIPUR | Contai-I | Midnapore Mechanical | BIRAMPUT AND ADJOINING MOUJAS PWSS | SM/12497 | New | Quotation Bill for New Service connection at T/W NO-II Of BIRAMPUT W/S Scheme under MMD, PHE, Dte. Block- CONTAI-I, WBSEDCL SUPPLY OFFICE: CONTAI C.C.C. Ref. Memo No- 2005011642/QUOT/03 DT. 17-12-2024 Application NO- 2005011642 Application type-New connection Consumer Id- 204475405 |  |  | BILL/03862/2024-2025 | C012539035678 | 21/01/2025 | 21/01/2025 | WBSEDCL | 3.52 | 0 | 0 | 0
Total | [13 empty] | 10451.04 | 186.53 | 1.78