## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Mahisadal | Tamluk Division | MADHYA HINGLI AND ADJOINING MOUJAS PWSS | SM/12498 | New | Ground water based Madhya Hingli Water Supply Scheme by providing Construction of Pump House, Boundary Wall, Laying of Distribution pipe line and FHTC work within Mahishadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-G) | Assistant Engineer | Junior Engineer | ORD/000821/2022-2023 | 3111/TD | 02/03/2023 | 01/04/2023 | SOUMYA ENTERPRISE | 49.53 | 38.52 | 77.77 | 80
2 | PURBA MEDINIPUR | Mahisadal | Tamluk Division | MADHYA HINGLI AND ADJOINING MOUJAS PWSS | SM/12498 | New | Ground water based Madhya Hingli Water Supply Scheme by providing Construction of Pump House, Boundary Wall, Laying of Distribution pipe line and FHTC work within Mahishadal Dev. Block under Haldia Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-C) | Assistant Engineer | Junior Engineer | ORD/000818/2022-2023 | 3108//TD | 02/03/2023 | 24/04/2026 | ALPHA ENGINEERS CO-OPERATIVE SOCIETY LTD. | 67.57 | 44.7 | 66.15 | 55
3 | PURBA MEDINIPUR | Mahisadal | Tamluk Division | MADHYA HINGLI AND ADJOINING MOUJAS PWSS | SM/12498 | New | Ground water based Madhya Hingli Water Supply Scheme by providing Construction of Pump House, Boundary Wall, Laying of Rising main, Laying of Distribution pipe line and FHTC work within Mahishadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-D) | Assistant Engineer | Junior Engineer | ORD/000819/2022-2023 | 3109/TD | 02/03/2023 | 01/04/2023 | SK SANAMAJ | 59.34 | 44.1 | 74.32 | 40
4 | PURBA MEDINIPUR | Mahisadal | Tamluk Division | MADHYA HINGLI AND ADJOINING MOUJAS PWSS | SM/12498 | New | Ground water based Madhya Hingli Water Supply Scheme by providing Construction of Pump House, Boundary Wall, Laying of Distribution pipe line and FHTC work within Mahishadal Dev. Block under Haldia Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-H) | Assistant Engineer | Junior Engineer | ORD/000822/2022-2023 | 3112/TD | 02/02/2023 | 22/02/2023 | PULAK KUMAR SAMANTA | 31.14 | 19.16 | 61.52 | 62
5 | PURBA MEDINIPUR | Mahisadal | Tamluk Division | MADHYA HINGLI AND ADJOINING MOUJAS PWSS | SM/12498 | New | Ground water based Madhya Hingli Water Supply Scheme by providing Construction of R.C.C. Over Head Reservoir of capacity 250 cum and staging height 20.00 mtr. with allied work including Sub Soil Investigation within Mahishadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. (Part-B) | Assistant Engineer | Junior Engineer | ORD/000296/2023-2024 | 585/TD | 16/05/2023 | 12/11/2023 | RAJ KUMAR SINGHA | 112.37 | 0 | 0 | 0
6 | PURBA MEDINIPUR | Mahisadal | Tamluk Division | MADHYA HINGLI AND ADJOINING MOUJAS PWSS | SM/12498 | New | Ground water based Madhya Hingli Water Supply Scheme by providing Laying of Distribution pipe line and FHTC work within Mahishadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur. (Part-F) | Assistant Engineer | Junior Engineer | ORD/000820/2022-2023 | 3110/TD | 02/03/2023 | 01/04/2023 | S. N. A. CONSTRUCTION | 58.38 | 50.43 | 86.38 | 35
7 | PURBA MEDINIPUR | Mahisadal | Midnapore Mechanical | MADHYA HINGLI AND ADJOINING MOUJAS PWSS | SM/12498 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for MADHYA HINGLI and ADJOINING MOUJAS, Block - Mahishadal, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/001625/2022-2023 | 510/W/MMD | 20/03/2023 | 31/12/2024 | SHOVAN KUMAR DAS | 22.81 | 10.54 | 46.22 | 45
8 | PURBA MEDINIPUR | Mahisadal | Tamluk Division | MADHYA HINGLI AND ADJOINING MOUJAS PWSS | SM/12498 | New | Sinking of 4 (Four) nos. Tube Well at different sites. Name of Sites: i) Sinking of 250mm. x 150mm. dia. x 280 mtr. Deep additional Tube well by direct rotary rig method at 1st Tube well Site of Bamanpur Water Supply Scheme within Mahishadal Dev. Block under Haldia Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. ii) Sinking of 250mm. x 150mm. dia. x 280 mtr. Deep additional Tube well by direct rotary rig method at 2nd Tube well Site of Bamanpur Water Supply Scheme within Mahishadal Dev. Block under Haldia Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. iii) Sinking of 250mm. x 150mm. dia. x 280 mtr. Deep additional Tube well by direct rotary rig method at 1st Tube well Site of Madhya Hingli Water Supply Scheme within Mahishadal Dev. Block under Haldia Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. iv) Sinking of 250mm. x 150mm. dia. x 280 mtr. Deep additional Tube well by direct rotary rig method at 2nd Tube well Site of Madhya Hingli Water Supply Scheme within Mahishadal Dev. Block under Haldia Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000898/2022-2023 | 3348/TD | 22/03/2023 | 19/12/2024 | M/S SYCHROTECH INDUSTRY | 62.36 | 25.35 | 40.64 | 100
9 | PURBA MEDINIPUR | Mahisadal | Tamluk Division | MADHYA HINGLI AND ADJOINING MOUJAS PWSS | SM/12498 | New | Canal Crossing Structure for Laying Distribution (Nodal Point - 17 - 18) & Rising Main Pipeline of Madhya Hingly Water Supply Scheme under Haldia Sub- Division of Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000651/2023-2024 | 2609/TD | 11/10/2023 | 10/11/2023 | SOUVIK GHOSAL | 7.39 | 4.72 | 63.94 | 100
10 | PURBA MEDINIPUR | Mahisadal | Tamluk Division | MADHYA HINGLI AND ADJOINING MOUJAS PWSS | SM/12498 | New | Ground water based Madhya Hingli Water Supply Scheme by providing Construction of Pump House, Boundary Wall, Laying of Distribution pipe line and FHTC work within Mahishadal Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-E) | Assistant Engineer | Junior Engineer | ORD/000070/2023-2024 | 140/TD | 10/04/2023 | 10/05/2023 | THREE MAA ENTERPRISE | 69.26 | 69.25 | 99.98 | 75
11 | PURBA MEDINIPUR | Mahisadal | Tamluk Division | MADHYA HINGLI AND ADJOINING MOUJAS PWSS | SM/12498 | New | Material Requisition To Resource Division |  |  | RTOR000138/2022-2023 | 2423/TD | 16/01/2023 | 16/01/2023 | Resource Division | 34.51 | 0 | 0 | 0
12 | PURBA MEDINIPUR | Mahisadal | Tamluk Division | MADHYA HINGLI AND ADJOINING MOUJAS PWSS | SM/12498 | New | Payment of WBSEDCL for Quotation of Shifting of 11 KV HTOH Line under Tamluk Division, PHE Dte. |  |  | BILL/01479/2023-2024 | BP-2023-24-666 | 15/12/2023 | 15/12/2023 | WBSEDCL | 2.75 | 0 | 0 | 0
13 | PURBA MEDINIPUR | Mahisadal | Midnapore Mechanical | MADHYA HINGLI AND ADJOINING MOUJAS PWSS | SM/12498 | New | Electric Quotation for MADHYA HINGLI Water Supply Scheme T/W-I, (Ref. ID-204136074) |  |  | BILL/03184/2023-2024 | BP-2023-24-441 | 19/12/2023 | 19/12/2023 | WBSEDCL | 5.95 | 0 | 0 | 0
14 | PURBA MEDINIPUR | Mahisadal | Tamluk Division | MADHYA HINGLI AND ADJOINING MOUJAS PWSS | SM/12498 | New | Material Requisition To Resource Division |  |  | RTOR000155/2023-2024 | 101/TD | 05/01/2024 | 05/01/2024 | Resource Division | 10.82 | 0 | 0 | 0
15 | PURBA MEDINIPUR | Mahisadal | Midnapore Mechanical | MADHYA HINGLI AND ADJOINING MOUJAS PWSS | SM/12498 | New | Quotation for new service connection at Madhya Hingli w/s scheme PH II |  |  | BILL/03665/2023-2024 | BP-2023-24-682 | 15/02/2024 | 15/02/2024 | WBSEDCL | 4.68 | 0 | 0 | 0
Total | [13 empty] | 598.85 | 306.76 | 51.22