## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Deshopran | Midnapore Mechanical | KAJI BASAN AND ADJOINING MOUJAS PWSS | SM/12499 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for KAJI BASAN and ADJOINING MOUJAS, Block - Deshopran, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division | ORD/001624/2022-2023 | 509/W/MMD | 20/03/2023 | 16/09/2023 | SANJIB SAHA | 22.79 | 0 | 0 | 0
2 | PURBA MEDINIPUR | Deshopran | Tamluk Division | KAJI BASAN AND ADJOINING MOUJAS PWSS | SM/12499 | New | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House & Providing Functional Household Tap Connection (61964 Nos) For 38 nos Pipe water supply Scheme including two years Operation & Maintainance within Patashpur-I, Patashpur-II , Egra-I and Deshapran Block Under Tamluk Division PHE Dte. Under Purba Medinipur District. | Assistant Engineer,Assistant Engineer, Headquaters | Junior Engineer | ORD/000677/2023-2024 | 2702/TD | 20/10/2023 | 30/03/2026 | MACKINTOSH BURN LIMITED | 19507.71 | 146.95 | 0.75 | 51
3 | PURBA MEDINIPUR | Deshopran | Tamluk Division | KAJI BASAN AND ADJOINING MOUJAS PWSS | SM/12499 | New | Material Requisition To Resource Division |  |  | RTOR000124/2022-2023 | 2402/TD | 16/01/2023 | 16/01/2023 | Resource Division | 11.28 | 0 | 0 | 0
4 | PURBA MEDINIPUR | Deshopran | Tamluk Division | KAJI BASAN AND ADJOINING MOUJAS PWSS | SM/12499 | New | Material Requisition To Resource Division |  |  | RTOR000096/2024-2025 | 2961/TD | 12/09/2024 | 12/09/2024 | Resource Division | 7.86 | 0 | 0 | 0
5 | PURBA MEDINIPUR | Deshopran | Midnapore Mechanical | KAJI BASAN AND ADJOINING MOUJAS PWSS | SM/12499 | New | Quotation Bill for New Service connection at T/W NO-I Of KAJIBASAN W/S Scheme under MMD, PHE, Dte. Block- CONTAI-II, WBSEDCL SUPPLY OFFICE: MUKUNDAPUR C.C.C. Ref. Memo No- 2004767101/QUOT/03 DT. 07-06-2024 Application NO- 2004767101 Application type-New connection Consumer Id- 204325527 |  |  | BILL/01221/2024-2025 | BP-2024-25-300 | 18/06/2024 | 18/06/2024 | WBSEDCL | 16.47 | 0 | 0 | 0
6 | PURBA MEDINIPUR | Deshopran | Midnapore Mechanical | KAJI BASAN AND ADJOINING MOUJAS PWSS | SM/12499 | New | Quotation Bill for New Service connection at T/W NO-II Of KAJIBASAN W/S Scheme under MMD, PHE, Dte. Block- CONTAI-II, WBSEDCL SUPPLY OFFICE: MUKUNDAPUR C.C.C. Ref. Memo No- 2005003663/QUOT/03 DT. 11-12-2024 Application NO- 2005003663 Application type-New connection Consumer Id- 204470602 |  |  | BILL/03655/2024-2025 | C012524056101 | 09/01/2025 | 09/01/2025 | WBSEDCL | 7.68 | 0 | 0 | 0
Total | [13 empty] | 19573.79 | 146.95 | 0.75