## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Deshopran | Tamluk Division | FULESHWAR AND ADJOINING MOUJAS PWSS | SM/12500 | New | Material Requisition To Resource Division |  |  | RTOR000122/2022-2023 | 2403/TD | 16/01/2023 | 16/01/2023 | Resource Division | 34.22 | 0 | 0 | 0
2 | PURBA MEDINIPUR | Deshopran | Midnapore Mechanical | FULESHWAR AND ADJOINING MOUJAS PWSS | SM/12500 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for FULESHWAR and ADJOINING MOUJAS, Block - Deshopran, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division | ORD/001622/2022-2023 | 508/W/MMD | 20/03/2023 | 16/09/2023 | M/S DILIP MITRA | 22.77 | 9.98 | 43.83 | 60
3 | PURBA MEDINIPUR | Deshopran | Tamluk Division | FULESHWAR AND ADJOINING MOUJAS PWSS | SM/12500 | New | Material Requisition To Resource Division |  |  | RTOR000095/2024-2025 | 2958/TD | 12/09/2024 | 12/09/2024 | Resource Division | 7.81 | 0 | 0 | 0
4 | PURBA MEDINIPUR | Deshopran | Tamluk Division | FULESHWAR AND ADJOINING MOUJAS PWSS | SM/12500 | New | Bill for payment to WBSEDCL for New Pipe Construction at Panchgachia new Sawsahan for Fuleshwar PWSS under Tamluk Division, PHE Dte. |  |  | BILL/02050/2023-2024 | BP-2023-24-962 | 14/03/2024 | 14/03/2024 | WBSEDCL | 0.27 | 0 | 0 | 0
5 | PURBA MEDINIPUR | Deshopran | Midnapore Mechanical | FULESHWAR AND ADJOINING MOUJAS PWSS | SM/12500 | New | Quotation bill for Fuleswar W/S scheme T/W. No.-I, P.S- Contai, Block.-Contai-II Application No.-2004626938 Ref ID.-204233452 Date.-01/03/2024 Quotation Date.-01-03-2024 Mukundapur CCC |  |  | BILL/04337/2023-2024 | BP-2023-24-808 | 11/03/2024 | 11/03/2024 | WBSEDCL | 3.24 | 0 | 0 | 0
6 | PURBA MEDINIPUR | Deshopran | Midnapore Mechanical | FULESHWAR AND ADJOINING MOUJAS PWSS | SM/12500 | New | Quotation Bill for New Service connection at T/W NO-II Of FULESWAR W/S Scheme under MMD, PHE, Dte. Block- CONTAI-II, WBSEDCL SUPPLY OFFICE: MUKUNDAPUR C.C.C. Ref. Memo No- 2004767027/QUOT/03 DT. 07-06-2024 Application NO- 2004767027 Application type-New connection Consumer Id- 204325420 |  |  | BILL/01222/2024-2025 | BP-2024-25-301 | 18/06/2024 | 18/06/2024 | WBSEDCL | 12.7 | 0 | 0 | 0
7 | PURBA MEDINIPUR | Deshopran | Tamluk Division | FULESHWAR AND ADJOINING MOUJAS PWSS | SM/12500 | New | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House & Providing Functional Household Tap Connection (61964 Nos) For 38 nos Pipe water supply Scheme including two years Operation & Maintainance within Patashpur-I, Patashpur-II , Egra-I and Deshapran Block Under Tamluk Division PHE Dte. Under Purba Medinipur District. | Assistant Engineer,Assistant Engineer, Headquaters | Junior Engineer | ORD/000677/2023-2024 | 2702/TD | 20/10/2023 | 30/03/2026 | MACKINTOSH BURN LIMITED | 19507.71 | 167.92 | 0.86 | 51
Total | [13 empty] | 19588.72 | 177.9 | 0.91