## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Bhagawanpur-I | Tamluk Division | BARTTAN AND ADJOINING MOUJAS PWSS | SM/12501 | New | Sinking of Tube Well ,Construction of Pump House ,350 cum OHR (Intze type with pile foundation), Rising main, Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC (3076 nos) under JJM with allied work including 02(two) Years Operation & Maintenance of Barttan PWSS within Bhagwanpur-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer,Assistant Engineer, Headquaters | Junior Engineer | ORD/000226/2023-2024 | 452/TD | 04/05/2023 | 26/09/2025 | TARUN KOLEY | 782.24 | 344.73 | 44.07 | 45
2 | PURBA MEDINIPUR | Bhagawanpur-I | Midnapore Mechanical | BARTTAN AND ADJOINING MOUJAS PWSS | SM/12501 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for BARTTAN and ADJOINING MOUJAS, Block ¿ Bhagawanpur I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001578/2022-2023 | 473/W/MMD | 20/03/2023 | 09/03/2025 | DEBJYOTI BASU | 25.26 | 18.96 | 75.08 | 100
3 | PURBA MEDINIPUR | Bhagawanpur-I | Tamluk Division | BARTTAN AND ADJOINING MOUJAS PWSS | SM/12501 | New | Material Requisition To Resource Division |  |  | RTOR000244/2022-2023 | 2724/TD | 06/02/2023 | 06/02/2023 | Resource Division | 35.45 | 0 | 0 | 0
4 | PURBA MEDINIPUR | Bhagawanpur-I | Midnapore Mechanical | BARTTAN AND ADJOINING MOUJAS PWSS | SM/12501 | New | Barttan W/S scheme T/W no.-II(Tower) Application-2004521219 Ref.-204156075 |  |  | BILL/03177/2023-2024 | BP-2023-24-477 | 27/12/2023 | 27/12/2023 | WBSEDCL | 3.01 | 0 | 0 | 0
5 | PURBA MEDINIPUR | Bhagawanpur-I | Midnapore Mechanical | BARTTAN AND ADJOINING MOUJAS PWSS | SM/12501 | New | Barttan W/S scheme T/W no.-I(Tower) Application-2004521240 Ref.-204156076 |  |  | BILL/03178/2023-2024 | BP-2023-24-478 | 27/12/2023 | 27/12/2023 | WBSEDCL | 2.93 | 0 | 0 | 0
6 | PURBA MEDINIPUR | Bhagawanpur-I | Tamluk Division | BARTTAN AND ADJOINING MOUJAS PWSS | SM/12501 | New | Material Requisition To Resource Division |  |  | RTOR000121/2023-2024 | 95/TD | 05/01/2024 | 05/01/2024 | Resource Division | 18.95 | 0 | 0 | 0
Total | [13 empty] | 867.82 | 363.69 | 41.91