## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Sutahata | Tamluk Division | JAYNAGAR AND ADJOINING MOUJAS PWSS | SM/12502 | New | Sinking of 2 (Two) nos. Tube Well at different sites. Name of Sites: i) Sinking of 250mm. x 150mm. dia. x 280 mtr. Deep additional Tube well by direct rotary rig method at 1st Tube well Site of Jaynagar Water Supply Scheme within Sutahata Block under Haldia Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. ii) Sinking of 250mm. x 150mm. dia. x 280 mtr. Deep additional Tube well by direct rotary rig method at 2nd Tube well Site of Jaynagar Water Supply Scheme within Sutahata Block under Haldia Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000895/2022-2023 | 3345/TD | 22/03/2023 | 16/04/2023 | M R ENTERPRISE | 30.84 | 0 | 0 | 0
2 | PURBA MEDINIPUR | Sutahata | Tamluk Division | JAYNAGAR AND ADJOINING MOUJAS PWSS | SM/12502 | New | Material Requisition To Resource Division |  |  | RTOR000163/2022-2023 | 2473/TD | 16/01/2023 | 16/01/2023 | Resource Division | 30.03 | 0 | 0 | 0
3 | PURBA MEDINIPUR | Sutahata | Tamluk Division | JAYNAGAR AND ADJOINING MOUJAS PWSS | SM/12502 | New | Ground water based Jaynagar Water Supply Scheme by providing Laying of Distribution pipe line and FHTC work (700 nos) within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-D) | Assistant Engineer | Junior Engineer | ORD/000791/2022-2023 | 3042/TD | 27/02/2023 | 22/12/2025 | RELIABLE CONSTRUCTIONS | 90.11 | 51.54 | 57.19 | 68
4 | PURBA MEDINIPUR | Sutahata | Tamluk Division | JAYNAGAR AND ADJOINING MOUJAS PWSS | SM/12502 | New | Installation of display board at 4 (four) nos work site under Haldia Sub-Division of Tamluk Division, PHE Dte. (Phase-I) [Jaynagar PWSS, Mohanpur PWSS, Erekhali PWSS & Hariballavpur PWSS] | Assistant Engineer | Junior Engineer | ORD/000829/2023-2024 | 617/HSD, | 21/12/2023 | 28/12/2023 | SNEHASIS BERA | 0.83 | 0.83 | 99.62 | 100
5 | PURBA MEDINIPUR | Sutahata | Tamluk Division | JAYNAGAR AND ADJOINING MOUJAS PWSS | SM/12502 | New | Preparation of design based on soil test report and submission of drawing of foundation for construction of 350 cum RCC OHR at Jaynagar PWSS at Mahisadal Block under Tamluk Division,PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001046/2023-2024 | 376/TD | 29/01/2024 | 08/02/2024 | ASTER CONSULTANCY | 0.95 | 0.95 | 100 | 100
6 | PURBA MEDINIPUR | Sutahata | Tamluk Division | JAYNAGAR AND ADJOINING MOUJAS PWSS | SM/12502 | New | Material Requisition To Resource Division |  |  | RTOR000190/2023-2024 | 639/W | 20/02/2024 | 20/02/2024 | Resource Division | 13.39 | 0 | 0 | 0
7 | PURBA MEDINIPUR | Sutahata | Midnapore Mechanical | JAYNAGAR AND ADJOINING MOUJAS PWSS | SM/12502 | New | Quotation bill for new service connection at TW-I of Joynagar w/s scheme Block-sutahata in the Dist. of Purba Medinipur under MMD ,PHE Dte. Name of C.C.C.-Chaitanyapur Application no.-2004839280 Application type-new connection Reference ID-204366525 Quotation Date-26/07/2024 Quotation due Date-28/07/2025 Contract Demand-8344W |  |  | BILL/01858/2024-2025 | C082408702219 | 07/08/2024 | 07/08/2024 | WBSEDCL | 7.89 | 0 | 0 | 0
8 | PURBA MEDINIPUR | Sutahata | Midnapore Mechanical | JAYNAGAR AND ADJOINING MOUJAS PWSS | SM/12502 | New | Quotation bill for new service connection at TW-II of Joynagar w/s scheme,Block-Sutahata under MMD PHE Dte. Name of C.C.C.-Chaitanyapur Application No.-2004818887 Application type-new connection Reference ID-204355766 Quotation Date-12/7/2024 Quotation Due Date-14/7/2025 Contract Demand-8344 W |  |  | BILL/01695/2024-2025 | BP-2024-25-495 | 29/07/2024 | 29/07/2024 | WBSEDCL | 4.61 | 0 | 0 | 0
9 | PURBA MEDINIPUR | Sutahata | Tamluk Division | JAYNAGAR AND ADJOINING MOUJAS PWSS | SM/12502 | New | Ground water based Jaynagar Water Supply Scheme by providing Laying of Distribution pipe line and FHTC work (774 nos) within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-E) | Assistant Engineer | Junior Engineer | ORD/000792/2022-2023 | 3043/TD | 27/02/2023 | 05/10/2025 | ZENITH CONSTRUCTION | 89.68 | 45.99 | 51.29 | 55
10 | PURBA MEDINIPUR | Sutahata | Tamluk Division | JAYNAGAR AND ADJOINING MOUJAS PWSS | SM/12502 | New | Ground water based Jaynagar Water Supply Scheme by providing Laying of Distribution pipe line and FHTC work and Construction of R.C.C. Over Head Reservoir of capacity 350 cum and staging height 20.00 mtr. with allied work including Sub Soil Investigation within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-B) | Assistant Engineer | Junior Engineer | ORD/000324/2023-2024 | 686/TD | 23/05/2023 | 26/06/2026 | RELIABLE CONSTRUCTIONS | 172.01 | 21.99 | 12.78 | 20
11 | PURBA MEDINIPUR | Sutahata | Tamluk Division | JAYNAGAR AND ADJOINING MOUJAS PWSS | SM/12502 | New | Land Development work at Head work site of Jaynagar Water supply Scheme within Sutahata Develompent Block under Haldia Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000006/2025-2026 | 1082/TD | 07/04/2025 | 16/02/2026 | PRAGATI ENGINEER'S CO-OP SOCIETY LTD. | 3.29 | 0 | 0 | 0
12 | PURBA MEDINIPUR | Sutahata | Tamluk Division | JAYNAGAR AND ADJOINING MOUJAS PWSS | SM/12502 | New | Construction of Box Culvert (5.00Mtr. X 3.50Mtr.) at 2nd Tube Well site of Jaynagar W/S Scheme within Sutahata Dev. Block under Haldia Sub- Division of Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000721/2023-2024 | 2943/TD | 23/11/2023 | 15/07/2025 | M/S SOURAV MAHAPATRA | 5.33 | 3.77 | 70.75 | 50
13 | PURBA MEDINIPUR | Sutahata | Tamluk Division | JAYNAGAR AND ADJOINING MOUJAS PWSS | SM/12502 | New | Sinking of 250mm. x 150mm. dia. x 280 mtr. Deep Tube well by direct rotary rig method at 1st & 2nd Tube well of Jaynagar Water Supply Scheme within Sutahata Development Block under Haldia Sub-Division, of Tamluk Division P.H.E.Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000142/2024-2025 | 2015/TD | 14/06/2024 | 01/02/2025 | PRANTIK DRILLING AGENCY | 30.07 | 7.48 | 24.89 | 100
14 | PURBA MEDINIPUR | Sutahata | Midnapore Mechanical | JAYNAGAR AND ADJOINING MOUJAS PWSS | SM/12502 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for JAYNAGAR and ADJOINING MOUJAS, Block ¿ Sutahata, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Tanmoy Shee, JE/Haldia Electrical Sub-Division. | ORD/001586/2022-2023 | 469/W/MMD | 20/03/2023 | 15/06/2026 | BHABANI PRASAD MANNA | 23.7 | 0 | 0 | 35
15 | PURBA MEDINIPUR | Sutahata | Tamluk Division | JAYNAGAR AND ADJOINING MOUJAS PWSS | SM/12502 | New | Ground water based Jaynagar Water Supply Scheme by providing Construction of Pump House, Boundary Wall, Laying of Rising main, Laying of Distribution pipe line and FHTC work (400nos) within Sutahata Dev. Block under Haldia Sub Division of Tamluk Division, PHE Dte. Purba Medinipur.(Part-C) | Assistant Engineer | Junior Engineer | ORD/000245/2023-2024 | 524/TD | 11/05/2023 | 20/03/2026 | ZENITH CONSTRUCTION | 141.93 | 45.73 | 32.22 | 30
Total | [13 empty] | 644.67 | 178.28 | 27.65