## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Egra-I | Tamluk Division | SHIPUR AND ADJOINING MOUJAS PWSS | SM/12503 | New | Material Requisition To Resource Division |  |  | RTOR000132/2022-2023 | 2416/TD | 16/01/2023 | 16/01/2023 | Resource Division | 19.96 | 0 | 0 | 0
2 | PURBA MEDINIPUR | Egra-I | Midnapore Mechanical | SHIPUR AND ADJOINING MOUJAS PWSS | SM/12503 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for SHIPUR and ADJOINING MOUJAS, Block ¿ Egra I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division | ORD/001413/2022-2023 | 2424/W/MMD | 31/12/2022 | 29/06/2023 | P.K.ENGINEERING | 22.8 | 0 | 0 | 51
3 | PURBA MEDINIPUR | Egra-I | Tamluk Division | SHIPUR AND ADJOINING MOUJAS PWSS | SM/12503 | New | Preparation of design based on soil test report and submission of drawing of foundation for construction of 250 cum RCC OHR at Shipur PWSS at Egra-I Block under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000173/2024-2025 | 2085/TD | 24/06/2024 | 04/07/2024 | ASTER CONSULTANCY | 0.95 | 0 | 0 | 100
Total | [13 empty] | 43.71 | 0 | 0