## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Bhagawanpur-I | Midnapore Mechanical | KHAGA AND IT'S ADJOINING MOUJAS PWSS | SM/12504 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for KHAGA and ADJOINING MOUJAS, Block ¿ Bhagawanpur I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001584/2022-2023 | 467/W/MMD | 20/03/2023 | 16/09/2023 | BHABANI PRASAD MANNA | 23.7 | 0 | 0 | 85
2 | PURBA MEDINIPUR | Bhagawanpur-I | Tamluk Division | KHAGA AND IT'S ADJOINING MOUJAS PWSS | SM/12504 | New | Sinking of Tube Well ,Construction of Pump House ,300 cum OHR (Intze type with pile foundation), Rising main, Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC (1806 nos) under JJM with allied work including 02(two) Years Operation & Maintenance of KHAGA PWSS within Bhagwanpur-I Block under Contai Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer, Headquaters | Junior Engineer | ORD/000326/2023-2024 | 698/TD | 23/05/2023 | 16/08/2026 | BANDHAB ENGINEERS CO-OPERATIVE SOCIETY LTD. | 581.3 | 242.94 | 41.79 | 40
3 | PURBA MEDINIPUR | Bhagawanpur-I | Tamluk Division | KHAGA AND IT'S ADJOINING MOUJAS PWSS | SM/12504 | New | Material Requisition To Resource Division |  |  | RTOR000245/2022-2023 | 2722/TD | 06/02/2023 | 06/02/2023 | Resource Division | 37.4 | 0 | 0 | 0
4 | PURBA MEDINIPUR | Bhagawanpur-I | Tamluk Division | KHAGA AND IT'S ADJOINING MOUJAS PWSS | SM/12504 | New | Laying Distribution System (Nodal-J-1 To J-2) of pipe line and its allied works for KHAGA water supply scheme in Bhgwanpur-I Block within Contai Sub-Division under Tamluk Division, PHE Dte, Purba Medinipur. (As per Revised LDS Drawing) | Assistant Engineer, Headquaters | Junior Engineer | ORD/001245/2023-2024 | 1080/TD | 16/03/2024 | 16/07/2025 | S.S. ENTERPRISE | 23.86 | 17.47 | 73.2 | 80
5 | PURBA MEDINIPUR | Bhagawanpur-I | Tamluk Division | KHAGA AND IT'S ADJOINING MOUJAS PWSS | SM/12504 | New | Material Requisition To Resource Division |  |  | RTOR000153/2023-2024 | 89/TD | 05/01/2024 | 05/01/2024 | Resource Division | 11.12 | 0 | 0 | 0
6 | PURBA MEDINIPUR | Bhagawanpur-I | Midnapore Mechanical | KHAGA AND IT'S ADJOINING MOUJAS PWSS | SM/12504 | New | Quotation Bill for New Service connection at T/W NO-I Of KHAGA W/S Scheme under MMD, PHE, Dte. Block- BHAGWANPUR-I, WBSEDCL SUPPLY OFFICE: BHAGWANPUR C.C.C. Ref. Memo No-2004686929/QUOT/03 DT. 19-04-2024 Application NO- 2004686929 Application type-New connection Consumer Id- 204277584 |  |  | BILL/00707/2024-2025 | BP-2024-25-140 | 09/05/2024 | 09/05/2024 | WBSEDCL | 2.87 | 0 | 0 | 0
7 | PURBA MEDINIPUR | Bhagawanpur-I | Midnapore Mechanical | KHAGA AND IT'S ADJOINING MOUJAS PWSS | SM/12504 | New | Quotation Bill for New Service connection at T/W NO-II Of KHAGA W/S Scheme under MMD, PHE, Dte. Block- BHAGWANPUR-I, WBSEDCL SUPPLY OFFICE: BHAGWANPUR C.C.C. Ref. Memo No- 2004739171/QUOT/03 DT. 16-05-2024 Application NO- 2004739171 Application type-New connection Consumer Id- 204309281 |  |  | BILL/01135/2024-2025 | BP-2024-25-244 | 06/06/2024 | 06/06/2024 | WBSEDCL | 3.96 | 0 | 0 | 0
Total | [13 empty] | 684.22 | 260.41 | 38.06