## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Deshopran | Tamluk Division | CHALTI AND ADJOINING MOUJAS PWSS | SM/12505 | New | Material Requisition To Resource Division |  |  | RTOR000123/2022-2023 | 2404/TD | 16/01/2023 | 16/01/2023 | Resource Division | 49.91 | 0 | 0 | 0
2 | PURBA MEDINIPUR | Deshopran | Tamluk Division | CHALTI AND ADJOINING MOUJAS PWSS | SM/12505 | New | Preparation of design based on soil test report and submission of drawing of foundation for construction of 150 cum RCC OHR at Chalti PWSS at Deshpran Block under Tamluk Division, PHE Dte. | Assistant Engineer |  | ORD/001279/2023-2024 | 1052/TD | 15/03/2024 | 25/03/2024 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.95 | 0 | 0 | 0
3 | PURBA MEDINIPUR | Deshopran | Tamluk Division | CHALTI AND ADJOINING MOUJAS PWSS | SM/12505 | New | Material Requisition To Resource Division |  |  | RTOR000080/2024-2025 | 2952/TD | 12/09/2024 | 12/09/2024 | Resource Division | 6.76 | 0 | 0 | 0
4 | PURBA MEDINIPUR | Deshopran | Midnapore Mechanical | CHALTI AND ADJOINING MOUJAS PWSS | SM/12505 | New | Quotation Bill for New Service connection at T/W NO-II Of CHALTI W/S Scheme under MMD, PHE, Dte. Block- CONTAI-II, WBSEDCL SUPPLY OFFICE: MUKUNDAPUR C.C.C. Ref. Memo No- 2004945784/QUOT/03 DT. 05-11-2024 Application NO- 2004767136 Application type-New connection Consumer Id- 204429932 |  |  | BILL/03007/2024-2025 | C112423558564 | 19/11/2024 | 19/11/2024 | WBSEDCL | 3.85 | 0 | 0 | 0
5 | PURBA MEDINIPUR | Deshopran | Tamluk Division | CHALTI AND ADJOINING MOUJAS PWSS | SM/12505 | New | Quotation Bill for New Service connection at T/W NO-I Of CHALTI W/S Scheme under MMD, PHE, Dte. Block- CONTAI-II, WBSEDCL SUPPLY OFFICE: MUKUNDAPUR C.C.C. Ref. Memo No- 2004767136/QUOT/03 DT. 07-06-2024 Application NO- 2004767136 Application type-New connection Consumer Id- 204325528 |  |  | BILL/00594/2024-2025 | BP-2024-25-291 | 29/07/2024 | 29/07/2024 | WBSEDCL | 21.24 | 0 | 0 | 0
6 | PURBA MEDINIPUR | Deshopran | Midnapore Mechanical | CHALTI AND ADJOINING MOUJAS PWSS | SM/12505 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for CHALTI and ADJOINING MOUJAS, Block ¿ Deshopran, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division | ORD/001411/2022-2023 | 2422/W/MMD | 31/12/2022 | 31/05/2025 | P.K.ENGINEERING | 22.8 | 0 | 0 | 90
7 | PURBA MEDINIPUR | Deshopran | Tamluk Division | CHALTI AND ADJOINING MOUJAS PWSS | SM/12505 | New | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House & Providing Functional Household Tap Connection (61964 Nos) For 38 nos Pipe water supply Scheme including two years Operation & Maintainance within Patashpur-I, Patashpur-II , Egra-I and Deshapran Block Under Tamluk Division PHE Dte. Under Purba Medinipur District. | Assistant Engineer,Assistant Engineer, Headquaters | Junior Engineer | ORD/000677/2023-2024 | 2702/TD | 20/10/2023 | 30/03/2026 | MACKINTOSH BURN LIMITED | 19507.71 | 0 | 0 | 51
Total | [13 empty] | 19613.23 | 0 | 0