## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Bhagawanpur-II | Tamluk Division | PANUSI AND ADJOINING MOUJAS PWSS | SM/12506 | New | Material Requisition To Resource Division |  |  | RTOR000312/2022-2023 | 2968TD | 27/02/2023 | 27/02/2023 | Resource Division | 21.55 | 0 | 0 | 0
2 | PURBA MEDINIPUR | Bhagawanpur-II | Tamluk Division | PANUSI AND ADJOINING MOUJAS PWSS | SM/12506 | New | Laying distribution pipe line, & Accommodate FHTC (325 nos) under JJM with allied work for Panusi & its adjoining moujas PWSS in Bhagwanpur-II Block within Contai Sub-Division under Tamluk Division, PHE Dte. (Part-D) | Assistant Engineer | Junior Engineer | ORD/000186/2023-2024 | 376/TD | 27/04/2023 | 26/06/2023 | A. K. SIKDAR | 73.19 | 35.95 | 49.12 | 52
3 | PURBA MEDINIPUR | Bhagawanpur-II | Tamluk Division | PANUSI AND ADJOINING MOUJAS PWSS | SM/12506 | New | Laying distribution pipe line, & Accommodate FHTC (322 nos) under JJM with allied work for Panusi & its adjoining moujas PWSS in Bhagwanpur-II Block within Contai Sub-Division under Tamluk Division, PHE Dte. (Part-E) | Assistant Engineer | Junior Engineer | ORD/000187/2023-2024 | 377/TD | 27/04/2023 | 23/02/2025 | SWARUPANANDA DAS | 73.44 | 36.55 | 49.77 | 50
4 | PURBA MEDINIPUR | Bhagawanpur-II | Tamluk Division | PANUSI AND ADJOINING MOUJAS PWSS | SM/12506 | New | Laying distribution pipe line, Boundary Wall & Accommodate FHTC (160 nos) under JJM with allied work for Panusi & its adjoining moujas PWSS in Bhagwanpur-II Block within Contai Sub-Division under Tamluk Division, PHE Dte. (Part-B) | Assistant Engineer | Junior Engineer | ORD/000252/2023-2024 | 516/TD | 11/05/2023 | 10/07/2023 | NEW STAR CONSTRUCTION | 84.23 | 60.35 | 71.65 | 73
5 | PURBA MEDINIPUR | Bhagawanpur-II | Tamluk Division | PANUSI AND ADJOINING MOUJAS PWSS | SM/12506 | New | Tube well, Pump House ,250 cum OHR (Intze type with pile foundation), Rising main, Head work site, Laying distribution pipe line, RCC Culvert, CC Pavement, Boundary Wall, Soil investigation & Accommodate FHTC (195 nos) under JJM with allied work for Panusi & its adjoining moujas PWSS in Bhagwanpur-II Block within Contai Sub-Division under Tamluk Division, PHE Dte. (Part-A) | Assistant Engineer | Junior Engineer | ORD/000377/2023-2024 | 1016/TD | 06/06/2023 | 21/05/2026 | DAS ENTERPRISE | 189.43 | 0 | 0 | 10
6 | PURBA MEDINIPUR | Bhagawanpur-II | Tamluk Division | PANUSI AND ADJOINING MOUJAS PWSS | SM/12506 | New | Preparation of design based on soil test report and submission of drawing of foundation for construction of 250 cum RCC OHR at Panushi PWSS at Bhagwanpur-II Block under Tamluk Division,PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001051/2023-2024 | 381/TD | 29/01/2024 | 08/02/2024 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.95 | 0.95 | 100 | 100
7 | PURBA MEDINIPUR | Bhagawanpur-II | Tamluk Division | PANUSI AND ADJOINING MOUJAS PWSS | SM/12506 | New | Instalation of display Board at different work site of Pachahari, Basudevberya,Panusi & Adjoining Moujas New PWSS in Bhagawanpur - II Block within Contai Sub- Division of Tamluk Division, PHE Dte. Purba Medinipur District. | Assistant Engineer |  | ORD/001174/2023-2024 | 2329/CSD | 29/12/2023 | 08/01/2024 | KAMAL KUMAR BERA | 0.62 | 0.62 | 100 | 100
8 | PURBA MEDINIPUR | Bhagawanpur-II | Tamluk Division | PANUSI AND ADJOINING MOUJAS PWSS | SM/12506 | New | Material Requisition To Resource Division |  |  | RTOR000186/2023-2024 | 635/W | 20/02/2024 | 20/02/2024 | Resource Division | 12.55 | 0 | 0 | 0
9 | PURBA MEDINIPUR | Bhagawanpur-II | Midnapore Mechanical | PANUSI AND ADJOINING MOUJAS PWSS | SM/12506 | New | Quotation Bill for New Service connection at T/W NO-II Of PANUSI W/S Scheme under MMD, PHE, Dte. Block- BHAGWANPUR-II, WBSEDCL SUPPLY OFFICE: MADHAKHALI C.C.C. Ref. Memo No-2004615668/QUOT/03 DT. 23-02-2024 Application NO- 2004615668 Application type-New connection Consumer Id- 204225684 |  |  | BILL/02553/2024-2025 | C102412615985 | 04/10/2024 | 04/10/2024 | WBSEDCL | 11.08 | 0 | 0 | 0
10 | PURBA MEDINIPUR | Bhagawanpur-II | Midnapore Mechanical | PANUSI AND ADJOINING MOUJAS PWSS | SM/12506 | New | Quotation Bill for New Service connection at T/W NO-I Of PANSUI W/S Scheme under MMD, PHE, Dte. Block- Bhagwanpur-II, MADHAKHALI C.C.C. Ref. Memo No- 2004601802/QUOT/03 DT. 15-02-2024 Application NO- 2004601802 Application type-New connection Reference Id- 204217830 |  |  | BILL/04342/2023-2024 | BP-2023-24-811 | 11/03/2024 | 11/03/2024 | WBSEDCL | 6.85 | 0 | 0 | 0
11 | PURBA MEDINIPUR | Bhagawanpur-II | Tamluk Division | PANUSI AND ADJOINING MOUJAS PWSS | SM/12506 | New | Laying distribution pipe line, & Accommodate FHTC (200 nos) under JJM with allied work for Panusi & its adjoining moujas PWSS in Bhagwanpur-II Block within Contai Sub-Division under Tamluk Division, PHE Dte.(Part-G) | Assistant Engineer | Junior Engineer | ORD/000189/2023-2024 | 379/TD | 27/04/2023 | 27/05/2023 | AMMON ENGINEERS CO-OPERATIVE SOCIETY LTD. | 38.51 | 22.02 | 57.16 | 60
12 | PURBA MEDINIPUR | Bhagawanpur-II | Tamluk Division | PANUSI AND ADJOINING MOUJAS PWSS | SM/12506 | New | Laying distribution pipe line, & Accommodate FHTC (150 nos) under JJM with allied work for Panusi & its adjoining moujas PWSS in Bhagwanpur-II Block within Contai Sub-Division under Tamluk Division, PHE Dte. (Part-H) | Assistant Engineer | Junior Engineer | ORD/000190/2023-2024 | 380/TD | 27/04/2023 | 22/05/2023 | AMMON ENGINEERS CO-OPERATIVE SOCIETY LTD. | 26.52 | 14.8 | 55.8 | 58
13 | PURBA MEDINIPUR | Bhagawanpur-II | Tamluk Division | PANUSI AND ADJOINING MOUJAS PWSS | SM/12506 | New | Laying distribution pipe line, & Accommodate FHTC (170 nos) under JJM with allied work for Panusi & its adjoining moujas PWSS in Bhagwanpur-II Block within Contai Sub-Division under Tamluk Division, PHE Dte.(Part-I) | Assistant Engineer | Junior Engineer | ORD/000191/2023-2024 | 381/TD | 27/04/2023 | 22/05/2023 | M/S. NEW DINDA ENTERPRISE | 19.14 | 7.88 | 41.18 | 45
14 | PURBA MEDINIPUR | Bhagawanpur-II | Tamluk Division | PANUSI AND ADJOINING MOUJAS PWSS | SM/12506 | New | Laying distribution pipe line, & Accommodate FHTC (140 nos) under JJM with allied work for Panusi & its adjoining moujas PWSS in Bhagwanpur-II Block within Contai Sub-Division under Tamluk Division, PHE Dte. (Part-F) | Assistant Engineer | Junior Engineer | ORD/000188/2023-2024 | 378/TD | 27/04/2023 | 27/05/2023 | M/S. NEW DINDA ENTERPRISE | 38.62 | 22.81 | 59.07 | 65
15 | PURBA MEDINIPUR | Bhagawanpur-II | Tamluk Division | PANUSI AND ADJOINING MOUJAS PWSS | SM/12506 | New | Laying distribution pipe line, Pump House & Accommodate FHTC (375 nos) under JJM with allied work for Panusi & its adjoining moujas PWSS in Bhagwanpur-II Block within Contai Sub-Division under Tamluk Division, PHE Dte. (Part-C) | Assistant Engineer | Junior Engineer | ORD/000253/2023-2024 | 517/TD | 11/05/2023 | 01/08/2026 | S.S.T ENGINEERING | 77.56 | 47.05 | 60.66 | 65
16 | PURBA MEDINIPUR | Bhagawanpur-II | Central Drilling | PANUSI AND ADJOINING MOUJAS PWSS | SM/12506 | New | Hiring of Diesel driven motor cab (BS-IV & Above) having contract carriage permit along with driver for the office of the Superintending Engineer, M/E, PMU WBDWSIP P.H.E. Dte. under CMSD-I(D), CDD, P.H.E. Dte. | Driller In Charge | Junior Engineer | ORD/000007/2024-2025 | 254/CMSD-I | 26/06/2024 | 25/12/2024 | SIDDHARTHA CHATTERJEE | 0.89 | 0.97 | 108.55 | 0
17 | PURBA MEDINIPUR | Bhagawanpur-II | Midnapore Mechanical | PANUSI AND ADJOINING MOUJAS PWSS | SM/12506 | New | Supply and fitting fixing of porcelain fuse unit and aluminum armored cable for receiving service connection at different PWSS under Egra-II, Bhagwanpur-I and II Block under Medinapore Mechanical Division, P.H.E. Dte. in the dist. of Purba Medinipur. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000130/2024-2025 | 702/HESD | 19/07/2024 | 03/03/2025 | SOUMEN ELECTRIC | 2.2 | 0 | 0 | 70
18 | PURBA MEDINIPUR | Bhagawanpur-II | Central Drilling | PANUSI AND ADJOINING MOUJAS PWSS | SM/12506 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 75.69 | 0.35 | 11
Total | [13 empty] | 22017.11 | 325.65 | 1.48