## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Potashpur-I | Tamluk Division | PALPARA AND ADJOINING MOUJAS PWSS | SM/12508 | New | Material Requisition To Resource Division |  |  | RTOR000202/2022-2023 | 2446/TD | 16/01/2023 | 16/01/2023 | Resource Division | 19.77 | 0 | 0 | 0
2 | PURBA MEDINIPUR | Potashpur-I | Midnapore Mechanical | PALPARA AND ADJOINING MOUJAS PWSS | SM/12508 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for PALPARA and ADJOINING MOUJAS, Block ¿ Potashpur I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001589/2022-2023 | 472/W/MMD | 20/03/2023 | 16/09/2023 | SOUMEN ELECTRIC | 25.24 | 17.6 | 69.73 | 53
3 | PURBA MEDINIPUR | Potashpur-I | Midnapore Mechanical | PALPARA AND ADJOINING MOUJAS PWSS | SM/12508 | New | Quotation Bill for New Service connection at T/W NO-II Of PALPARA W/S Scheme under MMD, PHE, Dte. Block- POTASHPUR-I, WBSEDCL SUPPLY OFFICE: AMARSHI C.C.C. Ref. Memo No-2004835399/QUOT/03 DT. 26-07-2024 Application NO- 2004835399 MEMO NO: AMR/PHE/281 DT.26/7/2024 Application type-New connection Consumer Id- 204365758 |  |  | BILL/01860/2024-2025 | BP-2024-25-541 | 07/08/2024 | 07/08/2024 | WBSEDCL | 4.98 | 0 | 0 | 0
4 | PURBA MEDINIPUR | Potashpur-I | Midnapore Mechanical | PALPARA AND ADJOINING MOUJAS PWSS | SM/12508 | New | Quotation Bill for New Service connection at T/W NO-I Of PALPARA W/S Scheme under MMD, PHE, Dte. Block- PATASHPUR-I, WBSEDCL SUPPLY OFFICE: AMARSHI C.C.C. Ref. Memo No- 2004895165/QUOT/03 DT. 10-09-2024 MEMO NO: AMR/PHE/377 DT. 10-09-2024 Application NO- 2004895165 Application type-New connection Consumer Id- 204395918 |  |  | BILL/02451/2024-2025 | BP-2024-25-718 | 30/09/2024 | 30/09/2024 | WBSEDCL | 3.34 | 0 | 0 | 0
5 | PURBA MEDINIPUR | Potashpur-I | Tamluk Division | PALPARA AND ADJOINING MOUJAS PWSS | SM/12508 | New | Shifting of HTOH line at Palpara PWSS, OHR Site under Patashpur-I Dev. Block. Memo No: AMR/SHIFTING/HTOH/.....Date: 05.04.2024 Reference ID: 860297135 Application ID: 100000104915 Application Date: 05.04.2024 |  |  | BILL/00129/2024-2025 | BP-2024-25-66 | 26/04/2024 | 26/04/2024 | WBSEDCL | 5.23 | 0 | 0 | 0
6 | PURBA MEDINIPUR | Potashpur-I | Tamluk Division | PALPARA AND ADJOINING MOUJAS PWSS | SM/12508 | New | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House, Pipe carrying structure & Providing Functional Household Tap Connection (4443 Nos) For 2 nos Pipe water supply Scheme including two years Operation & Maintainance work for Goyalda PWSS, Palpara PWSS within Patashpur-I Block Under Contai Sub Division of Tamluk Division, PHE. Dept, Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000371/2023-2024 | 879/TD | 01/06/2023 | 17/01/2026 | SANKHA ENTERPRISE | 1144 | 121.46 | 10.62 | 30
7 | PURBA MEDINIPUR | Potashpur-I | Tamluk Division | PALPARA AND ADJOINING MOUJAS PWSS | SM/12508 | New | Material Requisition To Resource Division |  |  | RTOR000036/2024-2025 | 1630/TD | 18/06/2025 | 18/06/2025 | Resource Division | 17.62 | 0 | 0 | 0
Total | [13 empty] | 1220.19 | 139.06 | 11.4