## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Egra-II | Midnapore Mechanical | RAJENDRA CHAK AND ADJOINING MOUJAS PWSS | SM/12509 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for RAJENDRA CHAK and ADJOINING MOUJAS, Block ¿ Egra II, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001407/2022-2023 | 2418/W/MMD | 31/12/2022 | 29/06/2023 | BOSE & CHATTERJEE INDUSTRIES | 22.73 | 0 | 0 | 0
2 | PURBA MEDINIPUR | Egra-II | Tamluk Division | RAJENDRA CHAK AND ADJOINING MOUJAS PWSS | SM/12509 | New | Material Requisition To Resource Division |  |  | RTOR000322/2022-2023 | 2975/TD | 27/02/2023 | 27/02/2023 | Resource Division | 18.5 | 0 | 0 | 0
3 | PURBA MEDINIPUR | Egra-II | Tamluk Division | RAJENDRA CHAK AND ADJOINING MOUJAS PWSS | SM/12509 | New | Laying distribution pipe line, & Accommodate FHTC (163 nos) under JJM with allied work for Rajendrachak PWSS within Egra-II Block including supply of all labour & materials under Digha Sub-Division of Tamluk Division, PHE Dte. (PART- C) | Assistant Engineer | Junior Engineer | ORD/000128/2023-2024 | 259/TD | 19/04/2023 | 19/05/2023 | BADAL CHANDRA GOLE | 41.58 | 31.33 | 75.36 | 77
4 | PURBA MEDINIPUR | Egra-II | Tamluk Division | RAJENDRA CHAK AND ADJOINING MOUJAS PWSS | SM/12509 | New | Laying distribution pipe line, Pump House , Boundary Wall & Accommodate FHTC ( 500 nos) under JJM with allied work for Rajendrachak PWSS within Egra-II Block including supply of all labour & materials under Digha Sub-Division of Tamluk Division, PHE Dte.. (PART- B) | Assistant Engineer | Junior Engineer | ORD/000281/2023-2024 | 553/TD | 12/05/2023 | 17/10/2025 | SK. NUR ISLAM | 114.81 | 81.88 | 71.32 | 80
5 | PURBA MEDINIPUR | Egra-II | Tamluk Division | RAJENDRA CHAK AND ADJOINING MOUJAS PWSS | SM/12509 | New | Soil investigation, 250 cum OHR (Intze type with pile foundation) under JJM with allied work for Rajendrachak PWSS within Egra-II Block including supply of all labour & materials under Digha Sub-Division of Tamluk Division, PHE Dte. (PART- D) | Assistant Engineer | Junior Engineer | ORD/000631/2023-2024 | 2439/TD | 19/09/2023 | 17/03/2024 | ANUSKA ENTERPRISE | 104.2 | 0 | 0 | 0
6 | PURBA MEDINIPUR | Egra-II | Tamluk Division | RAJENDRA CHAK AND ADJOINING MOUJAS PWSS | SM/12509 | New | Preparation of design based on soil test report and submission of drawing of foundation for construction of 250 cum RCC OHR at Rajendrachak PWSS at Egra-II Block under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000159/2024-2025 | 2071/TD | 24/06/2024 | 04/07/2024 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.95 | 0.95 | 100 | 100
7 | PURBA MEDINIPUR | Egra-II | Midnapore Mechanical | RAJENDRA CHAK AND ADJOINING MOUJAS PWSS | SM/12509 | New | Quotation Bill for New Service connection at T/W NO-II Of RAJENDRACHAK W/S Scheme under MMD, PHE, Dte. Block- EGRA-II, WBSEDCL SUPPLY OFFICE: BALIGHAI C.C.C. Ref. Memo No- 2004732464/QUOT/03/212 DT. 13-05-2024 Application NO- 2004732464 Application type-New connection Consumer Id- 204305461 |  |  | BILL/01132/2024-2025 | BP-2024-25-248 | 06/06/2024 | 06/06/2024 | WBSEDCL | 3.9 | 0 | 0 | 0
8 | PURBA MEDINIPUR | Egra-II | Midnapore Mechanical | RAJENDRA CHAK AND ADJOINING MOUJAS PWSS | SM/12509 | New | Quotation Bill for New Service connection at T/W NO-I Of RAJENDRACHAK W/S Scheme under MMD, PHE, Dte. Block- EGRA-II, WBSEDCL SUPPLY OFFICE: BALIGHAI C.C.C. Ref. Memo No- 2004940316/QUOT/03/770 DT. 25-10-2024 Application NO- 2004940316 Application type-New connection Consumer Id- 204428743 |  |  | BILL/03021/2024-2025 | C112429700471 | 25/11/2024 | 25/11/2024 | WBSEDCL | 6.29 | 0 | 0 | 0
9 | PURBA MEDINIPUR | Egra-II | Central Drilling | RAJENDRA CHAK AND ADJOINING MOUJAS PWSS | SM/12509 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 46.31 | 0.22 | 11
10 | PURBA MEDINIPUR | Egra-II | Tamluk Division | RAJENDRA CHAK AND ADJOINING MOUJAS PWSS | SM/12509 | New | Laying distribution pipe line, Pump House , Boundary Wall & Accommodate FHTC ( 997 nos) under JJM with allied work for Rajendrachak PWSS within Egra-II Block including supply of all labour & materials under Digha Sub-Division of Tamluk Division, PHE Dte. (PART- A) | Assistant Engineer | Junior Engineer | ORD/000345/2023-2024 | 849/TD | 31/05/2023 | 23/07/2025 | JAGANNATH MAKAR | 256.07 | 178.54 | 69.72 | 85
Total | [13 empty] | 21908.79 | 339.01 | 1.55