## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Egra-I | Tamluk Division | MAHABISHRA AND IT'S ADJOINING MOUJAS PWSS | SM/12510 | New | Material Requisition To Resource Division |  |  | RTOR000133/2022-2023 | 2417/TD | 16/01/2023 | 16/01/2023 | Resource Division | 24.12 | 0 | 0 | 0
2 | PURBA MEDINIPUR | Egra-I | Tamluk Division | MAHABISHRA AND IT'S ADJOINING MOUJAS PWSS | SM/12510 | New | Preparation of design based on soil test report and submission of drawing of foundation for construction of 300 cum RCC OHR at Mahabisra PWSS at Egra-I Block under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000169/2024-2025 | 2081/TD | 24/06/2024 | 04/07/2024 | ASTER CONSULTANCY | 0.95 | 0.95 | 100 | 100
3 | PURBA MEDINIPUR | Egra-I | Tamluk Division | MAHABISHRA AND IT'S ADJOINING MOUJAS PWSS | SM/12510 | New | Quotation for new service connection at TW-II of Mahabishra ws scheme under MMD,PHE Dte, Block-Egra-I, EGRA CCC Application no-2004823398 Consumer ID-204358386 |  |  | BILL/00729/2024-2025 | BP-2024-25-380 | 29/08/2024 | 29/08/2024 | WBSEDCL | 17.31 | 0 | 0 | 0
4 | PURBA MEDINIPUR | Egra-I | Midnapore Mechanical | MAHABISHRA AND IT'S ADJOINING MOUJAS PWSS | SM/12510 | New | Quotation Bill for New Service connection at T/W NO-I Of MAHABISHRA W/S Scheme under MMD, PHE, Dte. Block- EGRA-I, WBSEDCL SUPPLY OFFICE: EGRA C.C.C. Ref. Memo No- 2004667051/QUOT/03 DT. 15-04-2024 Application NO- 2004667051 Application type-New connection Consumer Id- 204275715 |  |  | BILL/00577/2024-2025 | BP-2024-25-101 | 26/04/2024 | 26/04/2024 | WBSEDCL | 6.36 | 0 | 0 | 0
5 | PURBA MEDINIPUR | Egra-I | Midnapore Mechanical | MAHABISHRA AND IT'S ADJOINING MOUJAS PWSS | SM/12510 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for MAHABISHRA and ADJOINING MOUJAS, Block ¿ Egra I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division | ORD/001582/2022-2023 | 465/W/MMD | 20/03/2023 | 31/05/2025 | DEY ENTERPRISE | 23.7 | 0 | 0 | 90
Total | [13 empty] | 72.44 | 0.95 | 1.32