## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Potashpur-II | Tamluk Division | TUPCHIBAR AND IT'S ADJOINING MOUJAS PWSS | SM/12511 | New | Material Requisition To Resource Division |  |  | RTOR000152/2022-2023 | 2458/TD | 16/01/2023 | 16/01/2023 | Resource Division | 40.42 | 0 | 0 | 0
2 | PURBA MEDINIPUR | Potashpur-II | Tamluk Division | TUPCHIBAR AND IT'S ADJOINING MOUJAS PWSS | SM/12511 | New | Material Requisition To Resource Division |  |  | RTOR000054/2024-2025 | 1665/TD | 29/04/2024 | 29/04/2024 | Resource Division | 7.01 | 0 | 0 | 0
3 | PURBA MEDINIPUR | Potashpur-II | Midnapore Mechanical | TUPCHIBAR AND IT'S ADJOINING MOUJAS PWSS | SM/12511 | New | Quotation Bill for New Service connection at T/W NO-I Of TUPCHIBAR W/S Scheme under MMD, PHE, Dte. Block- POTASHPUR-II, WBSEDCL SUPPLY OFFICE: PATASPUR C.C.C. Ref. Memo No- 2004889798/QUOT/03 DT. 12-09-2024 Application NO- 2004889798 Application type-New connection Consumer Id- 204393534 |  |  | BILL/02499/2024-2025 | C092445096068 | 30/09/2024 | 30/09/2024 | WBSEDCL | 3.76 | 0 | 0 | 0
4 | PURBA MEDINIPUR | Potashpur-II | Midnapore Mechanical | TUPCHIBAR AND IT'S ADJOINING MOUJAS PWSS | SM/12511 | New | Quotation Bill for New Service connection at T/W NO-II Of TUPCHIBAR W/S Scheme under MMD, PHE, Dte. Block- POTASHPUR-II, WBSEDCL SUPPLY OFFICE: PATASPUR C.C.C. Ref. Memo No- 2004657850/QUOT/03/1514 DT. 28-03-2024 Application NO- 2004657850 Application type-New connection Consumer Id- 204257679 |  |  | BILL/00259/2024-2025 | BP-2024-25-31 | 15/04/2024 | 15/04/2024 | WBSEDCL | 4.12 | 0 | 0 | 0
5 | PURBA MEDINIPUR | Potashpur-II | Midnapore Mechanical | TUPCHIBAR AND IT'S ADJOINING MOUJAS PWSS | SM/12511 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for TUPCHIBAR and ADJOINING MOUJAS, Block ¿ Potashpur II, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001581/2022-2023 | 464/W/MMD | 20/03/2023 | 02/03/2025 | CHOWDHURY AND BASU ENTERPRISE | 22.79 | 0 | 0 | 80
6 | PURBA MEDINIPUR | Potashpur-II | Tamluk Division | TUPCHIBAR AND IT'S ADJOINING MOUJAS PWSS | SM/12511 | New | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House & Providing Functional Household Tap Connection (61964 Nos) For 38 nos Pipe water supply Scheme including two years Operation & Maintainance within Patashpur-I, Patashpur-II , Egra-I and Deshapran Block Under Tamluk Division PHE Dte. Under Purba Medinipur District. | Assistant Engineer,Assistant Engineer, Headquaters | Junior Engineer | ORD/000677/2023-2024 | 2702/TD | 20/10/2023 | 01/10/2025 | MACKINTOSH BURN LIMITED | 19507.71 | 110.17 | 0.56 | 51
Total | [13 empty] | 19585.82 | 110.17 | 0.56