## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Moyna | Tamluk Division | SRIKANTHA AND ADJOINING MOUJAS PWSS | SM/12512 | New | Material Requisition To Resource Division |  |  | RTOR000172/2022-2023 | 2436/TD | 16/01/2023 | 16/01/2023 | Resource Division | 23.09 | 0 | 0 | 0
2 | PURBA MEDINIPUR | Moyna | Tamluk Division | SRIKANTHA AND ADJOINING MOUJAS PWSS | SM/12512 | New | Material Requisition To Resource Division |  |  | RTOR000013/2024-2025 | 1571/TD | 23/04/2024 | 23/04/2024 | Resource Division | 15.86 | 0 | 0 | 0
3 | PURBA MEDINIPUR | Moyna | Midnapore Mechanical | SRIKANTHA AND ADJOINING MOUJAS PWSS | SM/12512 | New | Quotation for new service connection at Srikanta w/s scheme PH II in the district of Purba Medinipur under MMD PHE Dte.( App No.- 2004707397, Ref ID 204292174) |  |  | BILL/01073/2024-2025 | BP-2024-25-192 | 24/05/2024 | 24/05/2024 | WBSEDCL | 8.38 | 0 | 0 | 0
4 | PURBA MEDINIPUR | Moyna | Tamluk Division | SRIKANTHA AND ADJOINING MOUJAS PWSS | SM/12512 | New | Preparation of design based on soil test report and submission of drawing of foundation for construction of 350 cum RCC OHR at SRIKANTHA PWSS at MOYNA Block under Tamluk Division, PHE Dte. Purba Medinipur District. | Assistant Engineer | Junior Engineer | ORD/000028/2025-2026 | 07/RWS/TSD | 04/04/2025 | 11/04/2025 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.95 | 0 | 0 | 100
5 | PURBA MEDINIPUR | Moyna | Tamluk Division | SRIKANTHA AND ADJOINING MOUJAS PWSS | SM/12512 | New | Installation of Land Demarcation Board at different PWSS works sites within Chandipur Block under Tamluk Division,P.H.E Dte. | Assistant Engineer, Headquaters | Junior Engineer | ORD/000500/2024-2025 | 3390/TD | 28/10/2024 | 07/11/2024 | AMITAVA MONDAL | 0.88 | 0 | 0 | 0
6 | PURBA MEDINIPUR | Moyna | Tamluk Division | SRIKANTHA AND ADJOINING MOUJAS PWSS | SM/12512 | New | Installation of Land Demarcation Board at different PWSS works sites within Ramnagar-II Block under Tamluk Division,P.H.E Dte. (Phase-II) | Assistant Engineer, Headquaters | Junior Engineer | ORD/000504/2024-2025 | 3395/TD | 28/10/2024 | 15/11/2024 | AMITAVA MONDAL | 0.88 | 0 | 0 | 0
7 | PURBA MEDINIPUR | Moyna | Tamluk Division | SRIKANTHA AND ADJOINING MOUJAS PWSS | SM/12512 | New | Installation of Land Demarcation Board at different PWSS works sites within Patashpur-II Block under Tamluk Division,P.H.E Dte. (Phase-V) | Assistant Engineer, Headquaters | Junior Engineer | ORD/000508/2024-2025 | 3389/TD | 28/10/2024 | 07/11/2024 | AMITAVA MONDAL | 0.79 | 0 | 0 | 0
8 | PURBA MEDINIPUR | Moyna | Tamluk Division | SRIKANTHA AND ADJOINING MOUJAS PWSS | SM/12512 | New | Installation of Land Demarcation Board at different PWSS works sites within Patashpur-II Block under Tamluk Division,P.H.E Dte. (Phase-III) | Assistant Engineer, Headquaters | Junior Engineer | ORD/000495/2024-2025 | 3385/TD | 28/10/2024 | 07/11/2024 | AMITAVA MONDAL | 0.88 | 0 | 0 | 0
9 | PURBA MEDINIPUR | Moyna | Tamluk Division | SRIKANTHA AND ADJOINING MOUJAS PWSS | SM/12512 | New | Installation of Land Demarcation Board at different PWSS works sites within Patashpur-II Block under Tamluk Division,P.H.E Dte. (Phase-IV) | Assistant Engineer, Headquaters | Junior Engineer | ORD/000516/2024-2025 | 3396/TD | 28/10/2024 | 07/11/2024 | TECHNO ENTERPRISE. | 0.88 | 0 | 0 | 0
10 | PURBA MEDINIPUR | Moyna | Tamluk Division | SRIKANTHA AND ADJOINING MOUJAS PWSS | SM/12512 | New | Installation of Land Demarcation Board at different PWSS works sites within Patashpur-I Block under Tamluk Division, P.H.E Dte. | Assistant Engineer, Headquaters | Junior Engineer | ORD/000469/2024-2025 | 3381/TD | 28/10/2024 | 07/11/2024 | AMITAVA MONDAL | 0.88 | 0 | 0 | 0
11 | PURBA MEDINIPUR | Moyna | Tamluk Division | SRIKANTHA AND ADJOINING MOUJAS PWSS | SM/12512 | New | Installation of Land Demarcation Board at different PWSS works sites within Patashpur-I Block under Tamluk Division,P.H.E Dte. (Phase-II) | Assistant Engineer, Headquaters | Junior Engineer | ORD/000505/2024-2025 | 3383/TD | 28/10/2024 | 07/11/2024 | AMITAVA MONDAL | 0.79 | 0 | 0 | 0
12 | PURBA MEDINIPUR | Moyna | Tamluk Division | SRIKANTHA AND ADJOINING MOUJAS PWSS | SM/12512 | New | Installation of Land Demarcation Board at different PWSS works sites within Patashpur-II under Tamluk Division,P.H.E Dte. | Assistant Engineer, Headquaters | Junior Engineer | ORD/000467/2024-2025 | 3379/TD | 28/10/2024 | 07/11/2024 | AMITAVA MONDAL | 0.88 | 0 | 0 | 0
13 | PURBA MEDINIPUR | Moyna | Tamluk Division | SRIKANTHA AND ADJOINING MOUJAS PWSS | SM/12512 | New | Installation of Land Demarcation Board at different PWSS works sites within Bhagwanpur-I Block under Tamluk Division,P.H.E Dte. (Phase-III) | Assistant Engineer, Headquaters | Junior Engineer | ORD/000502/2024-2025 | 3392/TD | 28/10/2024 | 07/11/2024 | TECHNO ENTERPRISE. | 0.88 | 0 | 0 | 0
14 | PURBA MEDINIPUR | Moyna | Tamluk Division | SRIKANTHA AND ADJOINING MOUJAS PWSS | SM/12512 | New | Installation of Land Demarcation Board at different PWSS works sites within Patashpur-II & Bhagwanpur-I Block under Tamluk Division,P.H.E Dte. | Assistant Engineer, Headquaters | Junior Engineer | ORD/000507/2024-2025 | 3388/TD | 28/10/2024 | 07/11/2024 | TECHNO ENTERPRISE. | 0.62 | 0 | 0 | 0
15 | PURBA MEDINIPUR | Moyna | Tamluk Division | SRIKANTHA AND ADJOINING MOUJAS PWSS | SM/12512 | New | Installation of Land Demarcation Board at different PWSS works sites within Ramnagar-II Block under Tamluk Division, P.H.E Dte. | Assistant Engineer, Headquaters | Junior Engineer | ORD/000468/2024-2025 | 3380/TD | 28/10/2024 | 07/11/2024 | AMITAVA MONDAL | 0.88 | 0 | 0 | 0
16 | PURBA MEDINIPUR | Moyna | Tamluk Division | SRIKANTHA AND ADJOINING MOUJAS PWSS | SM/12512 | New | Installation of Land Demarcation Board at different PWSS works sites within Patshpur-II Block under Tamluk Division,P.H.E Dte. (Phase-II) | Assistant Engineer, Headquaters | Junior Engineer | ORD/000501/2024-2025 | 3391/TD | 28/10/2024 | 07/11/2024 | TECHNO ENTERPRISE. | 0.88 | 0 | 0 | 0
Total | [13 empty] | 58.4 | 0 | 0