## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Moyna | Tamluk Division | SRIKANTHA AND ADJOINING MOUJAS PWSS | SM/12512 | New | Material Requisition To Resource Division |  |  | RTOR000172/2022-2023 | 2436/TD | 16/01/2023 | 16/01/2023 | Resource Division | 23.09 | 0 | 0 | 0
2 | PURBA MEDINIPUR | Moyna | Tamluk Division | SRIKANTHA AND ADJOINING MOUJAS PWSS | SM/12512 | New | Material Requisition To Resource Division |  |  | RTOR000013/2024-2025 | 1571/TD | 23/04/2024 | 23/04/2024 | Resource Division | 15.86 | 0 | 0 | 0
3 | PURBA MEDINIPUR | Moyna | Midnapore Mechanical | SRIKANTHA AND ADJOINING MOUJAS PWSS | SM/12512 | New | Quotation for new service connection at Srikanta w/s scheme PH II in the district of Purba Medinipur under MMD PHE Dte.( App No.- 2004707397, Ref ID 204292174) |  |  | BILL/01073/2024-2025 | BP-2024-25-192 | 24/05/2024 | 24/05/2024 | WBSEDCL | 8.38 | 0 | 0 | 0
4 | PURBA MEDINIPUR | Moyna | Tamluk Division | SRIKANTHA AND ADJOINING MOUJAS PWSS | SM/12512 | New | Preparation of design based on soil test report and submission of drawing of foundation for construction of 350 cum RCC OHR at SRIKANTHA PWSS at MOYNA Block under Tamluk Division, PHE Dte. Purba Medinipur District. | Assistant Engineer | Junior Engineer | ORD/000028/2025-2026 | 07/RWS/TSD | 04/04/2025 | 11/04/2025 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.95 | 0 | 0 | 100
5 | PURBA MEDINIPUR | Moyna | Tamluk Division | SRIKANTHA AND ADJOINING MOUJAS PWSS | SM/12512 | New | Installation of Land Demarcation Board at different PWSS works sites within Chandipur Block under Tamluk Division,P.H.E Dte. | Assistant Engineer, Headquaters | Junior Engineer | ORD/000500/2024-2025 | 3390/TD | 28/10/2024 | 07/11/2024 | AMITAVA MONDAL | 0.88 | 0 | 0 | 0
6 | PURBA MEDINIPUR | Moyna | Tamluk Division | SRIKANTHA AND ADJOINING MOUJAS PWSS | SM/12512 | New | Installation of Land Demarcation Board at different PWSS works sites within Ramnagar-II Block under Tamluk Division,P.H.E Dte. (Phase-II) | Assistant Engineer, Headquaters | Junior Engineer | ORD/000504/2024-2025 | 3395/TD | 28/10/2024 | 15/11/2024 | AMITAVA MONDAL | 0.88 | 0 | 0 | 0
7 | PURBA MEDINIPUR | Moyna | Tamluk Division | SRIKANTHA AND ADJOINING MOUJAS PWSS | SM/12512 | New | Installation of Land Demarcation Board at different PWSS works sites within Patashpur-II Block under Tamluk Division,P.H.E Dte. (Phase-V) | Assistant Engineer, Headquaters | Junior Engineer | ORD/000508/2024-2025 | 3389/TD | 28/10/2024 | 07/11/2024 | AMITAVA MONDAL | 0.79 | 0 | 0 | 0
8 | PURBA MEDINIPUR | Moyna | Tamluk Division | SRIKANTHA AND ADJOINING MOUJAS PWSS | SM/12512 | New | Installation of Land Demarcation Board at different PWSS works sites within Patashpur-II Block under Tamluk Division,P.H.E Dte. (Phase-III) | Assistant Engineer, Headquaters | Junior Engineer | ORD/000495/2024-2025 | 3385/TD | 28/10/2024 | 07/11/2024 | AMITAVA MONDAL | 0.88 | 0 | 0 | 0
9 | PURBA MEDINIPUR | Moyna | Tamluk Division | SRIKANTHA AND ADJOINING MOUJAS PWSS | SM/12512 | New | Installation of Land Demarcation Board at different PWSS works sites within Patashpur-II Block under Tamluk Division,P.H.E Dte. (Phase-IV) | Assistant Engineer, Headquaters | Junior Engineer | ORD/000516/2024-2025 | 3396/TD | 28/10/2024 | 07/11/2024 | TECHNO ENTERPRISE. | 0.88 | 0 | 0 | 0
10 | PURBA MEDINIPUR | Moyna | Tamluk Division | SRIKANTHA AND ADJOINING MOUJAS PWSS | SM/12512 | New | Installation of Land Demarcation Board at different PWSS works sites within Patashpur-I Block under Tamluk Division, P.H.E Dte. | Assistant Engineer, Headquaters | Junior Engineer | ORD/000469/2024-2025 | 3381/TD | 28/10/2024 | 07/11/2024 | AMITAVA MONDAL | 0.88 | 0 | 0 | 0
11 | PURBA MEDINIPUR | Moyna | Tamluk Division | SRIKANTHA AND ADJOINING MOUJAS PWSS | SM/12512 | New | Installation of Land Demarcation Board at different PWSS works sites within Patashpur-I Block under Tamluk Division,P.H.E Dte. (Phase-II) | Assistant Engineer, Headquaters | Junior Engineer | ORD/000505/2024-2025 | 3383/TD | 28/10/2024 | 07/11/2024 | AMITAVA MONDAL | 0.79 | 0 | 0 | 0
12 | PURBA MEDINIPUR | Moyna | Tamluk Division | SRIKANTHA AND ADJOINING MOUJAS PWSS | SM/12512 | New | Installation of Land Demarcation Board at different PWSS works sites within Patashpur-II under Tamluk Division,P.H.E Dte. | Assistant Engineer, Headquaters | Junior Engineer | ORD/000467/2024-2025 | 3379/TD | 28/10/2024 | 07/11/2024 | AMITAVA MONDAL | 0.88 | 0 | 0 | 0
13 | PURBA MEDINIPUR | Moyna | Tamluk Division | SRIKANTHA AND ADJOINING MOUJAS PWSS | SM/12512 | New | Installation of Land Demarcation Board at different PWSS works sites within Bhagwanpur-I Block under Tamluk Division,P.H.E Dte. (Phase-III) | Assistant Engineer, Headquaters | Junior Engineer | ORD/000502/2024-2025 | 3392/TD | 28/10/2024 | 07/11/2024 | TECHNO ENTERPRISE. | 0.88 | 0 | 0 | 0
14 | PURBA MEDINIPUR | Moyna | Tamluk Division | SRIKANTHA AND ADJOINING MOUJAS PWSS | SM/12512 | New | Installation of Land Demarcation Board at different PWSS works sites within Patashpur-II & Bhagwanpur-I Block under Tamluk Division,P.H.E Dte. | Assistant Engineer, Headquaters | Junior Engineer | ORD/000507/2024-2025 | 3388/TD | 28/10/2024 | 07/11/2024 | TECHNO ENTERPRISE. | 0.62 | 0 | 0 | 0
15 | PURBA MEDINIPUR | Moyna | Tamluk Division | SRIKANTHA AND ADJOINING MOUJAS PWSS | SM/12512 | New | Installation of Land Demarcation Board at different PWSS works sites within Ramnagar-II Block under Tamluk Division, P.H.E Dte. | Assistant Engineer, Headquaters | Junior Engineer | ORD/000468/2024-2025 | 3380/TD | 28/10/2024 | 07/11/2024 | AMITAVA MONDAL | 0.88 | 0 | 0 | 0
16 | PURBA MEDINIPUR | Moyna | Tamluk Division | SRIKANTHA AND ADJOINING MOUJAS PWSS | SM/12512 | New | Installation of Land Demarcation Board at different PWSS works sites within Patshpur-II Block under Tamluk Division,P.H.E Dte. (Phase-II) | Assistant Engineer, Headquaters | Junior Engineer | ORD/000501/2024-2025 | 3391/TD | 28/10/2024 | 07/11/2024 | TECHNO ENTERPRISE. | 0.88 | 0 | 0 | 0
17 | PURBA MEDINIPUR | Moyna | Tamluk Division | SRIKANTHA AND ADJOINING MOUJAS PWSS | SM/12512 | New | Installation of display Board at 4 nos {1. SRIKHANTA PWSS,( PUMP HOUSE 1 & 2) 2. KIYARANA PWSS ( PUMP HOUSE -1 &2), all are under Moyna Development Block work site for Open Land under Tamluk Division, PHE Dte. Purba Medinipur District. | Assistant Engineer | Junior Engineer | ORD/000256/2025-2026 | 62/RWS/TSD | 06/05/2025 | 13/05/2025 | SUDIP MANNA | 0.69 | 0 | 0 | 100
18 | PURBA MEDINIPUR | Moyna | Tamluk Division | SRIKANTHA AND ADJOINING MOUJAS PWSS | SM/12512 | New | Installation of Land Demarcation Board at different PWSS works sites within Ramnagar-II & Chandipur Block under Tamluk Division,P.H.E Dte. | Assistant Engineer, Headquaters | Junior Engineer | ORD/000509/2024-2025 | 3394/TD | 28/10/2024 | 07/11/2024 | AMITAVA MONDAL | 0.79 | 0 | 0 | 0
19 | PURBA MEDINIPUR | Moyna | Midnapore Mechanical | SRIKANTHA AND ADJOINING MOUJAS PWSS | SM/12512 | New | New service connection at Srikantha w/s scheme PH I ind the district of Purba Medinipur under MMD PHE Dte.(App No 2005056297, Con ID 2045505102) |  |  | BILL/04274/2024-2025 | C032554814129 | 17/03/2025 | 17/03/2025 | WBSEDCL | 5.55 | 0 | 0 | 0
20 | PURBA MEDINIPUR | Moyna | Tamluk Division | SRIKANTHA AND ADJOINING MOUJAS PWSS | SM/12512 | New | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House & Providing Functional Household Tap Connection (32862 Nos), including 2 years Operation & Maintenance For 21 nos Pipe Water Supply Scheme within MOYNA AND CONTAI -I Block Under Tamluk Division PHE Dte. Under Purba Medinipur District. | Assistant Engineer | Junior Engiener,Junior Engineer | ORD/000538/2023-2024 | 1937/TD | 16/08/2023 | 28/03/2026 | MACKINTOSH BURN LIMITED | 10310.59 | 115.91 | 1.12 | 75
21 | PURBA MEDINIPUR | Moyna | Midnapore Mechanical | SRIKANTHA AND ADJOINING MOUJAS PWSS | SM/12512 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for SRIKANTHA and ADJOINING MOUJAS, Block ¿ Moyna, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/001588/2022-2023 | 471/W/MMD | 20/03/2023 | 30/10/2025 | SOUMEN ELECTRIC | 25.24 | 19.29 | 76.41 | 60
Total | [13 empty] | 10401.26 | 135.2 | 1.3