## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Potashpur-II | Tamluk Division | KSHETRAPAL AND IT'S ADJOINING MOUJAS | SM/12513 | New | Material Requisition To Resource Division |  |  | RTOR000150/2022-2023 | 2456/TD | 16/01/2023 | 16/01/2023 | Resource Division | 19.2 | 0 | 0 | 0
2 | PURBA MEDINIPUR | Potashpur-II | Tamluk Division | KSHETRAPAL AND IT'S ADJOINING MOUJAS | SM/12513 | New | Preparation of design based on soil test report and submission of drawing of foundation for construction of 250 cum RCC OHR at Kshetrapal PWSS at Patashpur-II Block under Tamluk Division, PHE Dte. | Assistant Engineer, Headquaters |  | ORD/000158/2024-2025 | 2070/TD | 24/06/2024 | 04/07/2024 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.95 | 0.95 | 100 | 100
3 | PURBA MEDINIPUR | Potashpur-II | Tamluk Division | KSHETRAPAL AND IT'S ADJOINING MOUJAS | SM/12513 | New | Material Requisition To Resource Division |  |  | RTOR000050/2024-2025 | 1657/TD | 29/04/2024 | 29/04/2024 | Resource Division | 11.58 | 0 | 0 | 0
4 | PURBA MEDINIPUR | Potashpur-II | Midnapore Mechanical | KSHETRAPAL AND IT'S ADJOINING MOUJAS | SM/12513 | New | Quotation Bill for New Service connection at T/W NO-I Of KSHETRAPAL W/S Scheme under MMD, PHE, Dte. Block- POTASHPUR-II, WBSEDCL SUPPLY OFFICE: PATASPUR C.C.C. Ref. Memo No- 2004685984/QUOT/03 DT. 16-04-2024 Application NO- 2004685984 Application type-New connection Consumer Id- 204277213 |  |  | BILL/00575/2024-2025 | BP-2024-25-103 | 26/04/2024 | 26/04/2024 | WBSEDCL | 3.53 | 0 | 0 | 0
5 | PURBA MEDINIPUR | Potashpur-II | Midnapore Mechanical | KSHETRAPAL AND IT'S ADJOINING MOUJAS | SM/12513 | New | Quotation Bill for New Service connection at T/W NO-II Of KSHETRAPAL W/S Scheme under MMD, PHE, Dte. Block- POTASHPUR-II, WBSEDCL SUPPLY OFFICE: PATASPUR C.C.C. Ref. Memo No- 2004686002/QUOT/03 DT. 16-04-2024 Application NO- 2004686002 Application type-New connection Consumer Id- 204277214 |  |  | BILL/00574/2024-2025 | BP-2024-25-104 | 26/04/2024 | 26/04/2024 | WBSEDCL | 5.44 | 0 | 0 | 0
6 | PURBA MEDINIPUR | Potashpur-II | Midnapore Mechanical | KSHETRAPAL AND IT'S ADJOINING MOUJAS | SM/12513 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for KSHETRAPAL and ADJOINING MOUJAS, Block - Potashpur II, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001637/2022-2023 | 517/W/MMD | 20/03/2023 | 01/06/2025 | KARUNAMOY ENGINEERING | 22.75 | 0 | 0 | 70
7 | PURBA MEDINIPUR | Potashpur-II | Midnapore Mechanical | KSHETRAPAL AND IT'S ADJOINING MOUJAS | SM/12513 | New | Hiring of inspection vehicle for supervision and monitoring of different on-going piped water supply scheme for covering Contai Sub-Division and its adjacent Sub-Division under the Dist. of Purba Medinipur under Jal Jeevan Mission programe. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000749/2023-2024 | 688/HESD | 29/08/2023 | 29/08/2024 | S.S.GHORAI | 2.12 | 0 | 0 | 50
8 | PURBA MEDINIPUR | Potashpur-II | Tamluk Division | KSHETRAPAL AND IT'S ADJOINING MOUJAS | SM/12513 | New | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House & Providing Functional Household Tap Connection (61964 Nos) For 38 nos Pipe water supply Scheme including two years Operation & Maintainance within Patashpur-I, Patashpur-II , Egra-I and Deshapran Block Under Tamluk Division PHE Dte. Under Purba Medinipur District. | Assistant Engineer,Assistant Engineer, Headquaters | Junior Engineer | ORD/000677/2023-2024 | 2702/TD | 20/10/2023 | 30/03/2026 | MACKINTOSH BURN LIMITED | 19507.71 | 255.57 | 1.31 | 51
Total | [13 empty] | 19573.27 | 256.52 | 1.31