## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Ramnagar-I | Tamluk Division | KAINARA & IT'S ADJOING MOUJAS | SM/12514 | New | Material Requisition To Resource Division |  |  | RTOR000270/2022-2023 | 2698/TD | 06/02/2023 | 06/02/2023 | Resource Division | 65.99 | 0 | 0 | 0
2 | PURBA MEDINIPUR | Ramnagar-I | Tamluk Division | KAINARA & IT'S ADJOING MOUJAS | SM/12514 | New | Material Requisition To Resource Division |  |  | RTOR000147/2023-2024 | 102/TD | 05/01/2024 | 05/01/2024 | Resource Division | 13.76 | 0 | 0 | 0
3 | PURBA MEDINIPUR | Ramnagar-I | Midnapore Mechanical | KAINARA & IT'S ADJOING MOUJAS | SM/12514 | New | Quotation Bill for New Service connection at T/W NO-II Of KAINARA W/S Scheme under MMD, PHE, Dte. Block- RAMANAGR-I, WBSEDCL SUPPLY OFFICE: DIGHA C.C.C. Ref. Memo No- 2004738882/QUOT/03 DT. 17-05-2024 Application NO-2004738882 Application type-New connection Consumer Id- 204309127 |  |  | BILL/01097/2024-2025 | BP-2024-25-226 | 31/05/2024 | 31/05/2024 | WBSEDCL | 4.09 | 0 | 0 | 0
4 | PURBA MEDINIPUR | Ramnagar-I | Midnapore Mechanical | KAINARA & IT'S ADJOING MOUJAS | SM/12514 | New | Quotation for new service connection at TW-I of KAINARA WS SCHEME under MMD,PHE Dte, Block-Ramnagar-I, DIGHA CCC, Application no-2004644445, CON ID-204246842 |  |  | BILL/04740/2023-2024 | BP-2023-24-914 | 28/03/2024 | 28/03/2024 | WBSEDCL | 6.46 | 0 | 0 | 0
5 | PURBA MEDINIPUR | Ramnagar-I | Midnapore Mechanical | KAINARA & IT'S ADJOING MOUJAS | SM/12514 | New | Quotation Bill for Shifting of LT POLE AT KAINARA T/W NO-I , BLOCK: RAMNAGRA -I WBSEDCL SUPPLY OFFICE: DIGHA C.C.C. Ref. MEMO No- DGA/QT/1042 Dt. 17.09.2024 Application NO- 100000119117 Dt. 17/09/2024 Reference Id- 860313097 |  |  | BILL/02500/2024-2025 | C102415728122 | 05/10/2024 | 05/10/2024 | WBSEDCL | 0.33 | 0 | 0 | 0
6 | PURBA MEDINIPUR | Ramnagar-I | Tamluk Division | KAINARA & IT'S ADJOING MOUJAS | SM/12514 | New | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House, Pipe carrying structure & Providing Functional Household Tap Connection (2813 Nos) For 2 nos Pipe Water Supply Scheme (Kainara & Nilkanthpur)including two years Operation & Maintainance work within Ramnagar-I Block Under Digha Sub Division of Tamluk Division, PHE. Dept, Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000681/2023-2024 | 2710/TD | 30/10/2023 | 28/12/2025 | TAPAS SANTRA | 866.03 | 368.95 | 42.6 | 85
7 | PURBA MEDINIPUR | Ramnagar-I | Midnapore Mechanical | KAINARA & IT'S ADJOING MOUJAS | SM/12514 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for KAINARA and ADJOINING MOUJAS, Block - Ramnagar I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division | ORD/001656/2022-2023 | 527/W/MMD | 20/03/2023 | 16/09/2023 | BHABANI PRASAD MANNA | 23.7 | 21.72 | 91.64 | 75
Total | [13 empty] | 980.36 | 390.67 | 39.85