## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Moyna | Tamluk Division | DKSHIM ANKHA & IT'S ADJOINING MOUJAS | SM/12515 | New | Material Requisition To Resource Division |  |  | RTOR000326/2022-2023 | 2990/TD | 27/02/2023 | 27/02/2023 | Resource Division | 46.28 | 0 | 0 | 0
2 | PURBA MEDINIPUR | Moyna | Tamluk Division | DKSHIM ANKHA & IT'S ADJOINING MOUJAS | SM/12515 | New | Laying distribution System, & Accommodate FHTC (50 nos) under JJM with allied work for Dakshin Ankha PWSS in Moyna Block including supply of all labour & materials within Tamluk Sub-Division under Tamluk Division, PHE Dte, Purba Medinipur. (PART-I) | Assistant Engineer | Junior Engineer | ORD/000185/2023-2024 | 375/TD | 27/04/2023 | 17/05/2023 | MRITYUNJOY PARIA | 9.97 | 0 | 0 | 60
3 | PURBA MEDINIPUR | Moyna | Tamluk Division | DKSHIM ANKHA & IT'S ADJOINING MOUJAS | SM/12515 | New | Laying distribution System, & Accommodate FHTC (50 nos) under JJM with allied work for Dakshin Ankha PWSS in Moyna Block including supply of all labour & materials within Tamluk Sub-Division under Tamluk Division, PHE Dte, Purba Medinipur. (PART-G) | Assistant Engineer | Junior Engineer | ORD/000183/2023-2024 | 373/TD | 27/04/2023 | 17/05/2023 | ACHINTA KUMAR HALDER | 9.86 | 0 | 0 | 71
4 | PURBA MEDINIPUR | Moyna | Tamluk Division | DKSHIM ANKHA & IT'S ADJOINING MOUJAS | SM/12515 | New | Laying distribution System, & Accommodate FHTC (50 nos) under JJM with allied work for Dakshin Ankha PWSS in Moyna Block including supply of all labour & materials within Tamluk Sub-Division under Tamluk Division, PHE Dte, Purba Medinipur. (PART-H) | Assistant Engineer | Junior Engineer | ORD/000184/2023-2024 | 374/TD | 27/04/2023 | 17/05/2023 | BAGLAMUKHI SECURITY SERVICE | 10 | 0 | 0 | 56
5 | PURBA MEDINIPUR | Moyna | Tamluk Division | DKSHIM ANKHA & IT'S ADJOINING MOUJAS | SM/12515 | New | Laying distribution System, Construction of Boundary wall at 1st. Tube well site & Accommodate FHTC (385 nos) under JJM with allied work for Dakshin Ankha PWSS in Moyna Block including supply of all labour & materials within Tamluk Sub-Division under Tamluk Division, PHE Dte, Purba Medinipur. (PART-B) | Assistant Engineer | Junior Engineer | ORD/000250/2023-2024 | 514/TD | 11/05/2023 | 22/02/2026 | MAA KALI CONSTRUCTION | 77.96 | 0 | 0 | 3
6 | PURBA MEDINIPUR | Moyna | Tamluk Division | DKSHIM ANKHA & IT'S ADJOINING MOUJAS | SM/12515 | New | Laying distribution System, Construction of Boundary Wall at 2nd. Tube well site , & Accommodate FHTC (500 nos) under JJM with allied work for Dakshin Ankha PWSS in Moyna Block including supply of all labour & materials within Tamluk Sub-Division under Tamluk Division, PHE Dte, Purba Medinipur. (PART-C) | Assistant Engineer | Junior Engineer | ORD/000251/2023-2024 | 515/TD | 11/05/2023 | 10/07/2023 | SHAKEEL KHAN | 89.3 | 0 | 0 | 31
7 | PURBA MEDINIPUR | Moyna | Tamluk Division | DKSHIM ANKHA & IT'S ADJOINING MOUJAS | SM/12515 | New | Laying distribution System, & Accommodate FHTC (50 nos) under JJM with allied work for Dakshin Ankha PWSS in Moyna Block including supply of all labour & materials within Tamluk Sub-Division under Tamluk Division, PHE Dte, Purba Medinipur. (PART-J) | Assistant Engineer | Junior Engineer | ORD/000702/2023-2024 | 2813/TD | 07/11/2023 | 27/11/2023 | CHANDA AGENCIES | 9.93 | 0 | 0 | 81
8 | PURBA MEDINIPUR | Moyna | Tamluk Division | DKSHIM ANKHA & IT'S ADJOINING MOUJAS | SM/12515 | New | Development of low land and construction of Link Road by carried earth at H/W Site for Dakshin Anukha PWSS under Tamluk Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000698/2023-2024 | 2738/TD | 01/11/2023 | 10/11/2025 | MAA KALI CONSTRUCTION | 6.92 | 0 | 0 | 25
9 | PURBA MEDINIPUR | Moyna | Central Drilling | DKSHIM ANKHA & IT'S ADJOINING MOUJAS | SM/12515 | New | Providing drilling crews Including Allied Materials for construction of Tube Well (300mm X200mm) at Dakshin Ankha PWSS within Moyna Block under Central Drilling Division, P.H.E. Dte. | Driller In Charge | Junior Engineer | ORD/000176/2023-2024 | 1469/CDD | 27/09/2023 | 24/04/2024 | PADMA ENGINEERING & CO. | 14.74 | 0 | 0 | 100
10 | PURBA MEDINIPUR | Moyna | Tamluk Division | DKSHIM ANKHA & IT'S ADJOINING MOUJAS | SM/12515 | New | Proposed retaining wall cum guard wall , approach road, earth filling at 2nd tube site under Dakshin Anukha and its adjoining mouzas PWSS under Moyna development block under Tamluk Sub-Division in Tamluk Division ,Dist-Pruba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000719/2023-2024 | 2941/TD | 23/11/2023 | 18/12/2023 | NARAYAN MANDAL | 8.22 | 0 | 0 | 60
11 | PURBA MEDINIPUR | Moyna | Central Drilling | DKSHIM ANKHA & IT'S ADJOINING MOUJAS | SM/12515 | New | Providing drilling crews Including Allied Materials for construction of Tube Well ( 250mm X150mm) at Dakshin Ankha W/S Scheme within Purba Medinipur District under Central Drilling Division, P.H.E. Dte. | Driller In Charge | Junior Engineer | ORD/000178/2023-2024 | 1414/CDD | 20/09/2023 | 17/04/2024 | MENAKA ENTERPRISE | 11.26 | 0 | 0 | 100
12 | PURBA MEDINIPUR | Moyna | Tamluk Division | DKSHIM ANKHA & IT'S ADJOINING MOUJAS | SM/12515 | New | Proposed Retaining wall cum Gurad Wall at Head work site under Dakshin Anukha and its Adjoning mouzas PWSS under Moyna Block Development Block under Tamluk Sub Division in Tamluk Division, Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000139/2024-2025 | 1928/TD | 07/06/2024 | 07/07/2024 | M J A ENTERPRISE | 3.33 | 0 | 0 | 100
13 | PURBA MEDINIPUR | Moyna | Central Drilling | DKSHIM ANKHA & IT'S ADJOINING MOUJAS | SM/12515 | New | Providing drilling crew and other allied works for construction of Tube Well ( 300mm X200mm X 250 Mtrs. Depth) by utilising Departmental Machineries for Dakshin Ankha W/S Scheme ( TW- II) , Moyna Block under Purba Midnapur District, Central Drilling Division, P.H.E. Dte. | Driller In Charge | Junior Engineer | ORD/000221/2023-2024 | 1844//CDD | 18/12/2023 | 16/04/2024 | PADMA ENGINEERING & CO. | 14.69 | 0 | 0 | 100
14 | PURBA MEDINIPUR | Moyna | Tamluk Division | DKSHIM ANKHA & IT'S ADJOINING MOUJAS | SM/12515 | New | Material Requisition To Resource Division |  |  | RTOR000004/2024-2025 | 1562/TD | 23/04/2024 | 23/04/2024 | Resource Division | 10.07 | 0 | 0 | 0
15 | PURBA MEDINIPUR | Moyna | Midnapore Mechanical | DKSHIM ANKHA & IT'S ADJOINING MOUJAS | SM/12515 | New | Additional quotation for Dakhin Anukha w/s scheme PH II in the district of Purba Medinipur under MMD PHE Dte. ( App ID 100000112312, Ref ID 860303992) |  |  | BILL/01721/2024-2025 | BP-2024-25-496 | 30/07/2024 | 30/07/2024 | WBSEDCL | 0.99 | 0 | 0 | 0
16 | PURBA MEDINIPUR | Moyna | Midnapore Mechanical | DKSHIM ANKHA & IT'S ADJOINING MOUJAS | SM/12515 | New | Quotation for Dakhin Ankha w/s scheme PH-I in the district of Purba Medinipur under MMD PHE dte.(Application No.-2004608983, Ref ID-204222616) |  |  | BILL/04501/2023-2024 | BP-2023-24-858 | 16/03/2024 | 16/03/2024 | WBSEDCL | 3.47 | 0 | 0 | 0
17 | PURBA MEDINIPUR | Moyna | Midnapore Mechanical | DKSHIM ANKHA & IT'S ADJOINING MOUJAS | SM/12515 | New | Quotation for Dakhin Ankha w/s scheme PH-II in the district of Purba Medinipur under MMD PHE dte.(Application No.-2004608987, Ref ID-204222617) |  |  | BILL/04496/2023-2024 | BP-2023-24-859 | 16/03/2024 | 16/03/2024 | WBSEDCL | 3.58 | 0 | 0 | 0
18 | PURBA MEDINIPUR | Moyna | Midnapore Mechanical | DKSHIM ANKHA & IT'S ADJOINING MOUJAS | SM/12515 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for DKSHIM ANKHA and ADJOINING MOUJAS, Block - Moyna, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/001636/2022-2023 | 516/W/MMD | 20/03/2023 | 31/01/2025 | KARUNAMOY ENGINEERING | 22.75 | 0 | 0 | 100
19 | PURBA MEDINIPUR | Moyna | Tamluk Division | DKSHIM ANKHA & IT'S ADJOINING MOUJAS | SM/12515 | New | Laying distribution System, Switch Room cum Chlorine Room I & II , Accommodate FHTC (550 nos) & Rising Main under JJM with allied work for Dakshin Ankha PWSS in Moyna Block including supply of all labour & materials within Tamluk Sub-Division under Tamluk Division, PHE Dte, Purba Medinipur. (PART-A) | Assistant Engineer | Junior Engineer | ORD/000293/2023-2024 | 582/TD | 16/05/2023 | 28/10/2025 | NARAYAN MANDAL | 138.66 | 0 | 0 | 80
20 | PURBA MEDINIPUR | Moyna | Tamluk Division | DKSHIM ANKHA & IT'S ADJOINING MOUJAS | SM/12515 | New | Soil investigation & R.C.C. Elevated Reservoir of capacity 250 cum and staging height 20.00 mtr. as per Departmental Drawing (Intze type with pile foundation) under JJM with allied work for Dakshin Ankha PWSS in Moyna Block including supply of all labour & materials within Tamluk Sub-Division under Tamluk Division, PHE Dte, Purba Medinipur. (PART-E) | Assistant Engineer | Junior Engineer | ORD/000528/2023-2024 | 1777/TD | 02/08/2023 | 30/11/2025 | NEW STAR CONSTRUCTION | 108.73 | 0 | 0 | 90
21 | PURBA MEDINIPUR | Moyna | Midnapore Mechanical | DKSHIM ANKHA & IT'S ADJOINING MOUJAS | SM/12515 | New | Hiring of inspection vehicle for supervision and monitoring of different on-going piped water supply scheme for covering Contai Sub-Division and its adjacent Sub-Division under the Dist. of Purba Medinipur under Jal Jeevan Mission programe. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division,Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000749/2023-2024 | 688/HESD | 29/08/2023 | 29/08/2024 | S.S.GHORAI | 2.12 | 0 | 0 | 50
Total | [13 empty] | 602.82 | 0 | 0