## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Egra-II | Midnapore Mechanical | MIRJAPUR AND IT'S ADJOINING MOUJAS | SM/12516 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for MIRJAPUR and ADJOINING MOUJAS, Block - Egra II, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001615/2022-2023 | 506/W/MMD | 20/03/2023 | 16/09/2023 | M/S DILIP MITRA | 21.59 | 0 | 0 | 0
2 | PURBA MEDINIPUR | Egra-II | Tamluk Division | MIRJAPUR AND IT'S ADJOINING MOUJAS | SM/12516 | New | Material Requisition To Resource Division |  |  | RTOR000319/2022-2023 | 2973/TD | 27/02/2023 | 27/02/2023 | Resource Division | 37.6 | 0 | 0 | 0
3 | PURBA MEDINIPUR | Egra-II | Tamluk Division | MIRJAPUR AND IT'S ADJOINING MOUJAS | SM/12516 | New | Laying distribution pipe line, under JJM with allied work for Mirjapur PWSS within Egra-II Block including supply of all labour & materials under Digha Sub-Division of Tamluk Division, PHE Dte. (PART-C) | Assistant Engineer | Junior Engineer | ORD/000127/2023-2024 | 258/TD | 19/04/2023 | 14/05/2023 | MENAKA ENTERPRISE | 13.21 | 0 | 0 | 0
4 | PURBA MEDINIPUR | Egra-II | Midnapore Mechanical | MIRJAPUR AND IT'S ADJOINING MOUJAS | SM/12516 | New | Quotation Bill for New Service connection at T/W NO-I Of MIRJAPUR W/S Scheme under MMD, PHE, Dte. Block- EGRA-II, WBSEDCL SUPPLY OFFICE: BALIGHAI C.C.C. Ref. Memo No- 2004671915/QUOT/03/50 DT. 05-04-2024 Application NO- 2004671915 Application type-New connection Consumer Id- 204266735 |  |  | BILL/00514/2024-2025 | BP-2024-25-92 | 24/04/2024 | 24/04/2024 | WBSEDCL | 4.49 | 0 | 0 | 0
5 | PURBA MEDINIPUR | Egra-II | Tamluk Division | MIRJAPUR AND IT'S ADJOINING MOUJAS | SM/12516 | New | Soil investigation, 150 cum OHR (Torch type with pile foundation) under JJM with allied work for Mirjapur PWSS within Egra-II Block including supply of all labour & materials under Digha Sub-Division of Tamluk Division, PHE Dte. (PART-D) | Assistant Engineer | Junior Engineer | ORD/000254/2023-2024 | 522/TD | 11/05/2023 | 28/12/2025 | SASWATA CONSTRUCTION | 86.46 | 0 | 0 | 0
6 | PURBA MEDINIPUR | Egra-II | Central Drilling | MIRJAPUR AND IT'S ADJOINING MOUJAS | SM/12516 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 64.14 | 0.3 | 11
7 | PURBA MEDINIPUR | Egra-II | Tamluk Division | MIRJAPUR AND IT'S ADJOINING MOUJAS | SM/12516 | New | Laying distribution pipe line, Pump House , Boundary Wall , Laying rising main pipe line & Accommodate FHTC (835 nos) under JJM with allied work for Mirjapur PWSS within Egra-II Block including supply of all labour & materials under Digha Sub-Division of Tamluk Division, PHE Dte. (PART-A) | Assistant Engineer | Junior Engineer | ORD/000518/2023-2024 | 1754/TD | 01/08/2023 | 09/07/2025 | BARH CONSTRUCTION | 211.44 | 0 | 0 | 70
8 | PURBA MEDINIPUR | Egra-II | Tamluk Division | MIRJAPUR AND IT'S ADJOINING MOUJAS | SM/12516 | New | Requirement of additional pipeline for distribution pipeline due to revised drawing for Mirjapur PWSS under JJM within Egra-II Block under Digha Sub-Division of Tamluk Division, P.H.E. Dte. within Purba Medinipur District. | Assistant Engineer | Junior Engineer | ORD/001179/2023-2024 | 723/TD | 28/02/2024 | 31/05/2025 | ELECTIVA ENTERPRISE | 6.28 | 0 | 0 | 0
9 | PURBA MEDINIPUR | Egra-II | Central Drilling | MIRJAPUR AND IT'S ADJOINING MOUJAS | SM/12516 | New | Hiring of Diesel driven motor cab (BS-III & Above) (Non AC) having contract carriage permit along with driver for the office of the DIC/ CMSD-I P.H.E. Dte. Under CMSD-I(D), CDD, P.H.E. Dte. | Driller In Charge | Junior Engineer | ORD/000006/2024-2025 | 253/CMSD-I | 26/06/2024 | 25/12/2024 | SUJATA BHOWMICK | 0.86 | 2.11 | 244.53 | 0
10 | PURBA MEDINIPUR | Egra-II | Midnapore Mechanical | MIRJAPUR AND IT'S ADJOINING MOUJAS | SM/12516 | New | Supply and fitting fixing of porcelain fuse unit and aluminum armored cable for receiving service connection at different PWSS under Egra-II, Bhagwanpur-I and II Block under Medinapore Mechanical Division, P.H.E. Dte. in the dist. of Purba Medinipur. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/000130/2024-2025 | 702/HESD | 19/07/2024 | 03/03/2025 | SOUMEN ELECTRIC | 2.2 | 0 | 0 | 70
Total | [13 empty] | 21723.9 | 66.26 | 0.31