## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Contai-I | Midnapore Mechanical | NAYAPUT AND IT'S ADJOINING MOUJAS PWSS | SM/12517 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for NAYAPUT and ADJOINING MOUJAS, Block - Contai I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division | ORD/001651/2022-2023 | 523/W/MMD | 20/03/2023 | 16/09/2023 | S.G.TECHNICAL SERVICE | 23.69 | 16.85 | 71.14 | 55
2 | PURBA MEDINIPUR | Contai-I | Tamluk Division | NAYAPUT AND IT'S ADJOINING MOUJAS PWSS | SM/12517 | New | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Head work site pipe connection, Rigid Pavement , Pump House & Boundry wall, Providing Functional Household Tap Connection (3145 Nos), including 2 years Operation & Maintenance For 4 nos Pipe Water Supply Scheme within Deshpran, Contai I &Contai III Block Under Tamluk Division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000496/2023-2024 | 1674/TD | 25/07/2023 | 09/07/2026 | HALDIA DEVELOPMENT CONSTRUCTION | 1173.36 | 219.1 | 18.67 | 30
3 | PURBA MEDINIPUR | Contai-I | Tamluk Division | NAYAPUT AND IT'S ADJOINING MOUJAS PWSS | SM/12517 | New | Material Requisition To Resource Division |  |  | RTOR000248/2022-2023 | 2718/TD | 06/02/2023 | 06/02/2023 | Resource Division | 38.35 | 0 | 0 | 0
4 | PURBA MEDINIPUR | Contai-I | Midnapore Mechanical | NAYAPUT AND IT'S ADJOINING MOUJAS PWSS | SM/12517 | New | Nayaput W/S scheme PH-I Application no.-2004522692 ref.-204156883 |  |  | BILL/03199/2023-2024 | BP-2023-24-473 | 27/12/2023 | 27/12/2023 | WBSEDCL | 4.81 | 0 | 0 | 0
5 | PURBA MEDINIPUR | Contai-I | Midnapore Mechanical | NAYAPUT AND IT'S ADJOINING MOUJAS PWSS | SM/12517 | New | Nayaput W/S scheme PH-II Application no.-2004522675 ref.-204156884 |  |  | BILL/03201/2023-2024 | BP-2023-24-474 | 27/12/2023 | 27/12/2023 | WBSEDCL | 4.44 | 0 | 0 | 0
6 | PURBA MEDINIPUR | Contai-I | Tamluk Division | NAYAPUT AND IT'S ADJOINING MOUJAS PWSS | SM/12517 | New | Material Requisition To Resource Division |  |  | RTOR000083/2024-2025 | 2969/TD | 12/09/2024 | 12/09/2024 | Resource Division | 12.36 | 0 | 0 | 0
7 | PURBA MEDINIPUR | Contai-I | Tamluk Division | NAYAPUT AND IT'S ADJOINING MOUJAS PWSS | SM/12517 | New | Restoration of damaged road work under WBSRDA, Purba Medinipur after laying of pipe line by PHE for different Piped Water Supply Scheme under Tamluk Division, PHE Dte. |  |  | BILL/01161/2024-2025 | BP-2024-25-607 | 30/10/2024 | 30/10/2024 | EXE-OFFICER, WBSRDA PURBA MEDINIPUR | 60.85 | 0 | 0 | 0
Total | [13 empty] | 1317.88 | 235.96 | 17.9