## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Potashpur-I | Tamluk Division | SELMABAD AND ADJOINING MOUJAS PWSS | SM/12518 | New | Material Requisition To Resource Division |  |  | RTOR000141/2022-2023 | 2443/TD | 16/01/2023 | 16/01/2023 | Resource Division | 14.54 | 0 | 0 | 0
2 | PURBA MEDINIPUR | Potashpur-I | Midnapore Mechanical | SELMABAD AND ADJOINING MOUJAS PWSS | SM/12518 | New | Quotation Bill for New Service connection at T/W NO-I Of SELMABAD W/S Scheme under MMD, PHE, Dte. Block- POTASHPUR-I, WBSEDCL SUPPLY OFFICE: AMARSHI C.C.C. Ref. Memo No-20048335913/QUOT/03 DT. 26-07-2024 Application NO- 20048335913 MEMO NO: AMR/PHE/282 DT.26/7/2024 Application type-New connection Consumer Id- 204365755 |  |  | BILL/01857/2024-2025 | BP-2024-25-539 | 07/08/2024 | 07/08/2024 | WBSEDCL | 4.45 | 0 | 0 | 0
3 | PURBA MEDINIPUR | Potashpur-I | Midnapore Mechanical | SELMABAD AND ADJOINING MOUJAS PWSS | SM/12518 | New | Quotation Bill for New Service connection at T/W NO-II Of SELMABAD W/S Scheme under MMD, PHE, Dte. Block- POTASHPUR-I, WBSEDCL SUPPLY OFFICE: AMARSHI C.C.C. Ref. Memo No-2004835826/QUOT/03 DT. 26-07-2024 Application NO- 2004835826 MEMO NO: AMR/PHE/288 DT.26/7/2024 Application type-New connection Consumer Id- 204365757 |  |  | BILL/01863/2024-2025 | BP-2024-25-538 | 07/08/2024 | 07/08/2024 | WBSEDCL | 4.24 | 0 | 0 | 0
4 | PURBA MEDINIPUR | Potashpur-I | Midnapore Mechanical | SELMABAD AND ADJOINING MOUJAS PWSS | SM/12518 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for SELMABAD and ADJOINING MOUJAS, Block - Potashpur I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001650/2022-2023 | 522/W/MMD | 20/03/2023 | 27/10/2026 | S.S.ENTERPRISES | 23.7 | 2.91 | 12.3 | 51
5 | PURBA MEDINIPUR | Potashpur-I | Tamluk Division | SELMABAD AND ADJOINING MOUJAS PWSS | SM/12518 | New | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House & Providing Functional Household Tap Connection (61964 Nos) For 38 nos Pipe water supply Scheme including two years Operation & Maintainance within Patashpur-I, Patashpur-II , Egra-I and Deshapran Block Under Tamluk Division PHE Dte. Under Purba Medinipur District. | Assistant Engineer,Assistant Engineer, Headquaters | Junior Engineer | ORD/000677/2023-2024 | 2702/TD | 20/10/2023 | 30/03/2026 | MACKINTOSH BURN LIMITED | 19507.71 | 143.9 | 0.74 | 51
Total | [13 empty] | 19554.63 | 146.81 | 0.75