## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Potashpur-I | Tamluk Division | SELMABAD AND ADJOINING MOUJAS PWSS | SM/12518 | New | Material Requisition To Resource Division |  |  | RTOR000141/2022-2023 | 2443/TD | 16/01/2023 | 16/01/2023 | Resource Division | 14.54 | 0 | 0 | 0
2 | PURBA MEDINIPUR | Potashpur-I | Midnapore Mechanical | SELMABAD AND ADJOINING MOUJAS PWSS | SM/12518 | New | Quotation Bill for New Service connection at T/W NO-I Of SELMABAD W/S Scheme under MMD, PHE, Dte. Block- POTASHPUR-I, WBSEDCL SUPPLY OFFICE: AMARSHI C.C.C. Ref. Memo No-20048335913/QUOT/03 DT. 26-07-2024 Application NO- 20048335913 MEMO NO: AMR/PHE/282 DT.26/7/2024 Application type-New connection Consumer Id- 204365755 |  |  | BILL/01857/2024-2025 | BP-2024-25-539 | 07/08/2024 | 07/08/2024 | WBSEDCL | 4.45 | 0 | 0 | 0
3 | PURBA MEDINIPUR | Potashpur-I | Midnapore Mechanical | SELMABAD AND ADJOINING MOUJAS PWSS | SM/12518 | New | Quotation Bill for New Service connection at T/W NO-II Of SELMABAD W/S Scheme under MMD, PHE, Dte. Block- POTASHPUR-I, WBSEDCL SUPPLY OFFICE: AMARSHI C.C.C. Ref. Memo No-2004835826/QUOT/03 DT. 26-07-2024 Application NO- 2004835826 MEMO NO: AMR/PHE/288 DT.26/7/2024 Application type-New connection Consumer Id- 204365757 |  |  | BILL/01863/2024-2025 | BP-2024-25-538 | 07/08/2024 | 07/08/2024 | WBSEDCL | 4.24 | 0 | 0 | 0
4 | PURBA MEDINIPUR | Potashpur-I | Midnapore Mechanical | SELMABAD AND ADJOINING MOUJAS PWSS | SM/12518 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for SELMABAD and ADJOINING MOUJAS, Block - Potashpur I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001650/2022-2023 | 522/W/MMD | 20/03/2023 | 27/10/2026 | S.S.ENTERPRISES | 23.7 | 0 | 0 | 51
5 | PURBA MEDINIPUR | Potashpur-I | Tamluk Division | SELMABAD AND ADJOINING MOUJAS PWSS | SM/12518 | New | Preparation of design based on soil test report and submission of drawing of foundation for construction of 350 cum RCC OHR at Selmabad PWSS at Patashpur-I Block under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000451/2024-2025 | 3480/TD | 06/11/2024 | 16/11/2024 | ASTER CONSULTANCY | 0.95 | 0 | 0 | 100
Total | [13 empty] | 47.88 | 0 | 0