## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Moyna | Tamluk Division | KIARANA AND ADJOINING MOUJAS PWSS | SM/12628 | New | Material Requisition To Resource Division |  |  | RTOR000178/2022-2023 | 2433/TD | 16/01/2023 | 16/01/2023 | Resource Division | 36.03 | 0 | 0 | 0
2 | PURBA MEDINIPUR | Moyna | Tamluk Division | KIARANA AND ADJOINING MOUJAS PWSS | SM/12628 | New | Preparation of design based on soil test report and submission of drawing of foundation for construction of 350 cum RCC OHR at Kiarana PWSS at Moyna Block under Tamluk Division,PHE Dte. | Assistant Engineer | Junior Engiener | ORD/000870/2023-2024 | 192/TD | 10/01/2024 | 20/01/2024 | ASTER CONSULTANCY | 0.95 | 0.95 | 100 | 100
3 | PURBA MEDINIPUR | Moyna | Tamluk Division | KIARANA AND ADJOINING MOUJAS PWSS | SM/12628 | New | Material Requisition To Resource Division |  |  | RTOR000009/2024-2025 | 1567/TD | 23/04/2024 | 23/04/2024 | Resource Division | 8.77 | 0 | 0 | 0
4 | PURBA MEDINIPUR | Moyna | Midnapore Mechanical | KIARANA AND ADJOINING MOUJAS PWSS | SM/12628 | New | Quotation for new service connection at Kiarana w/s scheme PH II in the district of Purba Medinipur under MMD PHE Dte. ( App ID 2004686357, Con ID 204277586) |  |  | BILL/00645/2024-2025 | BP-2024-25-110 | 06/05/2024 | 06/05/2024 | WBSEDCL | 13.89 | 0 | 0 | 0
5 | PURBA MEDINIPUR | Moyna | Midnapore Mechanical | KIARANA AND ADJOINING MOUJAS PWSS | SM/12628 | New | Quotation for Kiarana w/s scheme PH I in the district of Purba Medinipur under MMD PHE Dte.(App No.- 2004620100, Ref ID 204229479) |  |  | BILL/04503/2023-2024 | BP-2023-24-860 | 16/03/2024 | 16/03/2024 | WBSEDCL | 4.37 | 0 | 0 | 0
6 | PURBA MEDINIPUR | Moyna | Midnapore Mechanical | KIARANA AND ADJOINING MOUJAS PWSS | SM/12628 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for KIARANA and ADJOINING MOUJAS, Block ¿ Moyna, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/001415/2022-2023 | 2426/W/MMD | 31/12/2022 | 31/10/2024 | DEY ENTERPRISE | 23.7 | 19.45 | 82.08 | 100
7 | PURBA MEDINIPUR | Moyna | Tamluk Division | KIARANA AND ADJOINING MOUJAS PWSS | SM/12628 | New | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House & Providing Functional Household Tap Connection (32862 Nos), including 2 years Operation & Maintenance For 21 nos Pipe Water Supply Scheme within MOYNA AND CONTAI -I Block Under Tamluk Division PHE Dte. Under Purba Medinipur District. | Assistant Engineer | Junior Engiener,Junior Engineer | ORD/000538/2023-2024 | 1937/TD | 16/08/2023 | 28/03/2026 | MACKINTOSH BURN LIMITED | 10310.59 | 385.99 | 3.74 | 75
Total | [13 empty] | 10398.31 | 406.39 | 3.91