## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Egra-I | Tamluk Division | AMDAI AND ADJOINING MOUJAS PWSS at Egra-I Block. | SM/12634 | New | Material Requisition To Resource Division |  |  | RTOR000158/2022-2023 | 2421/TD | 16/01/2023 | 16/01/2023 | Resource Division | 16.01 | 0 | 0 | 0
2 | PURBA MEDINIPUR | Egra-I | Tamluk Division | AMDAI AND ADJOINING MOUJAS PWSS at Egra-I Block. | SM/12634 | New | Preparation of design based on soil test report and submission of drawing of foundation for construction of 250 cum RCC OHR at Amdai PWSS at Egra-I Block under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000172/2024-2025 | 2084/TD | 24/06/2024 | 04/07/2024 | ASTER CONSULTANCY | 0.95 | 0.95 | 100 | 100
3 | PURBA MEDINIPUR | Egra-I | Midnapore Mechanical | AMDAI AND ADJOINING MOUJAS PWSS at Egra-I Block. | SM/12634 | New | Quotation for new service connection at TW-1 of Amdai w/s scheme under MMD,PHE DTE, Block-Egra-1,Chorpalia CCC,Application no-2004635540.Con ID-204242882 |  |  | BILL/04574/2023-2024 | BP-2023-24-886 | 22/03/2024 | 22/03/2024 | WBSEDCL | 5.55 | 0 | 0 | 0
4 | PURBA MEDINIPUR | Egra-I | Midnapore Mechanical | AMDAI AND ADJOINING MOUJAS PWSS at Egra-I Block. | SM/12634 | New | Quotation for new service connection at TW-II of AMDAI WS Scheme under MMD,PHE DTE, Block-Egra-1,Chorpalia ccc . Application no-2004635643. CON ID-204240383. |  |  | BILL/04576/2023-2024 | BP-2023-24-887 | 22/03/2024 | 22/03/2024 | WBSEDCL | 4.92 | 0 | 0 | 0
5 | PURBA MEDINIPUR | Egra-I | Midnapore Mechanical | AMDAI AND ADJOINING MOUJAS PWSS at Egra-I Block. | SM/12634 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for AMDAI and ADJOINING MOUJAS, Block ¿ Egra I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division | ORD/001405/2022-2023 | 2416/W/MMD | 31/12/2022 | 31/05/2025 | RITESH ENTERPRISE | 22.81 | 0 | 0 | 80
Total | [13 empty] | 50.24 | 0.95 | 1.9