## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Potashpur-I | Tamluk Division | BARA BHAGIA AND ADJOINING MOUJAS PWSS | SM/12704 | New | Material Requisition To Resource Division |  |  | RTOR000199/2022-2023 | 2444/TD | 16/01/2023 | 16/01/2023 | Resource Division | 33.17 | 0 | 0 | 0
2 | PURBA MEDINIPUR | Potashpur-I | Midnapore Mechanical | BARA BHAGIA AND ADJOINING MOUJAS PWSS | SM/12704 | New | Quotation Bill for New Service connection at T/W NO-I Of BARA BHAGIA W/S Scheme under MMD, PHE, Dte. Block- PATASHPUR-I, WBSEDCL SUPPLY OFFICE: AMARSHI C.C.C. Ref. Memo No- 2004870409/QUOT/03 DT. 23-08-2024 MEMO NO: AMR/PHE/338 DT. 23-08-2024 Application NO- 2004870409 Application type-New connection Consumer Id- 204383603 |  |  | BILL/02398/2024-2025 | BP-2024-25-648 | 06/09/2024 | 06/09/2024 | WBSEDCL | 5.91 | 0 | 0 | 0
3 | PURBA MEDINIPUR | Potashpur-I | Midnapore Mechanical | BARA BHAGIA AND ADJOINING MOUJAS PWSS | SM/12704 | New | Quotation Bill for New Service connection at T/W NO-II Of BARA BHAGIA W/S Scheme under MMD, PHE, Dte. Block- PATASHPUR-I, WBSEDCL SUPPLY OFFICE: AMARSHI C.C.C. Ref. Memo No- 2004878231/QUOT/03 DT. 30-08-2024 MEMO NO: AMR/PHE/351 DT. 30-08-2024 Application NO- 2004878231 Application type-New connection Consumer Id- 204387577 |  |  | BILL/02453/2024-2025 | C102415714404 | 05/10/2024 | 05/10/2024 | WBSEDCL | 3.05 | 0 | 0 | 0
4 | PURBA MEDINIPUR | Potashpur-I | Midnapore Mechanical | BARA BHAGIA AND ADJOINING MOUJAS PWSS | SM/12704 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for BARA BHAGIA and ADJOINING MOUJAS, Block - Potashpur I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001626/2022-2023 | 511/W/MMD | 20/03/2023 | 30/09/2025 | GLACIER ENGINEERING CO. | 22.8 | 16.26 | 71.29 | 60
Total | [13 empty] | 64.93 | 16.26 | 25.04