## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Potashpur-I | Tamluk Division | BELDA AND IT'S ADJOINING MOUJAS PWSS | SM/12710 | New | Material Requisition To Resource Division |  |  | RTOR000144/2022-2023 | 2447/TD | 16/01/2023 | 16/01/2023 | Resource Division | 22.75 | 0 | 0 | 0
2 | PURBA MEDINIPUR | Potashpur-I | Midnapore Mechanical | BELDA AND IT'S ADJOINING MOUJAS PWSS | SM/12710 | New | Quotation Bill for New Service connection at T/W NO-I Of BELDA W/S Scheme under MMD, PHE, Dte. Block- POTASHPUR-I, AMARSI C.C.C. Ref. Memo No- 2004607449/QUOT/03 DT. 21-02-2024 Application NO- 2004607449 Application type-New connection Consumer Id- 204223207 |  |  | BILL/04386/2023-2024 | BP-2023-24-824 | 13/03/2024 | 13/03/2024 | WBSEDCL | 3.03 | 0 | 0 | 0
3 | PURBA MEDINIPUR | Potashpur-I | Midnapore Mechanical | BELDA AND IT'S ADJOINING MOUJAS PWSS | SM/12710 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for BELDA and ADJOINING MOUJAS, Block ¿ Potashpur I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001349/2022-2023 | 2360/W/MMD | 31/12/2022 | 30/06/2025 | WEST BENGAL ENGINEERING CO. | 23.67 | 0 | 0 | 50
4 | PURBA MEDINIPUR | Potashpur-I | Tamluk Division | BELDA AND IT'S ADJOINING MOUJAS PWSS | SM/12710 | New | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House & Providing Functional Household Tap Connection (61964 Nos) For 38 nos Pipe water supply Scheme including two years Operation & Maintainance within Patashpur-I, Patashpur-II , Egra-I and Deshapran Block Under Tamluk Division PHE Dte. Under Purba Medinipur District. | Assistant Engineer,Assistant Engineer, Headquaters | Junior Engineer | ORD/000677/2023-2024 | 2702/TD | 20/10/2023 | 01/10/2025 | MACKINTOSH BURN LIMITED | 19507.71 | 193.47 | 0.99 | 51
Total | [13 empty] | 19557.17 | 193.47 | 0.99