## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Potashpur-II | Midnapore Mechanical | GABARDHANPUR AND IT'S ADJOINING MOUJAS PWSS | SM/12774 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for GABARDHANPUR and ADJOINING MOUJAS, Block - Potashpur II, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Sukanta Mondal, JE/Haldia Electrical Sub-Division. | ORD/001639/2022-2023 | 519/W/MMD | 20/03/2023 | 16/09/2023 | RMD TRADING | 22.76 | 0 | 0 | 0
2 | PURBA MEDINIPUR | Potashpur-II | Tamluk Division | GABARDHANPUR AND IT'S ADJOINING MOUJAS PWSS | SM/12774 | New | Material Requisition To Resource Division |  |  | RTOR000185/2022-2023 | 2455/TD | 16/01/2023 | 16/01/2023 | Resource Division | 15.86 | 0 | 0 | 0
3 | PURBA MEDINIPUR | Potashpur-II | Tamluk Division | GABARDHANPUR AND IT'S ADJOINING MOUJAS PWSS | SM/12774 | New | Preparation of design based on soil test report and submission of drawing of foundation for construction of 250 cum RCC OHR at Gabardhanpur PWSS at Pataspur-II Block under Tamluk Division, PHE Dte. | Assistant Engineer, Headquaters |  | ORD/000191/2024-2025 | 2201/TD | 09/07/2024 | 19/07/2024 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.95 | 0.95 | 100 | 100
4 | PURBA MEDINIPUR | Potashpur-II | Tamluk Division | GABARDHANPUR AND IT'S ADJOINING MOUJAS PWSS | SM/12774 | New | Material Requisition To Resource Division |  |  | RTOR000044/2024-2025 | 1650/TD | 29/04/2024 | 29/04/2024 | Resource Division | 10.35 | 0 | 0 | 0
5 | PURBA MEDINIPUR | Potashpur-II | Midnapore Mechanical | GABARDHANPUR AND IT'S ADJOINING MOUJAS PWSS | SM/12774 | New | Quotation Bill for New Service connection at T/W NO-I Of Gabardhanpur W/S Scheme under MMD, PHE, Dte. Block- PATASHPUR-II, PATASHPUR C.C.C. Ref. Memo No- 2004595896/QUOT/03 DT. 12-03-2024 Application NO- 2004595896 Application type-New connection CONSUMER ID: 204213657 |  |  | BILL/04738/2023-2024 | BP-2023-24-921 | 28/03/2024 | 28/03/2024 | WBSEDCL | 3.29 | 0 | 0 | 0
6 | PURBA MEDINIPUR | Potashpur-II | Midnapore Mechanical | GABARDHANPUR AND IT'S ADJOINING MOUJAS PWSS | SM/12774 | New | Quotation Bill for New Service connection at T/W NO-II Of GOBARDHANPUR W/S Scheme under MMD, PHE, Dte. Block- POTASHPUR-II, WBSEDCL SUPPLY OFFICE: PATASPUR C.C.C. Ref. Memo No- 2004595917/QUOT/03 DT. 12-02-2024 Application NO- 2004595917 Application type-New connection Consumer Id- 204213656 |  |  | BILL/01134/2024-2025 | BP-2024-25-250 | 06/06/2024 | 06/06/2024 | WBSEDCL | 3.79 | 0 | 0 | 0
7 | PURBA MEDINIPUR | Potashpur-II | Tamluk Division | GABARDHANPUR AND IT'S ADJOINING MOUJAS PWSS | SM/12774 | New | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House & Providing Functional Household Tap Connection (61964 Nos) For 38 nos Pipe water supply Scheme including two years Operation & Maintainance within Patashpur-I, Patashpur-II , Egra-I and Deshapran Block Under Tamluk Division PHE Dte. Under Purba Medinipur District. | Assistant Engineer,Assistant Engineer, Headquaters | Junior Engineer | ORD/000677/2023-2024 | 2702/TD | 20/10/2023 | 01/10/2025 | MACKINTOSH BURN LIMITED | 19507.71 | 126.18 | 0.65 | 51
Total | [13 empty] | 19564.71 | 127.13 | 0.65