## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Sahid Matangini | Midnapore Mechanical | SOYA DIGHI AND IT'S ADJOINING MOUJAS | SM/12809 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for SOYA DIGHI and ADJOINING MOUJAS, Block - Shahid Matangini, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Raju Pramanik, JE/Haldia Electrical Sub-Division. | ORD/002035/2022-2023 | 943/W/MMD | 28/03/2023 | 24/09/2023 | ORIENTAL ENGINEERING CO. | 22.79 | 0 | 0 | 0
2 | PURBA MEDINIPUR | Sahid Matangini | Tamluk Division | SOYA DIGHI AND IT'S ADJOINING MOUJAS | SM/12809 | New | Material Requisition To Resource Division |  |  | RTOR000257/2022-2023 | 2680/TD | 06/02/2023 | 06/02/2023 | Resource Division | 20.04 | 0 | 0 | 0
3 | PURBA MEDINIPUR | Sahid Matangini | Tamluk Division | SOYA DIGHI AND IT'S ADJOINING MOUJAS | SM/12809 | New | Material Requisition To Resource Division |  |  | RTOR000172/2023-2024 | 110/TD | 05/01/2024 | 05/01/2024 | Resource Division | 11.79 | 0 | 0 | 0
4 | PURBA MEDINIPUR | Sahid Matangini | Midnapore Mechanical | SOYA DIGHI AND IT'S ADJOINING MOUJAS | SM/12809 | New | Quatation bill for Swadighi H/W Site W/S SCHEME under MMD,PHE,Dte. BLOCK- Sahid Matangini WBSEDCL SUPPLY OFFICE: Matangini C.C.C Ref. Memo No- 2004992438/Quot/03/1203 DT. 05-12-2024 APPLICATION NO: 2004992438 Consumer Id- 204463808 |  |  | BILL/03680/2024-2025 |  | 18/12/2024 | 18/12/2024 | WBSEDCL | 8.06 | 0 | 0 | 0
5 | PURBA MEDINIPUR | Sahid Matangini | Tamluk Division | SOYA DIGHI AND IT'S ADJOINING MOUJAS | SM/12809 | New | Sinking of Tube Well ,Construction of Pump House ,250 cum OHR (Intze type with pile foundation), Rising main, Laying distribution pipe line, Boundary Wall, Soil investigation & Accommodate FHTC (1914 nos) under JJM with allied work including 02(two) Years Operation & Maintenance of SOYA DIGHI PWSS within Sahid Matangini Block under Tamluk Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000205/2023-2024 | 412/TD | 02/05/2023 | 31/07/2025 | JAYANTA KUMAR MONDAL | 418.27 | 0 | 0 | 40
Total | [13 empty] | 480.96 | 0 | 0