## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Moyna | Midnapore Mechanical | GOJINA AND IT'S ADJOINING MOUJAS PWSS | SM/12812 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for GOJINA and ADJOINING MOUJAS, Block - Moyna, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/001654/2022-2023 | 526/W/MMD | 20/03/2023 | 16/09/2023 | BHABANI PRASAD MANNA | 23.7 | 5.65 | 23.85 | 60
2 | PURBA MEDINIPUR | Moyna | Tamluk Division | GOJINA AND IT'S ADJOINING MOUJAS PWSS | SM/12812 | New | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House & Providing Functional Household Tap Connection (32862 Nos), including 2 years Operation & Maintenance For 21 nos Pipe Water Supply Scheme within MOYNA AND CONTAI -I Block Under Tamluk Division PHE Dte. Under Purba Medinipur District. | Assistant Engineer | Junior Engiener,Junior Engineer | ORD/000538/2023-2024 | 1937/TD | 16/08/2023 | 28/03/2026 | MACKINTOSH BURN LIMITED | 10310.59 | 355.87 | 3.45 | 75
3 | PURBA MEDINIPUR | Moyna | Tamluk Division | GOJINA AND IT'S ADJOINING MOUJAS PWSS | SM/12812 | New | Material Requisition To Resource Division |  |  | RTOR000174/2022-2023 | 2435/TD | 16/01/2023 | 16/01/2023 | Resource Division | 46.71 | 0 | 0 | 0
4 | PURBA MEDINIPUR | Moyna | Tamluk Division | GOJINA AND IT'S ADJOINING MOUJAS PWSS | SM/12812 | New | Preparation of design based on soil test report and submission of drawing of foundation for construction of 300 cum RCC OHR at Gojina PWSS at Moyna Block under Tamluk Division,PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000878/2023-2024 | 200/TD | 10/01/2024 | 20/01/2024 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.95 | 0.95 | 100 | 100
5 | PURBA MEDINIPUR | Moyna | Tamluk Division | GOJINA AND IT'S ADJOINING MOUJAS PWSS | SM/12812 | New | Material Requisition To Resource Division |  |  | RTOR000006/2024-2025 | 1564/TD | 23/04/2024 | 23/04/2024 | Resource Division | 15.01 | 0 | 0 | 0
6 | PURBA MEDINIPUR | Moyna | Midnapore Mechanical | GOJINA AND IT'S ADJOINING MOUJAS PWSS | SM/12812 | New | Quotation for Gojina w/s scheme PH-II in the district of Purba Medinipur under MMD PHE dte.(Application No.-2004619845, Ref ID-204229480) |  |  | BILL/04499/2023-2024 | BP-2023-24-862 | 16/03/2024 | 16/03/2024 | WBSEDCL | 5.65 | 0 | 0 | 0
7 | PURBA MEDINIPUR | Moyna | Midnapore Mechanical | GOJINA AND IT'S ADJOINING MOUJAS PWSS | SM/12812 | New | Quotation for Gojina w/s scheme PH-I in the district of Purba Medinipur under MMD PHE dte.(Application No.-2004619919, Ref ID-204229478) |  |  | BILL/04500/2023-2024 | BP-2023-24-861 | 16/03/2024 | 16/03/2024 | WBSEDCL | 2.78 | 0 | 0 | 0
8 | PURBA MEDINIPUR | Moyna | Tamluk Division | GOJINA AND IT'S ADJOINING MOUJAS PWSS | SM/12812 | New | Continuation for Hiring of Diesel Motor Cab / Luxury Taxi (Commercial) with catalytic converter attachment (Bharat Stage-IV) on daily basis for the period from 01.07.2025 to 31.12.2025 i.e. 06 (Six) months for the use of the Office of the Assistant Engineer, RWS Tamluk Sub-Division, under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000423/2025-2026 | 169/RWS/TSD | 26/06/2025 | 27/12/2025 | SADHAN CHANDRA SAMANTA | 0.87 | 0 | 0 | 50
Total | [13 empty] | 10406.27 | 362.47 | 3.48