## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Khejuri-I | Tamluk Division | JAHANABAD AND IT'S ADJOINING MOUJAS | SM/12813 | New | Material Requisition To Resource Division |  |  | RTOR000230/2022-2023 | 2709/TD | 06/02/2023 | 06/02/2023 | Resource Division | 14.75 | 0 | 0 | 0
2 | PURBA MEDINIPUR | Khejuri-I | Central Drilling | JAHANABAD AND IT'S ADJOINING MOUJAS | SM/12813 | New | Providing drilling crew and other allied works for construction of Tube Well (250mm X150mm X 280 Mtrs. Depth) by utilising Departmental Machineries for Jahanabad W/S Scheme (T/W-I), Khejuri-I Block under Purba Medinipur District, Central Drilling Division, P.H.E. Dte. | Driller In Charge | Junior Engineer | ORD/000101/2023-2024 | 851/CDD | 10/07/2023 | 05/05/2024 | UNIVERSAL ENTERPRISES | 15.71 | 0 | 0 | 100
3 | PURBA MEDINIPUR | Khejuri-I | Tamluk Division | JAHANABAD AND IT'S ADJOINING MOUJAS | SM/12813 | New | Material Requisition To Resource Division |  |  | RTOR000097/2024-2025 | 2959/TD | 12/09/2024 | 12/09/2024 | Resource Division | 14.85 | 0 | 0 | 0
4 | PURBA MEDINIPUR | Khejuri-I | Midnapore Mechanical | JAHANABAD AND IT'S ADJOINING MOUJAS | SM/12813 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for JAHANABAD and ADJOINING MOUJAS, Block - Khejuri I, District - Purba Medinipurunder JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/000089/2023-2024 | 1267/W/MMD | 04/05/2023 | 31/03/2025 | MENAKA ENTERPRISE | 25.14 | 0 | 0 | 0
5 | PURBA MEDINIPUR | Khejuri-I | Tamluk Division | JAHANABAD AND IT'S ADJOINING MOUJAS | SM/12813 | New | Sinking of Tube Well ,Head work site pipe connection,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system ,Rigid Pavement, Pump House &Boundary Wall, Providing Functional Household Tap Connection (5341Nos), including 2 years Operation & Maintenance For PATNA, Jahanabad, Pipe water supply Scheme within Khejuri-I Block Under Tamluk Division PHE Dte. Under Purba Medinipur District. | Assistant Engineer | Junior Engineer | ORD/000429/2023-2024 | 1413/TD | 12/07/2023 | 01/07/2025 | GEE BEE NIRMAN CO PVT LTD. | 1697.21 | 0 | 0 | 60
Total | [13 empty] | 1767.66 | 0 | 0