## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Egra-I | Tamluk Division | KIA AND IT'S ADJOINING MOUJAS | SM/12814 | New | Material Requisition To Resource Division |  |  | RTOR000128/2022-2023 | 2412/TD | 16/01/2023 | 16/01/2023 | Resource Division | 35.2 | 0 | 0 | 0
2 | PURBA MEDINIPUR | Egra-I | Midnapore Mechanical | KIA AND IT'S ADJOINING MOUJAS | SM/12814 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for KIA and ADJOINING MOUJAS, Block - Egra I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division | ORD/002034/2022-2023 | 942/W/MMD | 28/03/2023 | 06/03/2025 | ORIENTAL ENGINEERING CO. | 22.79 | 7.34 | 32.2 | 90
3 | PURBA MEDINIPUR | Egra-I | Tamluk Division | KIA AND IT'S ADJOINING MOUJAS | SM/12814 | New | Preparation of design based on soil test report and submission of drawing of foundation for construction of 300 cum RCC OHR at Kia PWSS at Egra-I Block under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000171/2024-2025 | 2083/TD | 24/06/2024 | 04/07/2024 | ASTER CONSULTANCY | 0.95 | 0.95 | 100 | 100
4 | PURBA MEDINIPUR | Egra-I | Midnapore Mechanical | KIA AND IT'S ADJOINING MOUJAS | SM/12814 | New | Quotation for new service connection at TW-1 of KIA ws scheme under MMD, PHE DTE, Block-Egra-1, under EGRA CCC. Application no-2004607227, CON ID-204221794. |  |  | BILL/04145/2023-2024 | BP-2023-24-758 | 01/03/2024 | 01/03/2024 | WBSEDCL | 4.72 | 0 | 0 | 0
5 | PURBA MEDINIPUR | Egra-I | Midnapore Mechanical | KIA AND IT'S ADJOINING MOUJAS | SM/12814 | New | Quotation Bill for New Service connection at T/W NO-II of KIA W/S Scheme under MMD, PHE, Dte. Block- Egra-I, Egra CCC Ref. Memo no- 2004607232/QUOT/03/3197 Dt. 20-Feb-2024 Application NO- 2004607232 Application type-New connection Reference Id- 204221796 |  |  | BILL/04144/2023-2024 | bp-2023-24-759 | 01/03/2024 | 01/03/2024 | WBSEDCL | 3.79 | 0 | 0 | 0
6 | PURBA MEDINIPUR | Egra-I | Tamluk Division | KIA AND IT'S ADJOINING MOUJAS | SM/12814 | New | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House & Providing Functional Household Tap Connection (61964 Nos) For 38 nos Pipe water supply Scheme including two years Operation & Maintainance within Patashpur-I, Patashpur-II , Egra-I and Deshapran Block Under Tamluk Division PHE Dte. Under Purba Medinipur District. | Assistant Engineer,Assistant Engineer, Headquaters | Junior Engineer | ORD/000677/2023-2024 | 2702/TD | 20/10/2023 | 01/10/2025 | MACKINTOSH BURN LIMITED | 19507.71 | 261.62 | 1.34 | 51
Total | [13 empty] | 19575.17 | 269.91 | 1.38