## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Khejuri-I | Central Drilling | KATARI AND ADJOINING MOUJAS PWSS | SM/12815 | New | Providing drliing crew and other allied works for construction of Tube Well (250 mm x 150mm x 280 Mtrs Depth) by utilising Departmental Machineries for katari W/S Scheme (T/W-III), khejuri-I Block under Purba Mednipur District, CDD PHE Dte. | Driller In Charge | Junior Engineer | ORD/000057/2023-2024 | 59/CDD | 06/04/2023 | 06/05/2023 | PADMA ENGINEERING & CO. | 15.48 | 12.9 | 83.36 | 100
2 | PURBA MEDINIPUR | Khejuri-I | Central Drilling | KATARI AND ADJOINING MOUJAS PWSS | SM/12815 | New | Provicjing drilling crew and other allied works for construction of Tube Well (250mm Xi50mm X 280 Mtrs. Depth) by utilising Departmental Machineries for Katari W/S Scheme (T/W-l) , Khejuri-l Block under Purba IVedinipur District, CentralDrilling Division, P.H.E. Dte. | Driller In Charge | Junior Engineer | ORD/000177/2023-2024 | 853/CDD | 10/07/2023 | 09/08/2023 | C.M. ENTERPRISE | 15.47 | 12.9 | 83.39 | 100
3 | PURBA MEDINIPUR | Khejuri-I | Tamluk Division | KATARI AND ADJOINING MOUJAS PWSS | SM/12815 | New | Material Requisition To Resource Division |  |  | RTOR000335/2022-2023 | 2980/TD | 27/02/2023 | 27/02/2023 | Resource Division | 17.68 | 0 | 0 | 0
4 | PURBA MEDINIPUR | Khejuri-I | Midnapore Mechanical | KATARI AND ADJOINING MOUJAS PWSS | SM/12815 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for KATARI and ADJOINING MOUJAS, Block - Khejuri I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/001612/2022-2023 | 505/W/MMD | 20/03/2023 | 16/09/2023 | AMIT DAS | 21.57 | 20.26 | 93.95 | 50
5 | PURBA MEDINIPUR | Khejuri-I | Tamluk Division | KATARI AND ADJOINING MOUJAS PWSS | SM/12815 | New | Material Requisition To Resource Division |  |  | RTOR000089/2024-2025 | 2965/TD | 12/09/2024 | 12/09/2024 | Resource Division | 4.72 | 0 | 0 | 0
6 | PURBA MEDINIPUR | Khejuri-I | Midnapore Mechanical | KATARI AND ADJOINING MOUJAS PWSS | SM/12815 | New | Katari W/S scheme PH.-I Application No.-2004565589 Ref No.-204193626 |  |  | BILL/03478/2023-2024 | BP-2023-24-590 | 02/02/2024 | 02/02/2024 | WBSEDCL | 5.84 | 0 | 0 | 0
7 | PURBA MEDINIPUR | Khejuri-I | Midnapore Mechanical | KATARI AND ADJOINING MOUJAS PWSS | SM/12815 | New | Katari W/S scheme PH.-II Application No.-2004565602 Ref No.-204193624 |  |  | BILL/03479/2023-2024 | BP-2023-24-591 | 02/02/2024 | 02/02/2024 | WBSEDCL | 5.2 | 0 | 0 | 0
8 | PURBA MEDINIPUR | Khejuri-I | Tamluk Division | KATARI AND ADJOINING MOUJAS PWSS | SM/12815 | New | Sinking of Tube well, Pump House , OHR (Intze type with pile foundation), Rising main, Head work site pipe connection, Laying distribution pipe line,Rigid Pavement, Boundary Wall, Soil investigation & Accommodate FHTC (2953 nos) Including 2 Years of Operation & Maintenance under JJM with allied work for Dakshin Kalamdan, Katari, and its adjoing Mouzas- PWSS in Khejuri-I Block within Contai Sub-Division under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000430/2023-2024 | 1417/TD | 12/07/2023 | 01/10/2025 | TAPAS SANTRA | 1109.38 | 124.19 | 11.19 | 75
9 | PURBA MEDINIPUR | Khejuri-I | Central Drilling | KATARI AND ADJOINING MOUJAS PWSS | SM/12815 | New | Hiring of diesel driven Motor Cab (BS-III & Above) having contract carriage permit along with driver for the office of The Executive Engineer, Central Drilling Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000059/2024-2025 | 11/S&WSD | 15/01/2025 | 31/07/2025 | SULEKHA PAUL | 0.94 | 1.9 | 203.55 | 0
Total | [13 empty] | 1196.29 | 172.16 | 14.39