## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Egra-I | Tamluk Division | PURANDA AND IT'S ADJOINING MOUJAS PWSS | SM/12818 | New | Material Requisition To Resource Division |  |  | RTOR000130/2022-2023 | 2414/TD | 16/01/2023 | 16/01/2023 | Resource Division | 25.18 | 0 | 0 | 0
2 | PURBA MEDINIPUR | Egra-I | Tamluk Division | PURANDA AND IT'S ADJOINING MOUJAS PWSS | SM/12818 | New | Preparation of design based on soil test report and submission of drawing of foundation for construction of 200 cum RCC OHR at Puronda PWSS at Egra-I Block under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000184/2024-2025 | 2194/TD | 09/07/2024 | 19/07/2024 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.95 | 0.95 | 100 | 100
3 | PURBA MEDINIPUR | Egra-I | Midnapore Mechanical | PURANDA AND IT'S ADJOINING MOUJAS PWSS | SM/12818 | New | Quotation Bill for New Service connection at T/W NO-II Of PURANDA W/S Scheme under MMD, PHE, Dte. Block- EGRA-I, WBSEDCL SUPPLY OFFICE: CHORPALIA C.C.C. Ref. Memo No- 2004674845/QUOT/03 DT. 09-04-2024 Application NO- 2004674845 Application type-New connection Consumer Id- 204269900 |  |  | BILL/00500/2024-2025 | BP-2024-25-83 | 24/04/2024 | 24/04/2024 | WBSEDCL | 3.69 | 0 | 0 | 0
4 | PURBA MEDINIPUR | Egra-I | Midnapore Mechanical | PURANDA AND IT'S ADJOINING MOUJAS PWSS | SM/12818 | New | Quotation Bill for New Service connection at T/W NO-I Of PURANDA W/S Scheme under MMD, PHE, Dte. Block- EGRA-I, WBSEDCL SUPPLY OFFICE: CHORPALIA C.C.C. Ref. Memo No- 2004674832/QUOT/03 DT. 09-04-2024 Application NO- 2004674832 Application type-New connection Consumer Id- 204269889 |  |  | BILL/00510/2024-2025 | BP-2024-25-82 | 24/04/2024 | 24/04/2024 | WBSEDCL | 6.05 | 0 | 0 | 0
5 | PURBA MEDINIPUR | Egra-I | Midnapore Mechanical | PURANDA AND IT'S ADJOINING MOUJAS PWSS | SM/12818 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for PURANDA and ADJOINING MOUJAS, Block - Egra I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division | ORD/001627/2022-2023 | 512/W/MMD | 20/03/2023 | 30/09/2025 | GLACIER ENGINEERING CO. | 22.8 | 16.25 | 71.25 | 100
Total | [13 empty] | 58.67 | 17.2 | 29.32