## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Deshopran | Midnapore Mechanical | DURMUT AND ADJOINING MOUJAS PWSS | SM/12820 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for DURMUT AND ADJOINING MOUJAS PWSS, Block Deshopran, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division | ORD/001913/2022-2023 | 815/W/MMD | 24/03/2023 | 20/09/2023 | TAPAN KUMAR DEY | 22.78 | 9.45 | 41.47 | 35
2 | PURBA MEDINIPUR | Deshopran | Tamluk Division | DURMUT AND ADJOINING MOUJAS PWSS | SM/12820 | New | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House & Providing Functional Household Tap Connection (61964 Nos) For 38 nos Pipe water supply Scheme including two years Operation & Maintainance within Patashpur-I, Patashpur-II , Egra-I and Deshapran Block Under Tamluk Division PHE Dte. Under Purba Medinipur District. | Assistant Engineer,Assistant Engineer, Headquaters | Junior Engineer | ORD/000677/2023-2024 | 2702/TD | 20/10/2023 | 30/03/2026 | MACKINTOSH BURN LIMITED | 19507.71 | 0 | 0 | 51
3 | PURBA MEDINIPUR | Deshopran | Tamluk Division | DURMUT AND ADJOINING MOUJAS PWSS | SM/12820 | New | Material Requisition To Resource Division |  |  | RTOR000121/2022-2023 | 2401/TD | 16/01/2023 | 16/01/2023 | Resource Division | 41.93 | 0 | 0 | 0
4 | PURBA MEDINIPUR | Deshopran | Tamluk Division | DURMUT AND ADJOINING MOUJAS PWSS | SM/12820 | New | Material Requisition To Resource Division |  |  | RTOR000092/2024-2025 | 2957/TD | 12/09/2024 | 12/09/2024 | Resource Division | 10.46 | 0 | 0 | 0
5 | PURBA MEDINIPUR | Deshopran | Tamluk Division | DURMUT AND ADJOINING MOUJAS PWSS | SM/12820 | New | Restoration of damaged road work under WBSRDA, Purba Medinipur after laying of pipe line by PHE for different Piped Water Supply Scheme under Tamluk Division, PHE Dte. |  |  | BILL/01161/2024-2025 | BP-2024-25-607 | 30/10/2024 | 30/10/2024 | EXE-OFFICER, WBSRDA PURBA MEDINIPUR | 60.85 | 0 | 0 | 0
Total | [13 empty] | 19643.72 | 9.45 | 0.05