## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Khejuri-I,Khejuri-II | Tamluk Division | HALUD BARI AND ADJOINING MOUJAS | SM/12821 | New | Material Requisition To Resource Division |  |  | RTOR000228/2022-2023 | 2708/TD | 06/02/2023 | 06/02/2023 | Resource Division | 20.18 | 0 | 0 | 0
2 | PURBA MEDINIPUR | Khejuri-I,Khejuri-II | Midnapore Mechanical | HALUD BARI AND ADJOINING MOUJAS | SM/12821 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for HALUD BARI and ADJOINING MOUJAS, Block - Khejuri II, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Krishanu Mondal, JE/Haldia Electrical Sub-Division. | ORD/001652/2022-2023 | 524/W/MMD | 20/03/2023 | 16/09/2023 | BHABANI PRASAD MANNA | 23.7 | 15.86 | 66.91 | 48
3 | PURBA MEDINIPUR | Khejuri-I,Khejuri-II | Midnapore Mechanical | HALUD BARI AND ADJOINING MOUJAS | SM/12821 | New | Quotation Bill for Haludbari Water Supply scheme Tube well no.-I Khejuri CCC Block-Khejuri Application No.-2004645013 Ref ID.-204247115 Quatation Bill Date.-14/03/2024 |  |  | BILL/04572/2023-2024 | BP-2023-24-888 | 22/03/2024 | 22/03/2024 | WBSEDCL | 4.93 | 0 | 0 | 0
4 | PURBA MEDINIPUR | Khejuri-I,Khejuri-II | Tamluk Division | HALUD BARI AND ADJOINING MOUJAS | SM/12821 | New | Payment of WBSEDCL for Quotation of Shifting of LTOH line at Haludbari Water Supply Scheme for Construction of New OHR. |  |  | BILL/01889/2023-2024 | BP-2023-24-844 | 07/02/2024 | 07/02/2024 | WBSEDCL | 1.52 | 0 | 0 | 0
5 | PURBA MEDINIPUR | Khejuri-I,Khejuri-II | Midnapore Mechanical | HALUD BARI AND ADJOINING MOUJAS | SM/12821 | New | Quotation for new service connection at Haludbari w/s scheme PH II in the district of Purba Medinipur under MMD PHE Dte.(App No. 2004785778, Ref ID 204336496) |  |  | BILL/01365/2024-2025 | BP-2024-25-377 | 08/07/2024 | 08/07/2024 | WBSEDCL | 4.71 | 0 | 0 | 0
Total | [13 empty] | 55.04 | 15.86 | 28.81