## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Contai-I | Midnapore Mechanical | SYAMRAIBAR AND IT'S ADJOINING MOUJAS PWSS | SM/12886 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for SYAMRAIBAR and ADJOINING MOUJAS, Block ¿ Contai I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division | ORD/001399/2022-2023 | 2410/W/MMD | 31/12/2022 | 29/06/2023 | SUJOY RANJAN BHOWMICK | 21.62 | 7.35 | 34.02 | 35
2 | PURBA MEDINIPUR | Contai-I | Tamluk Division | SYAMRAIBAR AND IT'S ADJOINING MOUJAS PWSS | SM/12886 | New | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House & Providing Functional Household Tap Connection (32862 Nos), including 2 years Operation & Maintenance For 21 nos Pipe Water Supply Scheme within MOYNA AND CONTAI -I Block Under Tamluk Division PHE Dte. Under Purba Medinipur District. | Assistant Engineer | Junior Engiener,Junior Engineer | ORD/000538/2023-2024 | 1937/TD | 16/08/2023 | 28/03/2026 | MACKINTOSH BURN LIMITED | 10310.59 | 14.85 | 0.14 | 75
3 | PURBA MEDINIPUR | Contai-I | Tamluk Division | SYAMRAIBAR AND IT'S ADJOINING MOUJAS PWSS | SM/12886 | New | Material Requisition To Resource Division |  |  | RTOR000168/2022-2023 | 2391/TD | 16/01/2023 | 16/01/2023 | Resource Division | 18.29 | 0 | 0 | 0
4 | PURBA MEDINIPUR | Contai-I | Tamluk Division | SYAMRAIBAR AND IT'S ADJOINING MOUJAS PWSS | SM/12886 | New | Preparation of design based on soil test report and submission of drawing of foundation for construction of 150 cum RCC OHR at Syamraibar PWSS at Contai-I Block under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000154/2024-2025 | 2065/TD | 24/06/2024 | 04/07/2024 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.95 | 0.95 | 100 | 100
5 | PURBA MEDINIPUR | Contai-I | Tamluk Division | SYAMRAIBAR AND IT'S ADJOINING MOUJAS PWSS | SM/12886 | New | Material Requisition To Resource Division |  |  | RTOR000067/2024-2025 | 2978/TD | 12/09/2024 | 12/09/2024 | Resource Division | 6.44 | 0 | 0 | 0
6 | PURBA MEDINIPUR | Contai-I | Tamluk Division | SYAMRAIBAR AND IT'S ADJOINING MOUJAS PWSS | SM/12886 | New | Restoration of damaged road work under WBSRDA, Purba Medinipur after laying of pipe line by PHE for different Piped Water Supply Scheme under Tamluk Division, PHE Dte. |  |  | BILL/01161/2024-2025 | BP-2024-25-607 | 30/10/2024 | 30/10/2024 | EXE-OFFICER, WBSRDA PURBA MEDINIPUR | 60.85 | 0 | 0 | 0
7 | PURBA MEDINIPUR | Contai-I | Midnapore Mechanical | SYAMRAIBAR AND IT'S ADJOINING MOUJAS PWSS | SM/12886 | New | Quotation Bill for New Service connection at T/W NO-I Of SHYAMRAIBAR W/S Scheme under MMD, PHE, Dte. Block- CONTAI-I, WBSEDCL SUPPLY OFFICE: CONTAI C.C.C. Ref. Memo No- 2005011621/QUOT/03 DT. 17-12-2024 Application NO- 2005011621 Application type-New connection Consumer Id- 204475366 |  |  | BILL/03861/2024-2025 | C012539048842 | 21/01/2025 | 21/01/2025 | WBSEDCL | 3.94 | 0 | 0 | 0
Total | [13 empty] | 10422.67 | 23.16 | 0.22