## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Contai-I | Tamluk Division | SYAMRAIBAR AND IT'S ADJOINING MOUJAS PWSS | SM/12886 | New | Material Requisition To Resource Division |  |  | RTOR000168/2022-2023 | 2391/TD | 16/01/2023 | 16/01/2023 | Resource Division | 18.29 | 0 | 0 | 0
2 | PURBA MEDINIPUR | Contai-I | Midnapore Mechanical | SYAMRAIBAR AND IT'S ADJOINING MOUJAS PWSS | SM/12886 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for SYAMRAIBAR and ADJOINING MOUJAS, Block ¿ Contai I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division | ORD/001399/2022-2023 | 2410/W/MMD | 31/12/2022 | 29/06/2023 | SUJOY RANJAN BHOWMICK | 21.62 | 7.35 | 34.02 | 35
3 | PURBA MEDINIPUR | Contai-I | Tamluk Division | SYAMRAIBAR AND IT'S ADJOINING MOUJAS PWSS | SM/12886 | New | Preparation of design based on soil test report and submission of drawing of foundation for construction of 150 cum RCC OHR at Syamraibar PWSS at Contai-I Block under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000154/2024-2025 | 2065/TD | 24/06/2024 | 04/07/2024 | GEOTECHNICAL ENGINEERS CONSORTIUM | 0.95 | 0.95 | 100 | 100
4 | PURBA MEDINIPUR | Contai-I | Tamluk Division | SYAMRAIBAR AND IT'S ADJOINING MOUJAS PWSS | SM/12886 | New | Material Requisition To Resource Division |  |  | RTOR000067/2024-2025 | 2978/TD | 12/09/2024 | 12/09/2024 | Resource Division | 6.44 | 0 | 0 | 0
Total | [13 empty] | 47.29 | 8.31 | 17.57