## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Egra-I | Tamluk Division | JUMKI AND ADJOINING MOUJAS PWSS | SM/12995 | New | Material Requisition To Resource Division |  |  | RTOR000316/2022-2023 | 2971/TD | 27/02/2023 | 27/02/2023 | Resource Division | 19.96 | 0 | 0 | 0
2 | PURBA MEDINIPUR | Egra-I | Midnapore Mechanical | JUMKI AND ADJOINING MOUJAS PWSS | SM/12995 | New | Quotation Bill for New Service connection at T/W NO-II Of JUMKI W/S Scheme under MMD, PHE, Dte. Block- EGRA-I, WBSEDCL SUPPLY OFFICE: CHORPALIA C.C.C. Ref. Memo No- 2004674807/QUOT/03 DT. 09-04-2024 Application NO- 2004674807 Application type-New connection Consumer Id- 204269878 |  |  | BILL/00504/2024-2025 | BP-2024-25-87 | 24/04/2024 | 24/04/2024 | WBSEDCL | 4.9 | 0 | 0 | 0
3 | PURBA MEDINIPUR | Egra-I | Midnapore Mechanical | JUMKI AND ADJOINING MOUJAS PWSS | SM/12995 | New | Quotation Bill for New Service connection at T/W NO-I Of JUMKI W/S Scheme under MMD, PHE, Dte. Block- EGRA-I, WBSEDCL SUPPLY OFFICE: CHORPALIA C.C.C. Ref. Memo No- 2004674743/QUOT/03 DT. 09-04-2024 Application NO- 2004674743 Application type-New connection Consumer Id- 204269918 |  |  | BILL/00505/2024-2025 | BP-2024-25-86 | 24/04/2024 | 24/04/2024 | WBSEDCL | 3.36 | 0 | 0 | 0
4 | PURBA MEDINIPUR | Egra-I | Midnapore Mechanical | JUMKI AND ADJOINING MOUJAS PWSS | SM/12995 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for JUMKI and ADJOINING MOUJAS, Block ¿ Egra I, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division | ORD/001360/2022-2023 | 2371/W/MMD | 31/12/2022 | 29/06/2023 | BHABANI PRASAD MANNA | 23.7 | 17.21 | 72.63 | 85
5 | PURBA MEDINIPUR | Egra-I | Tamluk Division | JUMKI AND ADJOINING MOUJAS PWSS | SM/12995 | New | Sinking of Tube Well , Laying distribution system, Pump House at Head work site & 2nd tube well site, Soil Test, OHR ( 250 Cum ) FHTC ( (1636 nos ) Boundary wall and Rising Main and 2 Years Maintenance under JJM with allied work for Jumki PWSS within Egra-I Block including supply of all labour & materials under Digha Sub-Division of Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000639/2023-2024 | 2485/TD | 26/09/2023 | 30/06/2026 | AJIT KUMAR SOM | 442.63 | 241.06 | 54.46 | 65
6 | PURBA MEDINIPUR | Egra-I | Tamluk Division | JUMKI AND ADJOINING MOUJAS PWSS | SM/12995 | New | Leftout pipeline to accommodate FHTC under JJM of Jumki Water Supply Scheme within Egra I Block under Digha Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000312/2024-2025 | 3156/TD | 27/09/2024 | 23/02/2025 | SOM CONSTRUCTION | 27.41 | 0 | 0 | 100
7 | PURBA MEDINIPUR | Egra-I | Tamluk Division | JUMKI AND ADJOINING MOUJAS PWSS | SM/12995 | New | Material Requisition To Resource Division |  |  | RTOR000014/2025-2026 | 2079/TD | 12/08/2025 | 12/08/2025 | Resource Division | 10.08 | 0 | 0 | 0
Total | [13 empty] | 532.03 | 258.27 | 48.54