## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to Accommodate FHTC under JJM in Ranisai PWSS under Ramnagar-I Block (Phase-III) | SM/13238 | Retrofitting | Relaying the Distribution pipe line (Damaged during the construction of RIDF road from Dakshin Purushottampur Khal Parh to House of Jugal Giri House) of Ranisai PWSS, Ramnagar- I Block under Digha Sub-Division of Tamluk Division , PHE Dte. in the district of Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000369/2022-2023 | 1336/TD | 16/09/2022 | 11/10/2022 | SUKOMAL BERA | 27.06 | 27.05 | 99.98 | 0
2 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to Accommodate FHTC under JJM in Ranisai PWSS under Ramnagar-I Block (Phase-III) | SM/13238 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000092/2023-2024 | 2995/TD | 29/11/2023 | 29/11/2023 | Resource Division | 2.24 | 0 | 0 | 0
3 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to Accommodate FHTC under JJM in Ranisai PWSS under Ramnagar-I Block (Phase-III) | SM/13238 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000036/2023-2024 | 2064/TD | 28/08/2023 | 28/08/2023 | Resource Division | 17.51 | 0 | 0 | 0
4 | PURBA MEDINIPUR |  | Midnapore Mechanical | Retrofitting to Accommodate FHTC under JJM in Ranisai PWSS under Ramnagar-I Block (Phase-III) | SM/13238 | Retrofitting | Quotation for new service connection at tw-III of Ranisai ws scheme under MMD PHE Dte,Block-Ramnagar-I, Digha CCC Application no-2004764426 Con ID-204324285 |  |  | BILL/01226/2024-2025 | C062416826632 | 18/06/2024 | 18/06/2024 | WBSEDCL | 4.3 | 0 | 0 | 0
5 | PURBA MEDINIPUR |  | Midnapore Mechanical | Retrofitting to Accommodate FHTC under JJM in Ranisai PWSS under Ramnagar-I Block (Phase-III) | SM/13238 | Retrofitting | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Retrofitting to Accommodate FHTC under JJM in Ranisai PWSS under Ramnagar-I Block (Phase-III) under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division,Sri Ujjal Kumar Dey, JE/Haldia Electrical Sub-Division. | ORD/001997/2022-2023 | 885/W/MMD | 27/03/2023 | 06/09/2026 | SUDIKSHA CONSTRUCTION | 12.37 | 3.05 | 24.64 | 10
6 | PURBA MEDINIPUR |  | Tamluk Division | Retrofitting to Accommodate FHTC under JJM in Ranisai PWSS under Ramnagar-I Block (Phase-III) | SM/13238 | Retrofitting | Laying of Distribution pipe line,Rising main pipe line, Pump House, Boundary Wall, Sinking of 3rd Tube Well with allied works of Ranisai & its adjoining mouzas W/S Scheme within Ramnagar - I Block under Digha Sub-Division of Tamluk Division, PHE Dte. Purba Medinipur district. | Assistant Engineer | Junior Engineer | ORD/000378/2023-2024 | 1027/TD | 07/06/2023 | 26/09/2025 | SWASTIK ENTERPRISE | 62.09 | 12.77 | 20.56 | 21
Total | [13 empty] | 125.57 | 42.86 | 34.14