## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Ramnagar - II | Tamluk Division | ISLAMPUR & IT'S ADJOINING MOUJAS PWSS | SM/13683 | New | Material Requisition To Resource Division |  |  | RTOR000157/2022-2023 | 2464/TD | 16/01/2023 |  | Resource Division | 24.12 | 0 | 0 | 0
2 | PURBA MEDINIPUR | Ramnagar - II | Tamluk Division | ISLAMPUR & IT'S ADJOINING MOUJAS PWSS | SM/13683 | New | Material Requisition To Resource Division |  |  | RTOR000143/2023-2024 | 103/TD | 05/01/2024 |  | Resource Division | 13 | 0 | 0 | 0
3 | PURBA MEDINIPUR | Ramnagar - II | Tamluk Division | ISLAMPUR & IT'S ADJOINING MOUJAS PWSS | SM/13683 | New | Laying distribution pipe line, & Accommodate FHTC (124 Nos) under JJM with allied work for Islampur & Its Adjoining Mouzas Water Supply Scheme within Ramnagar-II Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur ( Part-F ) | Assistant Engineer | Junior Engineer | ORD/000868/2022-2023 | 3181/TD | 10/03/2023 | 25/03/2023 | ANUPAM CONSTRUCTION | 19.87 | 6.04 | 30.41 | 60
4 | PURBA MEDINIPUR | Ramnagar - II | Tamluk Division | ISLAMPUR & IT'S ADJOINING MOUJAS PWSS | SM/13683 | New | Laying distribution pipe line, Pump House, Boundary Wall soil investigation, 300 Cum OHR ( with pile foundatio ) & Accommodate FHTC ( 414 Nos) under JJM with allied work for Islampur & Its Adjoining Mouzas Water Supply Scheme within Ramnagar-II Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur (Part-A) | Assistant Engineer | Junior Engineer | ORD/000412/2023-2024 | 1098/TD | 08/06/2023 | 05/12/2023 | FIROZ KHAN | 199.26 | 0 | 0 | 0
5 | PURBA MEDINIPUR | Ramnagar - II | Tamluk Division | ISLAMPUR & IT'S ADJOINING MOUJAS PWSS | SM/13683 | New | Laying distribution pipe line, & Accommodate FHTC (124 Nos) under JJM with allied work for Islampur & Its Adjoining Mouzas Water Supply Scheme within Ramnagar-II Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur ( Part-E ) | Assistant Engineer | Junior Engineer | ORD/000866/2022-2023 | 3180/TD | 10/03/2023 | 25/03/2023 | ANUPAM CONSTRUCTION | 19.85 | 6.03 | 30.39 | 62
6 | PURBA MEDINIPUR | Ramnagar - II | Tamluk Division | ISLAMPUR & IT'S ADJOINING MOUJAS PWSS | SM/13683 | New | Laying distribution pipe line, & Accommodate FHTC ( 124 Nos) under JJM with allied work for Islampur & Its Adjoining Mouzas Water Supply Scheme within Ramnagar-II Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur ( Part-G ) | Assistant Engineer | Junior Engineer | ORD/000071/2023-2024 | 173/TD | 11/04/2023 | 26/04/2023 | AYSAN KHAN | 19.97 | 0 | 0 | 0
7 | PURBA MEDINIPUR | Ramnagar - II | Tamluk Division | ISLAMPUR & IT'S ADJOINING MOUJAS PWSS | SM/13683 | New | Laying distribution pipe line, & Accommodate FHTC ( 124 Nos) under JJM with allied work for Islampur & Its Adjoining Mouzas Water Supply Scheme within Ramnagar-II Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur ( Part-H ) | Assistant Engineer | Junior Engineer | ORD/000869/2022-2023 | 3182/TD | 10/03/2023 | 25/03/2023 | MAHAMAYA TIMBER AND CONSTRUCTION | 6.81 | 2.96 | 43.5 | 95
8 | PURBA MEDINIPUR | Ramnagar - II | Tamluk Division | ISLAMPUR & IT'S ADJOINING MOUJAS PWSS | SM/13683 | New | Laying of Balance Distribution HDPE Pipe Line(225 mm dia) for Islampur Piped Water Supply Scheme due to Revised drawing within Ramnagar-II Block under Digha Sub-Division of Tamluk Division,PHED , Purba Medinipur. | Assistant Engineer | Junior Engineer | ORD/000706/2023-2024 | 2872/TD | 17/11/2023 | 07/12/2023 | A. K. SIKDAR | 9.42 | 4.68 | 49.72 | 99
9 | PURBA MEDINIPUR | Ramnagar - II | Tamluk Division | ISLAMPUR & IT'S ADJOINING MOUJAS PWSS | SM/13683 | New | Laying distribution pipe line, & Accommodate FHTC ( 538 Nos) under JJM with allied work for Islampur & Its Adjoining Mouzas Water Supply Scheme within Ramnagar-II Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur (Part-D) | Assistant Engineer | Junior Engineer | ORD/000536/2023-2024 | 1839/TD | 08/08/2023 | 17/09/2023 | MRINAL KANTI PRADHAN | 84.49 | 26.08 | 30.87 | 65
10 | PURBA MEDINIPUR | Ramnagar - II | Central Drilling | ISLAMPUR & IT'S ADJOINING MOUJAS PWSS | SM/13683 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 17/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
11 | PURBA MEDINIPUR | Ramnagar - II | Tamluk Division | ISLAMPUR & IT'S ADJOINING MOUJAS PWSS | SM/13683 | New | Laying distribution pipe line, & Accommodate FHTC ( 538 Nos) under JJM with allied work for Islampur & Its Adjoining Mouzas Water Supply Scheme within Ramnagar-II Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur (Part-C) | Assistant Engineer | Junior Engineer | ORD/000865/2022-2023 | 3179/TD | 10/03/2023 | 19/04/2023 | LOKENATH ENTERPRISES | 84.26 | 27.05 | 32.11 | 65
12 | PURBA MEDINIPUR | Ramnagar - II | Tamluk Division | ISLAMPUR & IT'S ADJOINING MOUJAS PWSS | SM/13683 | New | Laying distribution pipe line, Pump House, Boundary Wall & Accommodate FHTC ( 238 Nos) under JJM with allied work for Islampur & Its Adjoining Mouzas Water Supply Scheme within Ramnagar-II Block under Digha Sub-Division of Tamluk Division , PHED , Purba Medinipur (Part-B) | Assistant Engineer | Junior Engineer | ORD/000284/2023-2024 | 563/TD | 12/05/2023 | 11/07/2023 | LOKENATH ENTERPRISES | 119.04 | 43.61 | 36.63 | 60
Total | [13 empty] | 21939.84 | 116.46 | 0.53