## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA MEDINIPUR | Deshopran | Tamluk Division | PURBA MAHAMMADPUR & IT'S ADJOINING MOUJAS | SM/13686 | New | Material Requisition To Resource Division |  |  | RTOR000205/2022-2023 | 2407/TD | 16/01/2023 | 16/01/2023 | Resource Division | 18.82 | 0 | 0 | 0
2 | PURBA MEDINIPUR | Deshopran | Midnapore Mechanical | PURBA MAHAMMADPUR & IT'S ADJOINING MOUJAS | SM/13686 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Water Based Piped Water Supply Scheme for PURBA MAHAMMADPUR and ADJOINING MOUJAS, Block ¿ Deshopran, District - Purba Medinipur under JJM Program under MMD PHE Dte. | Sri Srinath Ranjan Ghosh, AE/Haldia Electrical Sub-Divi | Sri Mrityunjoy Paria, JE/Haldia Electrical Sub-Division | ORD/001667/2022-2023 | 550/W/MMD | 20/03/2023 | 01/03/2025 | DEBJYOTI BASU | 21.62 | 11.03 | 51.03 | 55
3 | PURBA MEDINIPUR | Deshopran | Tamluk Division | PURBA MAHAMMADPUR & IT'S ADJOINING MOUJAS | SM/13686 | New | Preparation of design based on soil test report and submission of drawing of foundation for construction of 150 cum RCC OHR at Purba Mahammadpur PWSS at Deshpran Block under Tamluk Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001275/2023-2024 | 1049/TD | 15/03/2024 | 25/03/2024 | ASTER CONSULTANCY | 0.95 | 0.95 | 100 | 100
4 | PURBA MEDINIPUR | Deshopran | Tamluk Division | PURBA MAHAMMADPUR & IT'S ADJOINING MOUJAS | SM/13686 | New | Material Requisition To Resource Division |  |  | RTOR000075/2024-2025 | 2973/TD | 12/09/2024 | 12/09/2024 | Resource Division | 6.99 | 0 | 0 | 0
5 | PURBA MEDINIPUR | Deshopran | Midnapore Mechanical | PURBA MAHAMMADPUR & IT'S ADJOINING MOUJAS | SM/13686 | New | Quotation Bill for New Service connection at T/W NO-I Of PURBA MAHAMMADPUR W/S Scheme under MMD, PHE, Dte. Block- CONTAI-II, WBSEDCL SUPPLY OFFICE: MUKUNDAPUR C.C.C. Ref. Memo No- 2004877670/QUOT/03 DT. 12-09-2024 Application NO- 2004877670 Application type-New connection Consumer Id- 204397980 |  |  | BILL/02497/2024-2025 | C092445105167 | 30/09/2024 | 30/09/2024 | WBSEDCL | 12.11 | 0 | 0 | 0
6 | PURBA MEDINIPUR | Deshopran | Tamluk Division | PURBA MAHAMMADPUR & IT'S ADJOINING MOUJAS | SM/13686 | New | Sinking of Tube Well ,Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works with laying distribution system , Pump House ,Boundary Wall & Providing Functional Household Tap Connection (3734 Nos), including 2 years Operation & Maintenance For Purba Mukundapur, Dakshin Kadua, Purba Mahammadpur Pipe water supply Scheme within Deshapran Block Under Tamluk Division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000492/2023-2024 | 1593/TD | 21/07/2023 | 01/07/2025 | JAYANTA KUMAR MONDAL | 1264.74 | 155.3 | 12.28 | 30
Total | [13 empty] | 1325.24 | 167.29 | 12.62